## Abstract
Abstract | [8 empty] | Annexure-2
Sr. no. | Description |  | No. of Works | Expenditure upto 31.03.2022 (in lacs) | Expenditure in Year 2022-23 (in lacs) | Expenditure in Year 2023-24 (in lacs) | Expenditure in Year 2024-25 (in lacs) | Expenditure in Year 2025-26 (in lacs) | Total during 3rd MYT Control Period (in lacs)
1 | Annex. I | West Zone | 102 | 280.76 | 8804.046 | 8035.134 | 8816.77 | 4961.2 | 21813.104
2 | Annex. II | South Zone | 107 | 728.1 | 11685.4088 | 10589.3382 | 3104.204 | 1151.542 | 14845.0842
3 | Annex. III | Central Zone | 56 | 82.12 | 3700.2824 | 4150.6096 | 5273.425 | 2384.895 | 11808.9296
4 | Annex. IV | North Zone | 94 | 639.75 | 6346.39 | 6855.7068 | 4825.12 | 1191.48 | 12872.3068
5 | Annex. V | Border Zone | 52 | 518.96 | 4644.19 | 5454.48 | 2402.64 | 0 | 7857.12
6 | Annex. VI | Works to be planned | 93 |  |  |  | 15470 | 35190.57 | 50660.57
Total |  |  | 504 | 2249.69 | 35180.3172 | 35085.2686 | 39892.159 | 44879.687 | 119857.1146
|  | rounded off in line with PSPCL's submission in the petition | [6 empty] | Rs. 1200 Cr.
|  |  |  | 22.4969 | 351.8032 | 350.8527 | 398.9216 | 448.7969
1198.5711
[7 empty] | 154.7 | 351.9057
[6 empty] | 350.8527 | 553.6216 | 800.7026

## Completed works (hidden)
Annexure-A
Sr.no. | TWL sr.no. 2022-23 | Annex. | Zone | Circle Name | MYT 2020-21 | MT 2021-22 | MT 2022-23 | Name of Work | Scope of Work | Estt. Cost (in lacs) | Estt. Cost (in lacs) | Status | Year
1 | 1/SZ/2022-23 Annexure-A | A | SZ | Barnala |  |  |  | 66 KV Line from 66 KV S/Stn Kupkalan to 66 KV S/Stn Ahmedgarh (0.125 sq", 10.5 KM / SC on RP) | Augmentation of existing ACSR 10.5 km with 0.2 sq." by replacement of HRP line with SC on DC towers 66 KV line | 283.08 -31.71 | 251.37 | Work completed | 2022-23
2 | 2/SZ/2022-23 Annexure-A | A | SZ | Patiala |  |  |  | a) 66 KV S/Stn Chappar (New) b) T-off of existing 66 KV line from 220 KV S/Stn Bhateri to 66 KV S/Stn Ghanour for new 66 KV S/Stn Chappar c) 66 KV Line Bay at new 66 KV S/Stn Chappar | a) 1 x 12.5 MVA, 66/11 KV b) 3.5 KM / 0.2 sq", SC on DC c) 1 No. | 219.92 94.36 29 | 343.28 | Work completed in 06/17 | 2022-23
3 | 3/SZ/2022-23 Annexure-A | A | SZ | Patiala |  |  |  | a) 66KV line from 220 KV S/Stn Focal Point Nabha to 66 KV S/Stn Samundgarh. b) 66 KV Line Bays (i) 1 No. at 66 KV S/Stn Samundgarh (ii) 1 No. at 220 KV S/Stn Focal Point Nabha | a)13.5 KM / 0.2 sq" , SC on DC b) (i) 1 No. (ii) To be executed by PSTCL | 363.96 29 | 392.96 | Work completed in 05/19 | 2022-23
4 | 4/SZ/2022-23 Annexure-A | A | SZ | Ropar | 111 |  |  | 66 KV S/Stn Kurali (Aug) 2 x 20 MVA, 66/11 KV | Addl 12.5 MVA, 66/11 KV, T/F | 203.61 | 203.61 | Work completed on 29.06.2021 | 2022-23
5 | 5/SZ/2022-23 Annexure-A | A | SZ | Ropar |  |  |  | a) 66 KV S/Stn Nalhoti (New) (including 66 KV Line Bay with Isolators only) b) Erection of 66 KV Line from Tower No. 53(of 66KV Line from 132 KV Anandpur Sahib to 66 KV Grid Nurpur Bedi) upto 66 KV Grid Nalhoti | a) 1x12.5 MVA, 66/11 KV b) 10 KM / 0.2Sq" SC on DC towers | 219.92 269.6 | 489.52 | Work completed in 12/19 | 2022-23
6 | 7/SZ/2022-23 Annexure-A | A | SZ | Ropar |  |  |  | 66 KV Line from 132 KV S/S Anandpur Sahib to 66 KV S/S Nurpur Bedi (0.1 sq" / 15 KM, SC on RP) | Augmentation of existing ACSR 15 km with 0.2 sq." by replacement of HRP line with SC on DC towers 66 KV line | 404.4 -45.3 | 359.1 | Work completed in 7/19 | 2022-23
7 | 9/SZ/2022-23 Annexure-A | A | SZ | Sangrur | 22 |  |  | a) 66 KV DC tower line from 220KV S/S Sunam to join near solid tap point for 66KV Sheron SC on DC line b) Stringing of 2nd Ckt from T-off ( as per 'a' above) to 66KV Sheron (Under erection) c) DC tower link line from 66KV Sheron to 66KV Longowal with stringing of 1 Ckt direct from T-off point as per 'a' above upto Longowal and 2 Ckt via 66KV Sheron d) 66 KV bays (2 no. each at Longowal end and 1 bay at Sheron) | 1KM / 0.2sq" DC on DC tower line 3.5KM / 0.2sq" line 7KM / 0.2sq" DC on DC line 5 no. | 36.39 32.97 254.73 145 | 469.09 | Work completed and charged of part a and b. WORK COMPLETED of part C completed in 05.2020 | 2022-23
8 | 11/SZ/2022-23 Annexure-A | A | SZ | Mohali |  |  |  | 1) 66 KV line from 220 KV S/Stn Lalru to 66 KV S/Stn Alamgir SC on DC (0.2Sq" / 4.75 Km) 2) 66 KV Line Bays (i) 1 No. at 66 KV S/Stn Alamgir (ii) 1 No. at 220 KV S/Stn Lalru | a) Conversion of 66KV existing line from 220 KV S/S Lalru to 66KV Handesra (SC on DC 0.2Sq") to Multi cirkit towers (0.2Sq" / 1.5Km) upto the crossing point of 66KV Dhulkot - Chandigarh Line with stringing of two ckt. For 66KV S/S Alamgir. b) New DC on DC Line (7.5 KM / 0.2 Sq' ) from crossing point of 66KV Dhulkot - Chandigarh Line as mentioned in (a) above upto Tower no. 19 of existing 66KV Lalru- Alamgir Alamgir Line. c) Stringing of 2nd Ckt. ( 0.2 sq " /1.0KM) from Tower no. 19 upto 66 KV S/S Alamgir. b) (i) 1 No. (ii) To be executed by PSTCL | 147.285 14.13 272.92 9.42 29 | 472.755 | Work completed AND LINE CHARGED ON 03/2021 | 2022-23
9 | 12/SZ/2022-23 Annexure-A | A | SZ | Barnala | 23 |  |  | 66 KV line from 220 KV S/S Malerkotla to 66 KV S/S Malerkotla (10.3 KM / 0.125 sq", SC on RP) | a) Stringing of 2nd circuit from 220 KV S/Stn. Malerkotla to Tower No.38 of Malerkotla- Dhuri(Banbhora) line 7.5 km b) b) 4.5 km SC/DC line, 0.2 Sq" ACSR from tower location No.38 Dhuri (Banbhora) 66 KV S/Stn Malerkotla using same ROW. c) 1.1 KM 240 sq. mm, 66 KV U/G cable SC by using different ROW | 70.65 121.3 -13.59 276.5 | 454.86 | Line charged on 13.02.2022 | 2022-23
10 | 13/SZ/2022-23 Annexure-A | A | SZ | Mohali |  |  |  | a) 66 KV S/S Ramgarh Bhuda (New) b) LILO of existing 66 KV Banur Bhabat Line for new 66 KV S/Stn Ramgarh Bhuda c) 66 KV Line Bay for LILO arrangements at new 66 KV S/Stn Ramgarh Bhuda d ) Cost of land | a) 1x20MVA, 66/11KV T/F b) 4.593Ckt.km/ 66KV U/G cable of 240 sq.mm (Single ckt.) + 1 no D 60 tower for T-off arrangement 2 nos. | 258.6 545 58 40.9 | 902.5 | Sub-Station charged in 09/2020 | 2022-23
11 | 14/SZ/2022-23 Annexure-A | A | SZ | Mohali |  |  |  | a) 66 KV Haripur Kura (New) b) LILO of 66 KV Line Ckt-1 0.4Sq" from 220KV Saidpura to 220 KV Lalru at 66KV S/S Haripur Kura (New) c) 66 KV Line Bays for LILO arrangement at 66 KV Grid Haripur Kura | a) 12.5MVA, 66/11 KV b) 1.2 Km / 0.4 sq" DC on DC Towers c) 2 Nos. Cost of Land | 219.9 82.28 58 48.19 | 408.37 | Sub-Station charged in 11/19 | 2022-23
12 | 15/SZ/2022-23 Annexure-A | A | SZ | Patiala |  |  |  | 66 KV Sub-Station Sanauri Adda (New) T-off of existing 66 KV Passiana - Sanaur Line for new 66 KV S/Stn Sanauri Adda [T-Off from TL No. 247 of 66 KV Passiana-Sanaur Line is proposed for new 66 KV S/Stn Sanauri Adda i.e.0.8 km +0.390km (SC on DC) + 0.380 km (240 sq. mm 66 KV U/G Cable) | 20 MVA, 66/11 KV T/F (including 1 No. 66 KV Line Bay with 66 KV Circuit Breaker) a) erection of overhead 66 KV Line 800 metres / 0.2 sq" / SC on DC from Point A to B b) erection of 380 metres 66 KV Underground Cable 240 sq. mm XLPE Cable from point B to C c) erection of overhead 66 KV Line 390 metres / 0.2 sq" / SC on DC from Point C to D (nomenclature of points A to D as specified in the vetted sketch formulated by SE/DS Circle, PSPCL, Patiala and Dy CE / TL Circle, PSPCL, Patiala furnished by SE / DS Circle, PSPCL, Patiala vide his office memo no. 5727 dated 17.04.2018) | 302.5 21.57 95.53 10.51 | 430.11 | Sub-Station charged in 08/19 | 2022-23
13 | 16/SZ/2022-23 Annexure-A | A | SZ | Sangrur |  |  | 67 | a) 66KV Line from 220 KV S/Stn BBMB Sangrur to 66 KV S/S Bhawanigarh (Ckt. I) (19.6 KM/ 0.125 sq", SC on RP) b) 1 No. 66 KV Line Bay at 220 KV S/Stn BBMB Sangrur. | a) Stringing of second ckt (0.2 sq"/ 10 KM) on already planned SC on DC from T-off point for 220 KV S/Stn Bhawanigarh to 220 KV S/Stn BBMB Sangrur. b) 1 No. (The matter may be taken by CE / TS, PSPCL with BBMB authorities for the requisite provision of 66 KV Line Bay (1 No.) at 220 KV S/Stn BBMB Sangrur) | 94 29 | 123 | Work Completed and Line energized . | 2022-23
14 | 25/SZ/2022-23 Annexure-A | A | SZ | Barnala |  |  | 74 | Stringing & Sagging of 66 KV line from 220 KV S/S Handiaya to 66 KV S/S Tapa | a) Stringing of 2nd ckt (0.2sq” / 14 Km) on DC towers along with 2 no. new D-60 towers, one at 66 KV S/S Tapa and one at 220 KV S/S Handiaya & 50 ckt mtr ACSR 0.2sq” 1no. 4 Rail Pole Structure a) & 20 ckt mtr ACSR 0.125sq” to be dismnatled. b) ((i) 1 no. 66 KV bay at 66 KV S/S Tapa (ii) 1 no. 66 Kv bay at 220 KV S/S Handiaya | 143.88 29 To be executed by PSTCL | 172.88 | Work completed and line energized during 05/2022. | 2022-23
15 | 28/SZ/2022-23 Annexure-A | A | SZ | Patiala |  |  |  | a) 66 KV S/Stn Bhasmara (New) (with 1 No. 66 KV Line Bay with Isolators only) b) T-off of existing 66 KV line from 220 KV S/Stn Devigarh to 66 KV S/Stn Rohar Jagir for new 66 KV S/Stn Bhasmara | 1 x 12.5 MVA, 66/11 KV 5.5 km / 0.2 sq"; SC on DC Towers. | 219.9 148.3 | 368.2 | S/Stn. commissioned in 03/2021 | 2022-23
16 | 34/SZ/2022-23 Annexure-A | A | SZ | Sangrur |  |  |  | Provision of 2 no. 66 KV lline bays (with 66 KV ckt. Breaker) at 66 KV grid S/S Khanori Shergarh). | a) Conversion of existing isolated controlled arrangement into 1 no arrangement into 1 no I/C 66 KV line bay with ckt. Breaker at 66 Kv S/S Khanori (Shergarh) for 66 Kv Patran Khanori ckt. 1 b) 1 no. additional 66 KV line bay with ckt Breaker for 66 KV Patran Khanori ckt2 at 66 KV S/S Khanori (Shergarh). | 22 29 | 51 | Bay work is completed | 2022-23
17 | 35/SZ/2022-23 Annexure-A | A | SZ | Ropar |  |  | 70 | a) Ghulal - Bhaini Sahib b) 66 KV line Bays (i) 1 No. at 220 KV S/Stn Ghulal (ii) 1 No. at 66 KV S/Stn Bhaini Sahib | a) 0.175 ckt-Km 66KV XLPE U/G cable of 240mm2 b) 5.851 Km /0.2sq” SC on DC towers by replacing existing idle rail pole line (using same ROW) c) Re-erection of some portion of 66KV ST Cotton + Shiva and Malwa + Arty with 1 no. 2-D-60 Multickt. Towers. Dismantlement of existing idle HRP line 4.391 Km / 0.1sq” 1 No. 66KV bay at 220 KV S/Stn Ghulal NOTE:- To be executed by PSTCL 1 No. 66KV bay at S/Stn Bhaini Sahib | 44 157.7 41.04 -7.5 29 | 264.24 | Line charged on 29.03.2022 | 2022-23
18 | 37/SZ/2022-23 Annexure-A | A | SZ | Barnala |  |  |  | a) 66 KV S/Stn Jhaloor (New) [ including 1 No. 66 KV Line Bay (with isolators only) at new 66 KV S/Stn Jhaloor b) T-off from existing ‘IDLE 66 KV line from 66 KV S/Stn Kuthala to 66 KV S/Stn Katron for new 66 KV S/Stn Jhaloor | 1 x 12.5 MVA, 66/11 KV New 6 Km 0.2sq”/SC on DC T-off from existing 220 KV Handiaya to 220KV Mehal Kalan idle line (DC on DC till 9 Km and beyond this SC on DC 0.2sq” tower line ) for newly proposed 66 KV S/S Jhaloor. | 219.92 198 | 417.92 | S/Stn. commissioned on 30.05.2022. | 2022-23
19 | 38/SZ/2022-23 Annexure-A | A | SZ | Barnala | 136 |  |  | 220 KV Malerkotla - Guara - Amargarh - Manvi 0.2 sq"/ 5.5 KM; SC on DC | a) Stringing of 2nd ckt. 0.2sq”/5.5 Km) on DC towers. b) Erection of 5 no. towers (2-D – 60, X-type, D 60+ 6m, D2 + 6m, 2D 30) needed for stringing of 2nd ckt and for shifting of gantries as per attached sketch. c) 1 no. new 66 KV bay required at 220 KV Malerkotla S/S to be planned by PSTCL. | 51.81 52 ---- | 103.81 | Work completed and line energized during 05/2022. | 2022-23
20 | 39/SZ/2022-23 Annexure-A | A | SZ | Patiala. |  |  |  | 66 KV line from 220 KV grid S/S Rajpura to 66 Kv grid S/S Focal Point, Rajpura. | a) Replacement of existing 66 KV Dharamgarh line SC on DC/ 0.2sq" emanting from 220 KV grid Rajpura from point H-I (4Km), with 3 ckts. of 0.2sq" on MCT (1 ckt. For 66 KV S/S Dharamgarh and 2 no. ckt. For 66 KV grid Focal Point, Rajpura. b) Replacement of existing 66 KV Dhulkot to Patiala idle line (SC/SC 0.1sq"), from point I - J (0.5Km) with 0.2sq"/DC on DC. c) Replacement of existing 66 KV DC on DC line (point J - K i.e. 6.5 Km) with 4 ckts. of 0.2sq" on MCT (2 ckt. for 66 KV S/S old Rajpura and 2 no. ckts. for 66 KV grid Focal Point, Rajpura. d) 2 no. 66 KV line bays (with 66 KV ckt. breakers) at 220 Kv grid S/S Rajpura for the above cited proposed 66 KV line arrangements. | 309.76 -12.08 14.17 -1.51 503.36 -19.63 To be executed by PSTCL | 794.07 | Line charged on 22.06.2022. | 2022-23
21 | 40/SZ/2022-23 Annexure-A | A | SZ | Mohali |  |  |  | Additional T/f work at 66 KV grid S/S Sunny Enclave, Sector-125, Mohali (existing 1x20 66/11 KV T/F | Additional 1 no. 20 MVA 66/11 KV P/T/F | 285.93 | 285.93 | Work Completed on 28.03.2022 | 2022-23
22 | 42/SZ/2022-23 Annexure-A | A | SZ | Ropar |  | 54 |  | 66 KV Grid S/Stn Bhagpur (1 x 20 MVA, 66/11 KV) | Addl 20 MVA, 66 / 11 KV | 285.93 | 285.93 | Work completed on 24.03.2022 | 2022-23
23 | 43/SZ/2022-23 Annexure-A | A | SZ | Sangrur | 117 |  |  | 66 KV Grid S/Stn Bhalwan (2 x 20 MVA, 66/11 KV) | 31.5 MVA, 66/11 KV T/F to replace 20 MVA, 66/11 KV T/F | 199.77 | 199.77 | Work completed on 29.03.2022 | 2022-23
24 | 44/SZ/2022-23 Annexure-A | A | SZ | Barnala |  |  |  | 66 KV S/Stn Malerkotla (Aug) 2 x 20 MVA, 66/11 KV | Addl. 20 MVA , 66/11 KV | 285.93 | 285.93 | Work completed on 09.08.2021 | 2022-23
25 | 45/SZ/2022-23 Annexure-A | A | SZ | MOH |  |  |  | 66 KV S/S Dhakoli 1x31.5 MVA + 1x20 MVA | Aug. of 20 MVA 66/11 KV T/F with 31.5MVA 66/11 KV | 199.77 | 199.77 | Work completed on 25.03.2022 | 2022-23
26 | 46/SZ/2022-23 Annexure-A | A | SZ | BNL |  |  |  | 66KV S/S Barnala (2x20 MVA + 1x12.5 MVA) | Aug.of 12.5 MVA T/F with 20 MVA 66/11 KV Barnala. | 157.03 | 157.03 | Work completed on 04.06.2021 | 2022-23
27 | 47/SZ/2022-23 Annexure-A | A | SZ | MOH |  |  |  | 66 KV S/S Haripur Kurran (1x12.5 MVA) | Aug.of 12.5 MVA T/F with 20 MVA , 66/11 KV | 157.03 | 157.03 | Work completed on 04.04.2022 | 2022-23
28 | 1/NZ/2022-23 /Annex. A | A | NZ | HSP | 63 |  |  | 66KV line from MPH Stage-II to MPH--Stage-I (66KV MPH V to MPH IV) | 10.127 KM/ 0.2sq'' SC on DC towers Note:- 430.81 lac cost includes 215 lac as expediture due to changed route | 488.0239 | 488.0239 | Work completed in 04/19 | 2022-23
29 | 2/NZ/2022-23 /Annex. A | A | NZ | HSP |  |  |  | a)66 KV line from 132 KV Bhogpur----66 KV Bullowal 15+3Km/HRP/Towers 0.15sq'' 2 No. Bays | Aug.of ACSR 15km with 0.2sq" by replacement of HRP line with SC on DC towers Deleted as not required | 404.4 -45.3 | 359.1 | Work completed in 04/19 | 2022-23
30 | 3/NZ/2022-23 /Annex. A | A | NZ | JLD |  |  |  | 33KV line from 132KV S/S Phagwara to 33KV G.T. Rd. Phagwara 3.4 KM/0.1Sq'' HRP line existing | i)6.871Km/0.2sq'' SConDC towers ii)1Km/0.2sq'' on WZ type towers iii)1.505Km/240mm2 Underground cable | 185.24 26.96 378.36 | 590.56 | Work completed in 09/19 | 2022-23
31 | 4/NZ/2022-23 /Annex. A | A | NZ | KPT |  |  |  | a)66KV line from 220KV S/S NoorMehal to 66KV Shanker b) 66KV bays 1 No. at 66 KV Shanker 1 No. at 220 KV Noor Mehal | 10KM/0.2sq"/SC on DC towers line new 1 No. To be planned by PSTCL | 269.60 29.00 | 298.6 | Work completed in 07/20 | 2022-23
32 | 10/NZ/2022-23 /Annex. A | A | NZ | JLD |  |  |  | a)66KV Line to connect 220KVS/S Kartarpur to 66KV Ring Main between 66KV S/S Focal Point & 66KV Maqsoodpur b) 66KV bay 2No. at 220KV Kartarpur | i)8KM /0.4 Sq" DC on DC Towers ii) 2 KM Under ground cable (set of 8 Cables)of equilivent size To be planned by PSTCL | 398.64 864.00 | 1262.64 | Work completed in 01/2021 | 2022-23
33 | 11/NZ/2022-23 /Annex. A | A | NZ | KPT |  |  |  | a)66KV Kanjli--Nangal Line LILO at 66 KV S/S Dainwind b) 66KV bays 2 No. at 66 KV Dainwind | 0.2 Km/ SC on DC line 0.2 Sq" ACSR. 2nos. | 5.39 58.00 | 63.39 | Line charged on 13.03.2022 | 2022-23
34 | 12/NZ/2022-23 /Annex. A | A | NZ | KPT | 52 |  |  | a) 66KV Bays. 1no at 66KV S/S Tibba and 1no at 66 KV S/S Khallu (to use 66KV line already exists between these S/Stns) b) 66KV bays, 2 no at 66 KV S/S Ucha (to control 66 KV S/S Surukhpur and 66KVS/S Kallu) | 2 nos 2 nos | 58.00 58.00 | 116 | In 10/2020 completed. Bay work of Ucha completed in 04/2022. | 2022-23
35 | 14/NZ/2022-23 /Annex. A | A | NZ | KPT |  |  |  | a)66KV Link line from 66KV S/S Sarhali --- 66 KV S/S Bundala b) 66KV bays 1 No. at 66KV Sarhali 1 No. at 66KV Bundala | New 5Km/0.2Sq"ACSR/ SC on DC tower line 2 Nos | 134.80 58.00 | 192.8 | Work completed | 2022-23
36 | 16/NZ/2022-23/Annex. A | A | NZ | KPT |  |  |  | a)66KV Line from 66KV S/S Kala Sanghian---66KV S/S Chitti (New) b) 66KV bays 1 No. at 66KV Kala Sanghian 1 No. at 66KV Chitti | 6.5Km/ SC on DC towers line 0.2 Sq" ACSR. 2 Nos | 175.24 58.00 | 233.24 | Work completed | 2022-23
37 | 18/NZ/2022-23 /Annex. A | A | NZ | JLD |  |  |  | a)66KV single circuit 2.0Km,66KV Underground cable 240mm2 T-off from BBMB —Tanda road 66 KV Ring Main Jalandhar to provide 2nd 66KV power source to 66KV Radial S/Stn.Jalandhar b) 66KV bays 1 No. at 66KV Radial Jal. | a) 2.0 Ckt-Km(1x4C) 66KV Underground cable 240mm2 1 No. | 502.80 29.00 | 531.8 | Work completed in 01/2020 | 2022-23
38 | 19/NZ/2022-23 /Annex. A | A | NZ | KPT |  |  |  | a)66KV S/S Sidhwan Dona (NEW) (including of 1 no. 66KV Bay) b) 8km / 0.2 sq'' /SC on DC towers 66KV line from existing 66KVS/S TalwandiMadho to 66KV proposed S/S SidhwanDona. c) 66KV line bay 1 No. at 66KV Talwandi Madho | 12.5 MVA, T/F 66/11 KV 8 km/ 0.2sq'' /SC on DC towers 66 KV line 1 no. | 219.92 215.68 29.00 | 464.6 | S/Stn. Commissioned in 11/2019. | 2022-23
39 | 22/NZ/2022-23 /Annex. A | A | NZ | NWSR |  |  |  | a)New 66 KV line from 220KV S/S Jadla--66KV Rahon b) 66KV bays 1 No. at 66KV Rahon 1 No. at 220KV Jandla | a) 12.7 Km/0.2Sq"/ SC on DC Towers line b) 66KV U/G cable 240mm2 =500mts. 1 No. To be planned by PSTCL | 342.39 125.70 29.00 | 497.09 | Line energized on 13.04.2022 | 2022-23
40 | 23/NZ/2022-23 /Annex. A | A | NZ | KPT |  |  |  | a)66KV S/S Sindhar (NEW) (including of 1 no. 66KV Bay) b) New 66KV line 6km, 0.2 sq" SC on DC tower line from 66KV S/Stn. Lohian upto proposed site of 66 KV S/Stn. Sindhar c)66KV bay 1 No. at 66KV Lohian | 12.5 MVA, T/F 66/11 KV New 6km /0.2 sq'' /SC on DC towers 66 KV line 1 No. | 219.92 161.76 29.00 | 410.68 | S/Stn. Commissioned in 05/2020 | 2022-23
41 | 24/NZ/2022-23 /Annex. A | A | NZ | KPT |  |  |  | a) 66 KV S/S Sultanpur (NEW) (Including 1 no. 66KV bay at new S/S Sultanpur) b) Stringing of 2nd ckt. 2.3Km/ 0.2sq”on existing SC on DC Sultanpurlodhi–Jakopur66KV line, from 220KV S/S Sultanpurlodhi up to tower no 12. c)Erection of 2Km/240mm2 66KV U/G cable from tower no 12. of existing Sultanpur Lodhi to Jakopur 66KV tower line up to proposed site of new 66KV S/S Sultanpur. | 20MVA,66/11KVP,T/F Stringing of 2nd Ckt./2.3Km/ 0.2sq"ACSR on existing SC on DC tower line 2Km/240mm2 66V U/G cable | 302.53 21.67 502.80 | 827 | S/Stn. Commissioned in 08/2019 | 2022-23
42 | 26/NZ/2022-23 /Annex. A | A | NZ | JAL |  |  |  | 33 KV HSP. Rd. PHG 1x12.5MVA 66-33/11 KV 1x12.5 MVA 66-33/11 KV 1x 5 MVA 66-33/11 KV | U/G 33 to 66KV with 1X20MVA, 66/11 KV to repl.1X12.5MVA & 1x5MVA,66-33/11 KV. Existing 2nd T/F 1x12.5MVA 66-33/11KV to be used at 66/11KV (Total installed capacity = 32.5MVA,66/11KV) | 225 | 225 | Work completed in 03/2021. | 2022-23
43 | 27/NZ/2022-23 /Annex. A | A | NZ | JAL |  |  |  | 33KV S/S GT Road Phagwara 1x12.5MVA 66-33/11 KV 1x12.5 MVA 66-33/11 KV | U/G to 66KV With 1X20MVA 66/11KV torepl.1x12.5MVA 66-33/11 KVExisting 2nd T/F 1x12.5 MVA 66-33/11 KV to be used at 66/11KV (Total installed capacity =32.5MVA,66/11KV) | 225 | 225 | Work completed in 03/2021. | 2022-23
44 | 28/NZ/2022-23 /Annex. A | A | NZ | JAL |  |  |  | 33 KV Chehru (Aug & U/G.) 1x12.5 MVA 33/11 KV 1x12.5MVA 66-33/11 KV | U/G to 66KV with 1X20 MVA 66/11 KV to repl 1X12.5 MVA 33/11 KV Existing 2nd T/F 1x12.5MVA 66-33/11 KV to be used at 66/11KV (Total installed capacity) =32.5 MVA,66/11KV ) | 225 | 225 | Work completed in 02/2021. | 2022-23
45 | 29/NZ/2022-23 /Annex. A | A | NZ | HSP | 83 |  |  | 66KV line from132KV Bhogpur--- 66KV Kala Bakra 10Km/0.1/0.2sq''/ tower/rail pole | Aug.of ACSR 1.8km with 0.2sq" by replacement of HRP line with SC on DC towers on same ROW upto Toff Kala Bakra | 48.53 -5.44 | 43.09 | Line charged on 02.02.2022 | 2022-23
46 | 32/NZ/2022-23 /Annex. A | A | NZ | KPT | 5 |  |  | a)66KVS/S Lakhan Ke Padde(New) (including 1no.66KV Bay) b)4km /0.2sq''/ SC on DC 66KV tower line T-off from existing Kartarpur—Nadala 66KV line ckt. upto the proposed site for new 66KV S/Stn. Lakhan Ke Padde | 12.5MVA, P,T/F 66/11KV 4.0Km/0.2sq''/SC on DC 66KV tower line | 219.92 107.84 | 327.76 | Sub-Station commissioned on 30.06.2021 | 2022-23
47 | 34/NZ/2022-23 /Annex. A | A | NZ | JAL | 2 |  |  | a)66KV S/S Focal Point-2 Jalandhar (NEW) b) Proposed 66KV double bus bar system at existing 66KV S/Stn Focal Point Jal. to provide 66KV supply to new proposed 66KV S/Stn. Focal Point-2 Jalandhar. C) 66KV Bays 1 No. at 66KV Focal Point Jal. 1 No. at 66KV Focal Point-2 Jal. Note:- 1) As per the recommendation of worth Director/Distribution & Dy.CE/TL(D),PSPCL, Patiala vide memo no. 40/41 dtd. 7.1.21, the length of multi ckt. Towers at Sr. no. (d) is corrected to 0.536 ckt.km instead of 0.730 ckt.km and also at Sr.no.(f), the dismantlement is of existing DC towers and not of rail pole line. 2) As per recommendation of Dy.CE/OP. PSPCL Jalandhar vide office memo no 4366 dt. 1.3.2019 & memo no 5203 dt. 13.3.2019 proposed site for proposed 66KV S/Stn Focal point -2 Jal. is in plot no C-75 and part of plot no. C-76, adjoining to existing 66 KV S/S Focal point Jalandhar. land provided for new proposed 66 KV S/S Focal point-2 is 4283 sq. yards measuring 136'X276.6'/290.3'. | i)1x25/31.5MVA 66/11 KV + ii)1x20MVA, 66/11 KV b)66KV double bus bar system at existing 66KV S/Stn Focal Point Jalandhar c) 2 nos 66 KV bays d) Erection of Multi ckt. Towers 0.536 ckt. Km/ 0.4 sq."/66 KV tower line (for 66 KV LILO arrangement of one ckt. at new proposed Focal Point-2 S/s having connectivity with 220 KV S/s BBMB, Kartarpur & Badshahpur mother stations) by replacing existing 0.6km/0.4 sq."/DC on DC tower line. e)78 ckt.mtr.U/G cable size 630 mm2 S/ckt.for looping in ckt.1 at Focal Point-1. f) Dismantlement of existing Rail Pole Line 0.6 km/0.4 sq." DC on DC tower line. | 393.11 302.53 10.00 58.00 63.24 32.38 -1.81 | 857.45 | Sub-Station commissioned on 31.05.2021 | 2022-23
48 | 35/NZ/2022-23 /Annex. A | A | NZ | JAL |  |  |  | a) 66 KV Paragpur (Jalandhar Cantt.) (New) b) 400 mts/ 240mm2, 66KV U/G cable from tower no CG-8 to tower no D,(new) T-off from existing Barringa to BBMB 66KV line c) Erection of structure on tower no CG-8 for erection of 66KV cable and erection of new tower no D, to replace existing (1no) HRP d) Augmentation of 100mts. ACSR cond. from point D to C of existing 66KV line from 0.15sq'' to 0.2 sq'' on existing structure. e) Proposed 1 Km / 66KV underground cable 240mm2 , from tower no C up to proposed site of 66KV sub S/Stn. f) Cost of land | 1x20 MVA 66/11 KV 400 mts/240mm2, 66KV, Underground cable . structure on tower no CG-8+new 1no DC tower at location D 100mts. 1Km/66KV 240mm2 , under ground cable | 302.53 100.56 10.30 2.70 251.40 330.57 | 998.06 | Work Completed and line charged on dt. 22.12.2020 | 2022-23
49 | 36/NZ/2022-23 /Annex. A | A | NZ | NWSR |  |  |  | a)66KV S/S Nawanshehar (NEW) b) 350 mts. 66KV 240mm2 underground XLPE cable from 132KV S/S Nawanshehar up to 66KV proposed S/S Nawanshehar | a)1x20MVA, T/F 66/11 KV b) 0.350 Ckt-Km (1X4C) 66KV U/G XLPE cable 240mm2 | 302.53 87.99 | 390.52 | Work completed | 2022-23
50 | 41/NZ/2022-23 /Annex. A | A | NZ | JLD |  | 17 |  | 66 KV Patara (Aug.) 1x20 KV 66/11 KV 1x12.5 MVA 66/11 KV | 20MVA to rep. 12.5MVA,66/11 KV | 157.04 | 157.04 | Work completed on 08.10.2021. | 2022-23
51 | 42/NZ/2022-23 /Annex. A | A | NZ | NWSR |  | 60 |  | 66KV Bheen (Aug.) 1x12.5MVA 66/11KV | 20MVA to rep. 12.5MVA,66/11 KV | 157.04 | 157.04 | Work completed on 23.02.2022. | 2022-23
52 | 43/NZ/2022-23 /Annex. A | A | NZ | JLD |  | 120 |  | 66 KV Chougittee 1x12.5 MVA, 66/11 KV 1x20 MVA, 66/11 KV | 1x20 MVA, 66/11 KV to repl. 1x12.5 MVA, 66/11 KV | 157.04 | 157.04 | Work completed on 12.03.2022. | 2022-23
53 | 1/BZ/2022-23/ /Annex.A | A | BZ | ASR |  |  |  | a) 66KV Line from 66 KV Hall gate to 66 KV Golden Temple b) 66KV Interlink line between 66KV Gowal Mandi to 66KV Kacheri Chowk c) 66KV Addl. 2nd Ckt. between 66 KV GT.Road to 66KV Golden Temple | a) U/G Cable 4x1/C 2.3km/630mm2 b) U/G Cable 4x1/C 1.6 km/630mm2 c)i) New tower line.1.1km/0.2sq" SC on DC ii)U/G Cable 4x1/C 0.960 km/ 630mm2 | 552.00 384.00 23.44 230.40 | 1189.84 | all the work completed | 2022-23
54 | 2/BZ/2022-23/ /Annex.A | A | BZ | GSP |  |  |  | a) 66 KV line from 132 KV Sarna-----Ranipur (pt.A to B) 12.5 km/0.2 Sc on DC (already Towers Proposed in TWL-2014-17 at Sr.No79) b) 66 KV line from Ranipur to Manwal T-off 10 km HRP c) New Link line from between Ranipur----Dhar (pt. K to L) d)66 KV line between Chhatwal & Dunera 35km /48mm2/HRP e) 66 KV line from 132KV Sarna---Dina nagar from T-off pt. for Gharota 5km/0.125/ HRP f) New Link line between Gharota--- Mirthal g) New T-off Link line between Gharota--Mirthal for Nangal bhoor h) Bays | This revised scope of work clubbed with amended scope of work at s.no 20/BZ of TWL 18-19 because this was relating to Sarna--Ranipur line portion b) New line from Ranipur-Manwal 10 km/0.2 sq." SC on DC towers c)Deleted as recommended by CE/TS vide memo no 3432/34 dt 13.5.19 d)Deleted as recommended by CE/TS vide memo no 3432/34 dt 13.5.19 e) 5 km 0.2 sq." SC on DC towers f) 4.5 km/0.2 sq." SC on DC towers g) 10 km 0.2 sq." SC on DC towers h) 6 nos. | NIL 269.60 NIL NIL 134.80 121.32 269.60 174.00 | 969.32 | work completed in 12/2019. | 2022-23
55 | 5/BZ/2022-23/ /Annex.A | A | BZ | TTN |  |  |  | Aug. of 66 KV line from T-off point for 66 KV Rashiana (now 220 KV Rashiana) to 66KV Fatehbad 9KM/0.15 sq"/HRP line b) 66 KV Bays 1 No. at 220 KV Rashiana | Aug.of ACSR 9 km with 0.2sq." by replacement of HRP line with SC on DC towers To be planned by PSTCL | 242.64 -27.18 | 215.46 | Line Charged on 09.06.2022 | 2022-23
56 | 6/BZ/2022-23/ /Annex.A | A | BZ | TTN |  |  |  | a)66 KV Butala (NEW) b)66 KV Sathiala --- Butala line c)66KV line from 220KV S/S Butari to Beas(10km/0.15 sq"/HRP)Aug. d)66KV Beas ---Sathiala line (8km/0.125 sq"/ HRP) Aug. e)66 KV bay at Sathiala for 66kv line Butala (New) | a) 1x12.5 MVA 66/11 KV b) 8KM /0.2 Sq" SC on DC Towers. c) Aug. of ACSR 10 km with 0.2sq." by replacement of HRP line with SC on DC towers d) Aug. of ACSR 8 km with 0.2sq." by replacement of HRP line with SC on DC towers e) Erection & stringing of 2nd ckt line 5 KM/DC on existing DC towers with ACSR 0.2 sq" up to Lidher tapping (up to Tower no. 25) f) 66 KV 240 mm2 70 ckt. meter cable is required from idle 66 KV Bay to existing first DC Tower of this line at 220 KV S/S Butari. g) Idle 66 KV bay of 220 KV S/s Butari to be operationalized by replacing old/damaged 66 KV CT, SF6 line breaker and installing C&R Panel by PSTCL Org 1 No. 66 KV Bay | 254.44 170.78 213.10 -30.20 170.78 -24.16 83.65 35.20 9.52 29.00 | 912.11 | a)work completed. b) Line charged. c)Line charged on 15.06.2022. d) Line charged. | 2022-23
57 | 12/BZ/2022-23/ Annex.A | A | BZ | TTN |  |  |  | 66KV line from 220KV S/S Butari to Nagoke (13 KM/0.125sq'' HRP) (Aug.) | Aug of ACSR 13 km with 0.2 sq." by replacement of HRP line with SC on DC towers | 350.48 -39.26 | 311.22 | Line charged in 03/2021 | 2022-23
58 | 14/BZ/2022-23/ Annex.A | A | BZ | TTN |  |  |  | a) 66KV Line from 220KV Algon -- 66KV Mari Mega (NEW) b) 66KV bays 1 No. at 66 KV Mari Mega 1 No. at 220 KV Algon | a)Stringing of 2nd Ckt.19Km/ 0.2Sq" ACSR on existing DC towers line to make DC on DC tower line 1 No. To be planned by PSTCL | 178.98 29.00 | 207.98 | Work completed in 06/18 | 2022-23
59 | 15/BZ/2022-23/ Annex.A | A | BZ | TTN |  |  |  | a) 66KV Line from 220KV Patti -- 66KV Ghariyala (NEW) | Aug of ACSR 12 km with 0.2 sq." by replacement of HRP line with SC on DC towers | 323.52 -36.24 | 287.28 | Line energized on 12.04.2021 | 2022-23
60 | 18/BZ/2022-23/ Annex.A | A | BZ | GSP |  |  |  | a) 66 KV S/Stn. Jaura Singha (NEW) (Including 1 nos. 66KV bay) b) 8km/0.2sq"/ SC on DC 66KV tower line, from existing 66KV S/S Bijliwal upto the site of proposed 66 KV S/S Jaura Singha. c) 66KV bay at 66KV S/Stn Bijliwal. | 12.5 MVA, 66/11 KV P,T/F 8km /0.2sq'' SC on DC 66KV towers line, 1nos. Note:- As per Gram Panchayat Resolution 2 Acre land shall be provided free of cost to PSPCL for new S/S. | 219.92 215.68 | 435.6 | S/Stn. commissioned in in 11/2020. | 2022-23
61 | 19/BZ/2022-23/ Annex.A | A | BZ | GSP |  |  |  | a) 66 KV S/S Bani Lodhi (NEW) (Including 1 nos. 66KV line bay) b) Shifting and conversion of 0.485Km portion of existing 0.125sq'' /HRP 66KV line between four pole structure & three rail structure near Mahanta di nadi BaniLodhi,of Sarna--Narot Jaimal Singh 66KV line, into 0.2sq"/0.6Km, SC on DC 66KV new tower line. (in order to make space for construction of new S/Stn. as the existing HRP line is passing through the proposed site of new proposed 66KV S/Stn.Bani Lodhi.) c) 0.02Km/DC on DC new 66KV LILO from above proposed new portion of Sarna--Narot Jaimal Singh SC on DC 66KV line, for new proposed 66KV S/Stn Bani Lodhi. d) 66KV bay (1nos. bay for outgoing 66KV line) | 12.5MVA, 66/11KV P,T/F Dismantlement of 0.485Km portion of existing 0.125sq''/HRP line and erection of new 0.6km/ 0.2sq"/SC on DC new 66KV towers line. 0.02km/ 0.2sq"/DC on DC new LILO 66KV towers line 1 nos. | 219.92 13.08 -1.46 0.73 29.00 | 261.27 | S/Stn. charged on 02.12.2021 | 2022-23
62 | 20/BZ/2022-23/ Annex.A | A | BZ | TTN | 1 |  |  | a) 66KV Line from 220KV Fategarh churian to 220KV Majitha 6Km/0.125Sq" /HRP line | Aug of ACSR 6 km with 0.2sq." by replacement of HRP line ( RP 60 to 100) with SC on DC towers | 161.76 -18.12 | 143.64 | Line charged ono 01.06.2022. | 2022-23
63 | 22/BZ/2022-23/ Annex.A | A | BZ |  |  |  |  | a) 66KV S/S Bharath. (NEW) (Including 1 nos. 66KV line bay with line Isolators only at new 66KV S/Stn Bharath) b)2.4km /0.2sq"/SC on DC towers 66KV line,T-off from existing Sri HargobindpurSahib to Qadian line18Km/0.125sq"/ HRP 66KV idle line circuit. | 1x12.5 MVA, 66/11 KV P,T/F New 2.4km/0.2sq" SC on DC towers line | 219.92 64.70 | 284.62 | S/Stn. commissioned on 26.05.2022. | 2022-23
64 | 23/BZ/2022-23/ Annex.A | A | BZ | ASR |  | 74 |  | 66 KV Sultanwind (Aug.) 1x20MVA 66/11KV | Addl.20MVA 66/11 KV | 285.94 | 285.94 | completed in 11/2020 | 2022-23
65 | 30/BZ/2022-23/ Annex.A | A | BZ | TTN |  | 104 |  | 66 KV Patti 1x10/ 12.5 MVA, 66/11 KV | 1x 20 MVA to repl. 1x10/12.5MVA, 66/11 KV | 157.04 | 157.04 | Work completed in 02.02.2022 | 2022-23
66 | 3/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | a)66KV line from 220KV S/S Humbran to 66 KV Bhundri 66KV Adda Dakha (New) 8 Km/0.2Sq"/SC on DC towers. b) 66KV Line Bays | 8 Km /0.2Sq"/ DC on DC Towers. b) 2 Nos. | 291.12 58 | 349.12 | Work completed in 11/19 | 2022-23
67 | 8/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | a) LILO of 66KV Line 220KV Jagroan to 66KV Raikot at 66KV S/S Roomi b)66kv Line from 66KV Raikot- 66KV Roomi up to T-Off point 15.0Kms/0.125Sq"/SC on SC Towers. c) 66KV Line Bay at 66KV Roomi end. | a)Stringing of 2nd Ckt.1.0Kms/ 0.2Sq"on existing structure to make LILO . a'-1)Stringing of 2nd Ckt.1.0Km/0.2Sq"/including providing 2no. Additional DC Towers to get the spans within permissible limits, to make the LILO for Roomi. b)15.0 Km / 0.2Sq" SC on DC Towers. c) One No | 9.42 7.25 404.40 -45.3 29 | 404.77 | Work completed | 2022-23
68 | 11/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | 220 KV Ladowal (Prop.) –66KV Amaltas 66KV line (New) b) 66kV line bays | a) i) 6.2Km./0.4sq"/SC on MC Towers (MCT- 41 Nos.) ii) 1.0 Km U/G Cable 630 mm2 b) 66 KV line bay- 1 No. (Amaltas end) | 103.73 415.1 29 | 547.83 | Work completed in 07/19 | 2022-23
69 | 12/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | 1,i)Creation of 3rd Ckt. of make capacity equal to 0.4 Sq." to 3x 0.4 Sq." ii) Ckts between 220 KV Sahnewal & 66 KV Kanganwal S/S iii) 2 (i) 66KV Kanganwal, 5x20 MVA (ii)66KV Bay at Kanganwal. | i)U/G cable 630 mm2 at 220KV Sahnewal end (already exists at site) = 217 mtr. Stringing of 3rd Ckt. 0.4Sq." on existing MCT at both Sahnewal & Kanganwal ends =2.159+0.992= 3.151 ckt. km Replacement of existing DC/DC towers with Sahnewal & Kanganwal ends new W & Z / MC Towers and stringing of 3 nos. Ckt. of 0.4 Sq. inch on them. (old conductor to be reused wherever feasible)=2.665 CKT.Km Augumentation of T/F T-5, 20 MVA with 31.5 MVA 1No. (Cost including shifting of two nos. T/Fs in back space of S/Stn. as per drawing SKS/1207/R-14 dt 18.9.19 revised route of 66KV line as intimated by CE/TS PSPCL Patiala vide his office note 14/PS/CE/TS dt 15.1.2021.) | 0 52.72 389.48 199.78 92.02 | 734 | Line energized on 02.04.2022 | 2022-23
70 | 14/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | a) 66 KV S/S Tajpur Road, b)66KV line from 220 KV Kohara to 66KV Tajpur Road. Ldh c) 2 No.66 KV line Bays | a) 1x20 MVA,66/11 KV b)i)11.856Km/0.2sq"/SC on DC towers ii)1Km/0.2Sq" 66 KV line on multi ckt towers(9 nos towers) iii) 1.6Km /0.2Sq" 66 KV line on WZ type towers (15nos towers) iv) 66KV U/G Cable 0.225Km/240mm2 c) 1 No. 66Kv line Bays at 66 KV S/S Tajpur road end. Note: 1No.66 KV Bay at 220KV S/S Kohara to be constructed by PSTCL. | 302.53 319.64 98.19 157.104 | 877.464 | Grid Work completed on 30.04.2013. Line has been charged in 07/2020 | 2022-23
71 | 15/CZ/2022-23 Annexure-A | A | CZ | KHN |  |  |  | a) To connect 4th idle ckt. of 66 KV multi ckt. line between G-2 & Badinpur at Badinpur S/S. b) 66 KV line bay | Termination and alignment of the existing line with the new bay at Badinpur by erection of 1 no. tower and 0.7 Ckt. Km, ACSR 0.2 sq." 1 No. at Badinpur | 6.914 29 | 35.914 | work completed in 12/2020 | 2022-23
72 | 17/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | a) 66 KV Bajra Road Meharban (new). b) 66 KV line/ U/G XLPE cable form 66 KV Gaunsgarh-66 KV Bajra Road Meharban new. 66KV Bays | 1x31.5 MVA, 66/11 KV T/F i)1.5 KMs/0.4 sq” SC on DC towers ii) 2.5 Kms/630 mm2 66 KV U/G XLPE cable. 1 No. Bay at 66KV Gaunsgarh | 393.11 77.76 600 29 | 1099.87 | S/Stn. commissioned in 08/2020. | 2022-23
73 | 18/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | 66 KV Pabbian 1X12.5 MVA T/F, 66/11 KV | Addl. 12.5 MVA 66/11 KV T/F | 203.61 | 203.61 | Work completed in 04/2021 | 2022-23
74 | 19/CZ/2022-23 Annexure-A | A | CZ | KHN |  |  |  | 66KV line from 220KV S/S Amloh to Bhadson (NEW) | New 8Km/0.2sq”/SC on DC towers 66KV line | 215.68 | 215.68 | Line has charged on 11/9/2021 | 2022-23
75 | 21/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | a)LILO of 66KV Line between 220KVJagroan - 66KV Sudhar at 66KV Pabian 0.6Km/ 0.2sq"/SC on DC Towers. b) 66KV Bay at 66KV Pabian end. | a)Replacement of existing 0.6Km T-off portion of 0.2sq"/SC on DC with 0.4sq" DC on DC to make LILO at Pabbian. 2 Nos. (1 No. Bay & Conversion of 1 No. LE to Breaker Controlled Bay) | 31.10 -1.81 29 22.32 | 80.61 | Line charged on 25.11.2021 | 2022-23
76 | 22/CZ/2022-23 Annexure-A | A | CZ | KHN | 131 |  |  | i)Proposed Multi ckt link line on MCT/0.2sq."/ ACSR 0.15Km from 220KVS/S Bhari to 66KV S/S Grain Market MGG (1No.Ckt. for Hargana S/Stn. & 2no.Ckts. for Grain market S/Stn.) ii) Erection of 3 Nos. 66KV Bays at 220KV S/S Bhari. | i) Proposed 0.15Km/ 0.2sq.inch/ 3no.Ckts on Multi ckt Towers at starting point of Bhari—Hargana & Grain market line ( from 220KV S/S Bhari S/Stn.) 1No.Ckt. for Hargana S/Stn. & 2no.Ckts. for Grain market S/Stn. Note:-Errection of 3 Nos. 66KV Bays at 220KV S/S Bhari shall be planned by PSTCL (1 nos. for Hargana line at Bhari because it is controlled by isolator & 2 no. 66 KV bays for Grain market ckts at Bhari) | 14.7285 | 14.7285 | Work completed in 06/2020 | 2022-23
77 | 23/CZ/2022-23 Annexure-A | A | CZ | LDH | 46 |  |  | a)66KV new link line from 220KV Ladowal to 66KV GT Road S/stn. b) 66KV line bays 4 nos. | i) 6Km/ 0.4Sq." DC on Existing Multi Circuit Towers. ii)6.2Km/0.4 Sq." DC on Monopoles. b)2 nos.(at 66 KV S/S G.T. Road) Note:- 2 Nos. bays at 220 KV S/S Ladhowal to be planned by PSTCL. | 200.76 1395 58 | 1653.76 | line charged on 11/6/2022 | 2022-23
78 | 24/CZ/2022-23 Annexure-A | A | CZ | LDH. |  | 37 |  | 66KV S/S Giaspur 3X20 MVA + 1X31.5MVA, 66/11KV | 1x31.5MVA, 66/11 KV to repl. 2nd T/F 1x20 MVA, 66/11K V | 199.78 | 199.78 | Work completed on 13/05/2021 | 2022-23
79 | 26/CZ/2022-23 Annexure-A | A | CZ | KHN. |  | 90 |  | a) 66KV line from 220KV S/S G1 to 66KV S/S F.P. MGG 1.162Km/0.2 Sq"/SC on DC Tower line. b) 66kV line bays | a)(i) Stringing for 2nd Ckt. 1.2 Km/ 0.2sq."/ ACSR conductor from 66KV Focal point upto the point where the ckt. for M/s Bhawani Castings separates. ii)Replacemrent of 66 KV line from 220 KV S/S G-1 on 2 nos. 2- D 60 towers, 2 nos. D - 60 towers, 1nos. CN tower, 1nos. D-30 tower, 1nos. X-type tower & 1 nos. gantry up to the point where the ckt. for M/s Bhawani Castings separates b)1 No. Bay with breaker control at at 66KV S/S Focal point MGG Note:-1 No. 66KV bay at 220KV S/S G-1 shall be planned by PSTCL. | 11.30 85 29 | 125.3 | Work completed on 16/05/2021 | 2022-23
80 | 28/CZ/2022-23 Annexure-A | A | CZ | S/U LDH | 45 |  |  | a) Un-manned 66KV S/S Jalaldiwal (NEW) b)66KV line 6km/0.2sq” SC on DC tower line from 66KV S/S Shahjahanpur to new proposed 66KV S/S Jaladiwal. c)66KV line Bay | a)1x 6.3 /8MVA,66/11 KV(OLD) &1 No. New 66KV line Bay b)New 6km/0.2sq”/SC on DC Tower 66KV line. C)1 No. New 66KV line Bay at 66KV S/S Shahjahanpur | 169.94 161.76 29 | 360.7 | S/Stn. charged on 23.12.2021. | 2022-23
81 | 30/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  |  | T-off from 66KV line from 220KV Gounsgarh to Phase-8 /0.4sq-inch line for 66KV S/S Tajpur road {2nd source of supply for 66KV Tajpur road S/S} | a)New 1.5Km 66KV under ground cable 630mm2 b) 66KV bay 1 nos. and sectionalizing of existing 66KV bus-bar | 622.65 44 | 666.65 | Line charged on 28.10.2021 | 2022-23
82 | 31/CZ/2022-23 Annexure-A | A | CZ | LDH |  |  | 19 | 66KV S/Stn. Tajpur Road 1x20MVA +1X31.5MVA 66/11KV T/Fs | 1x31.5MVA, 66/11KV to repl. 1x20 MVA, 66/11 KV T/F | 199.78 | 199.78 | Work completed on 07/05/2021 | 2022-23
83 | 1/WZ/2022-23 Annexure-A | A | WZ | BTI |  |  |  | a) 66 KV IGC(Dabwali Rd).-66 KV MES (Barnala Rd.)BTI DC on DC towers line with LILO of both the ckt at 66 KV Model Town Phase-3 b) 66 KV bays | 8 Kms/0.2 Sq" DC on DC towers 4 No.( 1 no. at MES, 1 No. at IGC & 2 No.at Phase-3) | 291.12 116.00 | 407.12 | Line charged on 16.04.2022 | 2022-23
84 | 3/WZ/2022-23 Annexure-A | A | WZ | BTI |  |  |  | a) 66 KV IGC(Dabwali Rd).- Malout Rd. DC on DC towers with LILO of both ckts at 66 KV Paras Ram Nagar b) 66 KV Bays | 9 kms/0.2sq" DC on DC towers 4 no. (1 No. at IGC,1 No. at Malout Rd. & 2 No. at Paras Ram Nagar) | 327.51 116.00 | 443.51 | Work completed in 02/2021 | 2022-23
85 | 4/WZ/2022-23 Annexure-A | A | WZ | BTI |  |  |  | a) 66 KV Malout Rd.-Sangat line upto T-off for Nandgarh Ghudda b) 66 KV line from T-off point Nandgarh Ghudda to Sangat. c) 66 KV Bays | a) Stringing of 2nd ckt with 12 km/0.2 Sq." on DC Towers. b) 4 KM/ 0.2 Sq." DC on DC towers to replace HRP 0.125 sq". 2 no. (1 no. at 66 KV Malout Rd and 1 no. at 66 KV Sangat) | 113.04 145.56 -12.08 58.00 | 304.52 | Work completed in 11/19 | 2022-23
86 | 5/WZ/2022-23 Annexure-A | A | WZ | FZR |  |  |  | 66 KV Chak Veroke 1x 20 MVA, 66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | completed in 05/19 | 2022-23
87 | 9/WZ/2022-23 Annexure-A | A | WZ | FZR |  |  |  | 66 KV Kassoana (Aug) 1x12.5 MVA,66/11 KV | Addl.1x12.5 MVA, 66/11KV | 203.61 | 203.61 | completed in 09/19 | 2022-23
88 | 10/WZ/2022-23 Annexure-A | A | WZ | MKT |  |  |  | a) 66 KV Pathrala-66 KV Killianwali new line link b) 66 KV Bays | 10KM/ 0.2sq" new line SC on DC tower 2 Nos (1 no. at 66 KV Pathrala and 1 no. at 66 KV Killianwali) | 269.60 58.00 | 327.6 | Work Completed and Line charged in 05-2020 | 2022-23
89 | 11/WZ/2022-23 Annexure-A | A | WZ | FDK |  |  |  | a) 220 KV Bajakhana- Jaito 66 KV line. 11.7Km/0.2Sq" SC on DC b) 66 KV Bay | Stringing of 2nd Ckt. 11.7Km/0.2Sq" on DC towers 1 no. Bay at Jaito 1 No. 66KV Bay at 220KV Bajakhana to be planned by PSTCL. | 110.21 29.00 --- | 139.21 | Line Completed in 11/2021 and Energised | 2022-23
90 | 13/WZ/2022-23 Annexure-A | A | WZ | FZR |  |  |  | 132KV Ferozshah- Mallanwala T-off Bhagoke 66 KV line. 19.36Km/ 0.15Sq" SC on RP 2 no. Bays at 66 KV Mallanwala | i) Replacement of 19.36KM HRP with 19.36Km/0.2Sq" SC on DC towers from Ferozshah to Mallanwala ii)2 No. Bays at 66KV Mallanwala (1 No. Bay for Bhago ke line and 1 No. Bay for Kamala Middu) on the old existing civil foundations. iii)Stringing of 2 No. Ckts.200m/0.2 sq." on existing multi ckts. Towers from MCT-T 2 to 66KV S/S Mallanwala | 521.94 -58.47 58.00 39.27 | 560.74 | Line charged on 25.05.2022. | 2022-23
91 | 15/WZ/2022-23 Annexure-A | A | WZ | MKT | 64 |  |  | 220KV Malout- Madhir 66 KV line 24km/0.1/0.15 Sq" SC on RP | 1) Stringing of SC on 3.5 Kms/0.2Sq” on Multi Ckt towers at Malkatora end already covered in Work No. 14/WZ/2021-22/Annexure-A 2) 20.5 Kms/0.2Sq” SC on DC 3) To retain portion from point G to E (20 no. span) and portion from point E toF (4 no. span) as per sketch of existing 220KV Malout Madhir 66 KV line for feeding 66KV Husnar. 4) 1 No. 66KV Bay at 66 KV S/S Madhir. | Nil 552.68 -44.48 29.00 | 537.2 | Work completed & line Enerzised in 06/2020 | 2022-23
92 | 18/WZ/2022-23 Annexure-A | A | WZ | BTI | 29 |  |  | i) 66KV Jhunir-Boha line, New T-off link for Tahlian. ii) 66KV Bays | a) 6 KM SC on DC new line 0.2Sq"ACSR. b) 1 no. LE controlled Bay at Tahlian. | 161.76 14.00 | 175.76 | Work completed and line charged in 30.09.2021 | 2022-23
93 | 20/WZ/2022-23 Annexure-A | A | WZ | FDK |  |  |  | 66 KV New link between 66 KV S/S Dagru to 66 KV S/S Daulatpura 66 KV Line Bays | 8 KM/ 0.2 Sq." SC on DC new line. 2 No. (1 No. at 66 KV S/S Dagru and 1 No. at 66 KV S/S Daulatpura). | 215.68 58.00 | 273.68 | Work Completed in 04-2021 and Line Charged | 2022-23
94 | 21/WZ/2022-23 Annexure-A | A | WZ | FDK |  |  |  | 66 KV New link between 66 KV S/S Daulatpura to 66 KV S/S Khosa Kotla 66 KV Line Bays | 8 KM/ 0.2 Sq." SC on DC new line 2 No. (1 No. at 66 KV S/S Daulatpura and 1 No. at 66 KV S/S Khosa Kotla). | 215.68 58.00 | 273.68 | Work Completed in 04-2021 and Line Charged | 2022-23
95 | 22/WZ/2022-23 Annexure-A | A | WZ | FDK |  |  |  | 66 KV New link between 66 KV S/S Fatehgarh Corotana to 66 KV S/S Bhinder Kalan 66 KV Line Bays | 8 KM/ 0.2 Sq." SC on DC new line 2 No. (1 No. at 66 KV S/S Fatehgarh Corotana and 1 No. at 66 KV S/S Bhinder Kalan). | 215.68 58.00 | 273.68 | Work completed and line charged on 12-6-2022 | 2022-23
96 | 23/WZ/2022-23 Annexure-A | A | WZ | FDK | 6 |  |  | 66 KV New link between 66 KV S/S Ramuwala to 66 KV S/S Charik 66 KV Line Bays | 6 KM/ 0.2 Sq." SC on DC new line 2 No. (1 No. at 66 KV S/S Ramuwala and 1 No. at 66 KV S/S Charik). | 161.76 58.00 | 219.76 | Work completed 12/2020 | 2022-23
97 | 30/WZ/2022-23 Annexure-A | A | WZ | FZR |  |  |  | i) 66 KV line Ferozepur Cantt- Chugatewala T off at Atari ii) 66 KV Bays (2 Nos) | Stringing of second Ckt 0.2 sq"/1.6KM from T-off point on the existing DC towers for LILO on Attari 1 No. Bay Convertion of 1 No. LE Controlled to Breaker Controlled Convertion of 1 No. LE Controlled to Breaker Controlled | 15.07 29.00 22.32 | 66.39 | 2nd CKT Completed and charged in 10-2020 | 2022-23
98 | 34/WZ/2022-23 Annexure-A | A | WZ | BTI |  | 7 |  | New 66 KV link from 66 KV Jhanduke to 66KV Ghaso-khanna. 66 KV line Bays | 7 KM SC on DC new line 0.2 Sq." ACSR. 2 No. 66 KV Breaker Controlled line Bays( 1 No. at Bay at 66 KV Jhanduke and 1 No. Bay at 66KV Ghaso- khanna.) | 188.72 58.00 | 246.72 | Work completed and line energized during 05/2022. | 2022-23
99 | 37/WZ/2022-23 Annexure-A | A | WZ | BTI |  |  |  | a) 66 KV Jiwan Singh Wala (New) (including 1 No. 66 KV Bay) b) New 66 KV line from T-off Tower of 66 KV Talwandi Sabo—Bangi Nihal Singh Line to proposed 66 KV Grid Jiwan Singh Wala. c) Augmentation of conductor of 66 KV Talwandi-Sabo—Bangi Nihal Singh Line (2nd circuit lying idle) from 220 KV Talwandi Sabo up to DC towers. d) New 66 KV Line DC on DC Towers (from last existing DC Tower of 66 KV Talwandi-Sabo—Bangi Nihal Singh Line upto T-OFF Tower) of 66 KV Talwandi Sabo—Bangi Nihal Singh line up to T-OFF Tower) with 0.2 Sq." Conductor by replacing 66 KV Talwandi Sabo— Bangi Nihal Singh Line (SC on SC towers) e) 1 No. 66 KV Bay at 220 KV S/S Talwandi Sabo. | 1X6.3/8 MVA, 66/11 KV 8 KM new line 0.2 Sq." SC on DC towers. 2.5 Km / 0.2 Sq.” DC on DC towers (One Ckt of 0.15 Sq." to be replaced with 0.2 Sq." for 66 KV S/S Jeewan Singh Wala). 5 Km / 0.2 Sq.” DC on DC towers to replace 0.15 Sq." SC on SC line. 1 No. 66 KV Bay to be planned by PSTCL | 219.92 215.68 90.97 181.95 -15.10 --- | 693.42 | S/Stn. commissioned on 24.01.2022. Work of part (d) completed in 06/2022. | 2022-23
100 | 38/WZ/2022-23 Annexure-A | A | WZ | FZR |  |  |  | a) 66 KV Grid S/S Sangrahoor (New) (including 1 No. 66 KV Bay) b) T-off of 66 KV line emanating from 220 KV Sadiq to 66 KV S/S Jhoke Tehal Singh for proposed 66 KV Grid 66 KV S/S Sangrahoor. | 1x12.5 MVA, 66/11 KV 1.5 Km / 0.2 Sq.” SC on DC towers . | 219.92 40.44 | 260.36 | S/Stn. charged on 25.10.2021. | 2022-23
101 | 39/WZ/2022-23 Annexure-A | A | WZ | MKT |  |  |  | a) 66 KV New Link line from 66 KV S/S Wara Kishanpura to 66 KV S/S Mallan b) 66 KV line Bays | 10 km new line, 0.2 Sq.", SC on DC towers 2 Nos. (one at 66 KV S/S Wara Kishanpura & another at 66 KV S/S Mallan ). | 269.60 58.00 | 327.6 | Line energized on 27.05.2021. | 2022-23
102 | 40/WZ/2022-23 Annexure-A | A | WZ | MKT | 44 |  |  | a) 66 KV Danewala (New) b) T-off of 132 KV Malout-33 KV Abul Khurana on 66 KV SC on Tower for 66 KV Danewala | 1x 12.5 MVA, 66/11 KV 3 Km/ 0.2 Sq." SC on DC towers | 219.92 80.88 | 300.8 | S/Stn. commissioned on 29.03.2022. | 2022-23
103 | 43/WZ/2022-23 Annexure-A | A | WZ | FDK |  |  |  | 66 KV Ramuwala 1x6.3/8 MVA, 66/11KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | work completed in 02/2020 | 2022-23
104 | 44/WZ/2022-23 Annexure-A | A | WZ | FDK |  |  |  | 66 KV Malke 1x12.5 MVA,66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | work completed in 11/2019 | 2022-23
105 | 45/WZ/2022-23 Annexure-A | A | WZ | MKT | 101 |  |  | 66 KV Bheetiwala 1X6.3/8 MVA, 66/11 KV 1X10/12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20MVA 66/11 KV. | 157.03 | 157.03 | Work completed in 12/2020. | 2022-23
106 | 51/WZ/2022-23 Annexure-A | A | WZ | FZR |  | 70 |  | 66 KV Zira gate 1X12.5 MVA, 66/11 KV 1X20 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | Work completed on 25.02.2022. | 2022-23
107 | 52/WZ/2022-23 Annexure-A | A | WZ | BTI |  | 24 |  | 66 KV Joend 1X12.5 MVA, 66/11 KV | Addl 1X6.3/8 MVA | 203.61 | 203.61 | Work completed on 20.09.2021 | 2022-23
108 | 53/WZ/2022-23 Annexure-A | A | WZ | FDK |  | 18 |  | 66 KV S/S JANER 1X12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | Work completed on 18.01.2022. | 2022-23
109 | 54/WZ/2022-23 Annexure-A | A | WZ | MKT | 105 |  |  | 66 KV Dabwali (Killianwali) 1x6.3/8 MVA, 66/11 KV 1x12.5 MVA, 66/11 KV | Augmentation of 8 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | Work completed on 28.01.2022. | 2022-23
110 | 56/WZ/2022-23 Annexure-A | A | WZ | MKT |  |  |  | a) 66 KV S/S Truck Union Hanuman Chowk Bathinda (New) b) Proposed New 2.8 Km 66 KV Underground Cable 240mm2 from existing 66 KV S/S MES Bathinda. c) 66 KV Line Bays | 1x20 MVA, 66/11 KV, T/F 2.8 Km 66 KV Underground Cable 240mm2 1 nos. | 258.59 380.80 28.00 | 667.39 | S/Stn. charged on 24.12.2021. | 2022-23
111 | 66/SZ/2022-23 Annexure-B | B | SZ | Barnala |  | 40 |  | 66 KV S/Stn Tallewal (Aug) 1x20 MVA + 1x12.5 MVA, 66/11 KV | 20 MVA to repl 12.5 MVA, 66/11 KV | 157.03 | 157.03 | Work Completed on 13.04.2022 | 2022-23
112 | 45/NZ/2022-23 /Annex. B | B | NZ | HSP |  |  |  | 66 KV Dasuya (Aug.) 1x10/12.5 MVA,66/11 KV 1X20 MVA,66/11 KV | 2nd 20 MVA to repl. 1x10/12.5 MVA,66/11 KV | 157.04 | 157.04 | Work completed in 08/19 | 2022-23
113 | 53/NZ/2022-23 /Annex. B | B | NZ | JAL | 107 |  |  | 66 KV T V Centre 1x20 KV 66/11 KV | 1x 25/31.5 MVA to repl. 1x20MVA 66/11 KV | 199.78 | 199.78 | Work completed in 02/2020 | 2022-23
114 | 54/NZ/2022-23 /Annex. B | B | NZ | JAL |  | 45 |  | 66 KV S/Stn.Panshta 1x20 MVA 66/11 KV | Addl 20 MVA, 66/11 KV | 285.94 | 285.94 | Work completed on 06.06.2021 | 2022-23
115 | 64/NZ/2022-23 /Annex. B | B | NZ | JAL |  | 95 |  | 66 KV S/Stn.Chara Mandi, Jalandhar T-1 & T-2 having Capacity 20MVA | Augmentation of 20 MVA Power T/F T-2 with 31.5 MVA | 199.78 | 199.78 | Work completed on 03.06.2022 | 2022-23
116 | 34/BZ/2022-23/ Annex.B | B | BZ | ASR | 70 |  |  | a) 66KV Line from 220KV Fatehgarh Churian-- 66KV Ajnala (NEW) b) 66KV bays 1 No. at 66 KV Ajnala 1 No. at 220 KV F/Churian | a)Stringing of 2nd Ckt 0.2Sq" 9Km ACSR on existing SC on DC Tower line up to Dyal Bharang in order to make Double Ckt.line 1 No. To be planned by PSTCL | 84.78 29.00 | 113.78 | Line charged on 18.06.2022 | 2022-23
117 | 59/BZ/2022-23 Annex.B | B | BZ | GSP |  |  |  | 66 KV S/S Ranipur | Augmentation of 6.3/8 MVA with 20MVA PTF | 157.04 | 157.04 | Augmented Power T/F Test charged on 08.06.2022 | 2022-23
118 | 60/BZ/2022-23 Annex.B | B | BZ | ASR |  |  |  | 66KV S/S Nag Kalan 2x12.5=25 MVA 66/11 MVA | Aug. of T-2, 12.5MVA, 66/11KV T/F with 20MVA, 66/11KV | 157.04 | 157.04 | Work completed on 25.04.2022 | 2022-23
119 | 61/BZ/2022-23 Annex.B | B | BZ | GSP |  |  |  | 66KV S/S Civil Hospital Batala 1x20= 20 MVA 66/11 MVA | Aug. of 20MVA, 66/11KV T/F with 31.5MVA, 66/11KV | 199.78 | 199.78 | Work completed on 22.04.2022 | 2022-23
120 | 33/CZ/2022-23 Annexure-B | B | CZ | LDH | 133 |  |  | 66 KV line between 220KV S/S Jagraon to 66 KV S/S Raikot (upto Roomi T-off from 220 KV Jagraon side.) Replacement of conductor on 10KM/0.125 Sq" to 0.15 Sq" on the same structure upto Roomi T-off. | 10km /0.2sq" SC on DC Tower upto Roomi T-off from 220 KV Jagraon side 66 KV line between 220 KV Jagraon- 66KV S/S Raikot . | 269.60 -30.2 | 239.4 | Work stands completed | 2022-23
121 | 35/CZ/2022-23 Annexure-B | B | CZ | S/U LDH |  |  |  | 66 KV line bays (66KV Ringmain of 66KV S/S Amaltas, 66KV S/S Bahadurke and 66KV S/S Baloki.) | 2 No. 66 KV line bays- (1No.existing incoming bay at 66KV S/S Amaltas to be converted into breaker controlled bay) (1 No. existing incoming bay at 66KV S/S Baloki to be converted into breaker controlled bay) | 44.64 | 44.64 | bay Work at baloki completed in 05/2022 | 2022-23
122 | 60/WZ/2022-23 Annexure-B | B | WZ | BTI |  |  |  | a) 66 KV Boha to 66 KV Chak Ali Sher b)66 KV line bays | a)Replacement of 9.850 Km existing 0.15 sq” SC on SC with 9.850 Km Km/0.2sq” DC on DC b) 2 No. (1 No. at 66 KV Boha and 1 No. at 66 KV Chak Ali Sher) | 358.44 -29.74 58.00 | 386.7 | Work completed & One Ckt amongst 2 Ckts Energized during 6/2022, Energization of one ckt is pending due to non-preparation of bay at 66 KV S/S Boha. | 2022-23
123 | 81/WZ/2022-23 Annexure-B | B | WZ | BTI |  |  |  | Stringing of 2nd ckt. of 9.35 Km, 0.2 sq." from 220 KV Bajakhana to 66 KV Jeeda on already existing SC/DC line. | 1. Stringing of 2nd ckt. of 9.35 Km, 0.2 sq." from 220 KV Bajakhana to 66 KV Jeeda on already existing SC/DC line. 2. 01 no. bay at 66 KV S/S Jeeda. 3. 01 no. bay at S/S 220 KV S/S Bajakhana to planned by PSTCL. | 88.1 29.00 --- | 117.1 | work completed and lin charged on 12-6-2022 | 2022-23
[5 empty] | 23 | 15 | 4

## WZ
|  |  | WEST ZONE | [11 empty] | Annexure-I
Sr.no. | TWL sr.no. 2022-23 | Zone | Circle Name | MYT 2020-21 | MT 2021-22 | MT 2022-23 | Name of Work | Scope of Work | Estt. Cost (in lacs) | Total cost | Status | Year | Expenditure upto 31.03.2022 (in lacs) | Expenditure in Year 2022-23 (in lacs) | Expenditure in Year 2023-24 (in lacs) | Expenditure in Year 2024-25 (in lacs) | Expenditure in Year 2025-26 (in lacs)
1 | 48/WZ/2022-23 Annexure-A | WZ | BTI | 98 |  |  | 66 KV Boha 1x20 MVA, 66/11 KV | Addl.12.5 MVA,66/11kV | 203.61 | 203.61 | Work in progress | 2022-23 | 70.74 | 132.87
2 | 49/WZ/2022-23 Annexure-A | WZ | BTI | 89 |  |  | 66 KV Datewas 1X20 MVA, 66/11 KV | Addl 1X12.5 MVA | 203.61 | 203.61 | Work held up due to non availaibility of Breaker | Paddy -23 |  | 143 | 60.61
3 | 55/WZ/2022-23 Annexure-A | WZ | BTI |  | 87 |  | 66KV S/S Maluka 1x12.5 MVA,66/11 KV | Additional 6.3/8MVA, 66/11KV PT/F | 203.61 | 203.61 | Work in progress | 2022-23 |  | 203.61
4 | 67/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 1) Additional T-Off Link For 66 KV S/S C-Compound. a) 2nd 66kv link for 66 KV S/s C-Compound through T-off from MES Ckt.2 b) 66 KV Line Bays 2.)Augmentation Of 66 KV Line From 220 KV S/S GNDTP To 66 KV S.S MES Ckt.1 &Ckt.2 66 KV lines from 220 KV GNDTP to 66 KV MES BTI /6.6Km/ 0.15sq” /DC/RP 3.LILO at 66 KV Gobindpura. a) 220kv S/S GNDTP to 66kv S/S Gobindpura 7KM/0.2sq”/SC on DC. b) 66 KV Line Bays | a) Stringing of 2nd link of 500m. 0.2sq”/SC on DC on existing Towers for 66 kv S/S C-Compound as T-off from 66kv MES ckt.2 on existing DC Towers. b)1 No. new bay at 66 KV S/S C-Compound Replacement of 5.435 Km(approx.) remaining portion of(i.e Excluding 1st two spans which are already of 0.2 sq.” & 0.685 Km (approx.) already augmented) existing double ckt. 66KV line from 220 KV S/S GNDTP to 66 KV MES 0.15 sq” Tower/ RP line to 0.2sq”/ DC on DC line alongwith replacement of 6 no. rail poles with towers. a) Stringing of 2nd Ckt. 7Km/0.2sq”/SC on DC link from T-off point to 66kv S/S Gobindpura. on existing DC Towers for making LILO arrangement at 66kv S/S Gobindpura.. b) 1 No. bay at 66 kv S/S Gobindpura. | 4.71 29.00 197.77 -16.41 65.94 29.00 | 310.01 |  | 2022-23 |  | 100 | 210.01
5 | 68/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 1. a) New 66KV link between 66 KV S/Stns. Maluka & Kalyan Sukha b) 66 KV Line Bays 2. a) LILO of Nathana line at 66 KV S/S Bhucho b) 66 KV Line Bays | a) New 66 KV link 66 KV S/Stns. Maluka & Kalyan Sukha 11Km/0.2sq”/SC on DC Towers b) 2 No. new bays one each at 66 KV S/s Maluka & 66 KV S/s Kalyan Sukha a) 100 mtr./0.2 sq." b) 1 No. new bay 66 KV S/S Bhucho | 296.6 58.00 3.63 29.00 | 387.23 |  | 2022-23 ( A) 2023-24 ( B) |  | 100 | 287.23
6 | 69/WZ/2022-23 Annexure-B | WZ | BTI |  | 11 |  | a) LILO of 220kV Mansa- Budhlada ckt-2 28KM/ 0.2sq inchDC on DC . b) 66 KV Line Bays a) LILO of 220kV Mansa- Dhalewan ckt-2 of Mansa to Bhikhi at 66 KV S/S Bhikhi. 13KM DC on DC + 9KM 0.2sq inch SC on SC b) 66 KV Line Bays | 1) LILO of 220kV Mansa- Budhlada ckt-1 05KM/0.2sq inch DC on DC at 66KV Borowal. 2) 02 no. 66KV Bays at 66kV Borawal. 1) LILO of 220 KV Mansa -Dhalewan (Ckt.2 of Mansa to Bhikhi DC on DC) at 66 KV S/S Bhikhi- 0.6KM/0.2sq" DC on DC. 2) 02 no. 66 KV bays at 66 KV Bhikhi | 181.95 58.00 21.83 58.00 | 319.78 |  | Paddy-2023 |  | 224 | 95.78
7 | 70/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 1. a)Stringing of 2nd CKT from 220 KV GHTP to 66KV Bhairupa. (Incoming circuit is LE control at Bhairupa grid) b) 66 KV Line Bays 2. a) LILO at 66 KV Mehraj (incoming circuit is LE control at Mehraj Grid) b) 66 KV Line Bays 3. a) LILO at 66 KV Selbrah (incoming circuit is LE control at Selbrah S/S) b) 66 KV Line Bays | 1. a) i) Stringing of second circuit of approx. 12.9 KM of 0.2 sq" conductor on existing DC towers of GHTP to Bhairupa Circuit-1 from Bhairupa diversion point to 66KV S/S Bhairupa. ii) Stringing of 2nd ckt approx. 13.2 KM of 0.4sq" conductor on existing DC towers of GHTP to Phul CKT-2 line from GHTP to Phul Grid. b) 01 no. bay at 220KV GHTP Lehra Mohabbat. c) 01 no. bay at 66KV Bhairupa 2. a) Stringing of 2nd ckt approx. 2.02km of 0.2sq" conductor on SC on DC on existing DC Towers for making LILO at 66KV S/S Mehraj b) 01 no. bay at 66KV Mehraj 3. a) Stringing of 2nd ckt approx. 2.24 KM of 0.2sq" conductor on SC on DC on existing DC Towers for making LILO at 66KV S/S Selbrah. b) 01 no. bay at 66KV Selbrah | 121.51 220.83 29.00 29.00 19.02 29.00 21.10 29.00 | 498.46 |  | Paddy-2023 |  | 349 | 149.46
8 | 89/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 66 kV line from 220 kV Jhunir to Sardulgarh 16.9 KM / 0.2sq"/DC on DC/Tower. | a) Replacement/augmentation of existing 66 kV Line from 220 kV Jhunir to Sardulgarh 16.9 KM/0.2sq"/DC on DC/Tower with 16.9KM /0.2sq" HTLS conductor/DC on DC/Tower. Or b) Replacement/augmentation of existing 66kV Line from 220 kV Jhunir to Sardulgarh 16.9 KM/0.2sq"/DC on DC/Tower with 16.9 KM/0.4sq" ACSR conductor/on new DC on DC/Tower. | 994.05 -51.03 | 943.02 |  | 2023-24 on Paddy-2023 |  | 661 | 282.02
9 | 103/WZ/2022-23 Annexure-C | WZ | BTI |  | 63 |  | 66 KV RAMAN 2X12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 |  |  | CE/DS West Bathinda shall take necessary action to include the same in TWL 2022-23. |  |  | 157.03
10 | 106/WZ/2022-23 Annexure-C | WZ | BTI |  | 44 |  | 66 KV JOGA RALLA 1X20 MVA, 66/11 KV 1X12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 |  |  | CE/DS West Bathinda shall take necessary action to include the same in TWL 2022-23. |  |  | 157.03
11 | 28/WZ/2022-23 Annexure-A | WZ | FDK | 12 |  |  | a) 66 KV Sadiq-Jhoke Tehal Singh 19 KM/ 0.2 Sq." b) 66 KV Bays | 19 Km, 0.4 Sq.", DC on DC towers, both Ckts. to be terminated at 66 KV S/S Jhoke Tehal Singh) b) 2 No. 66 KV Bays at 66 KV S/S Jhoke Tehal Singh | 691.41 -57.38 58.00 | 692.03 | Work in progress | 2023-24 |  | 208 | 484.03
12 | 72/WZ/2022-23 Annexure-B | WZ | FDK |  |  |  | 66 KV line from 220 KV S/S Himmatpura to 66 KV S/S Patto Hira Singh 17 KM/0.2 sq"/SC on DC/T . ii) 66 KV line Bays | i) Stringing of 2nd circuit of 66 KV line from 220 KV S/S Himmatpura to 66 KV S/S Patto Hira Singh, 17 KM/0.2 sq"/SC on DC/T . ii) 1 no. at 66 KV S/S Patto Hira Singh. iii) 1 no. 66 KV Bay at 220 KV S/S Himmatpura to be planned by PSTCL. | 160.14 29.00 | 189.17 |  | Paddy-2023 |  | 133 | 56.17
13 | 73/WZ/2022-23 Annexure-B | WZ | FDK |  |  |  | 66 KV line from 220 KV S/S Himmatpura to 66 KV S/S Dina Sahib 15 KM/0.2 sq"/SC on DC/T . ii) 66 KV line Bays | i) Stringing of 2nd circuit of 66 KV line from 220 KV S/S Himmatpura to 66 KV S/S Dina sahib, 15 KM/0.2 sq" on existing DC/T . ii) 1 no. at 66 KV S/S Dina sahib iii) 1 no. 66 KV Bay at 220 KV S/S Himmatpura to be planned by PSTCL. | 141.30 29.00 -- | 170.3 |  | Paddy-2023 |  | 120 | 50.3
14 | 77/WZ/2022-23 Annexure-B | WZ | FDK |  | 51 |  | 66 KV S/s Baba Sheikh Farid 1x12.5MVA, 66/11KV | Addl.12.5 MVA, 66/11KV | 203.61 | 203.61 |  | 2023-24 |  | 62 | 141.61
15 | 100/WZ/2022-23 Annexure-B | WZ | FDK |  |  | 11 | 66KV S/S Patto Hira Singh, 1x31.5 MVA P/T/F T-1 + 1x20 MVA P/T/F T-2 | Augmentation of P/T/F T-2, 20MVA with 31.5MVA | 199.77 | 199.77 |  | Paddy -2023 |  | 140 | 59.77
16 | 101/WZ/2022-23 Annexure-B | WZ | FDK |  |  |  | 66KV S/S Focal Point Moga, 1x10/12.5 MVA + 1x20 MVA | Augmentation of P/T/F T-2 from 10/12.5MVA with 20MVA | 157.03 | 157.03 |  |  |  |  | 157.03
17 | 29/WZ/2022-23 Annexure-A | WZ | FRZ | 10 |  |  | 220 KV Botianwala to Makhu+Khosa Dal Singh 22.72 KM/ RP(12)+Tubeler Pole(130)+ACSR 0.1 Sq." | Replace with 22.72 KM 0.2 Sq." on SC on DC Towers. | 612.53 -68.61 | 543.92 | Work in progress | 2023-24 |  | 163.176 | 380.744
18 | 33/WZ/2022-23 Annexure-A | WZ | FZR | 31 |  |  | a) 66 KV Jhoke Tehal singh- Guru Har Sahai line. 14.66KM 0.1sq" RP | Replacement of 14.66KM RP line with 14.66 Km/0.2Sq" SC on DC line | 395.23 -44.27 | 350.96 | material alloted | 2023-24 |  | 106 | 244.96
19 | 63/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 66KV S/S FCI 2x12.5 MVA,66/11 KV | Augmentation of 12.5MVA, PT/F T-1 and T-2 with 20MVA, 66/11KV PT/F . | 314.06 | 314.06 |  | Paddy-2023 |  | 220 | 94.06
20 | 78/WZ/2022-23 Annexure-B | WZ | FZR |  | 78 |  | 66 KV S/S Fatehgarh Sabraon 1x20MVA, 66/11KV | Addl.12.5 MVA, 66/11KV | 203.61 | 203.61 |  | Paddy-2023 |  | 143 | 60.61
21 | 79/WZ/2022-23 Annexure-B | WZ | FZR | 112 |  |  | 66 KV S/s Hamad 1x10/12.5MVA, 66/11KV | Augmentation of 12.5 MVA, 66/11KV PTF with 20MVA, 66/11KV. | 157.03 | 157.03 |  | paddy-2023 |  | 110 | 47.03
22 | 82/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | To provide Ring Main system to 66KV S/S Ferozepur City. | 1. T-off 66KV line from 220 KV Ferozepur to Zira Gate (from point A to B as per sketch) 475 meters/ 0.2 sq. inch/ SC on DC (overhead) and 2 no. Ordinary Towers. 2. 12 no. Narrow base Towers (from point B to D as per sketch) 1650 meters/ 0.2sq". 3. 66KV underground cable (from point D to E as per attached sketch) 1250 meters/ 240 mm2. 4. 01 no. bay at 66KV S/S Ferozepur city. | 12.80 32.30 (20.72 NB Towers cost+15.58 Conductor Cost) 314.25 29.00 | 388.35 |  | 2023-24 |  | 50 | 338.35
23 | 97/WZ/2022-23 Annexure-B | WZ | FZR |  |  | 52 | 66KV S/S Mallanwala, 1x12.5 MVA 66/11 KV + 1x20 MVA 66/11 KV | Augmentation of P/T/F T-1, 12.5MVA with 20MVA P/T/F | 157.03 | 157.03 |  | Paddy-2023 |  | 110 | 47.03
24 | 98/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 66KV S/S Makhu, 2x20 MVA, 66/11KV | Augmentation of P/T/F T-1, 20 MVA with 31.5MVA | 199.77 | 199.77 |  | 2022-23 |  | 199.77
25 | 16/WZ/2022-23 Annexure-A | WZ | MKT |  |  |  | a) 132 KV Badal-Lambi 66 KV Line 9.5 KM/ 0.2Sq." SC on DC b) 66 KV Bays | a) 220 KV Badal end 2.144 KM on Multi ckt towers 0.2 Sq." to replace the existing 66 KV Killianwali line b) 66 KV S/Stn Lambi end 0.360 KM on Multi ckt towers 0.2 sq." to replace Tharajwala DC line. c) Remaining portion 0.2Sq" on DC on DC towers d) 1 No. at Lambi end 1 No. 66KV Bay at 220KV Badal to be planned by PSTCL. | 210.51 -6.47 35.34 -1.09 254.58 29.00 | 521.87 | Budha Dal Dispute at Tower no 23 and Akal University dispute at TL no 5 & TL no 6. | Paddy-2023 |  | 366 | 155.87
26 | 25/WZ/2022-23 Annexure-A | WZ | MKT | 30 |  |  | 33/66 KV line 220 KV Abohar (upgraded from 132 KV S/S)-Khui Khera--18km /0.1sq" HRP | 1) Replace of initial 1 kM 33/66kV line with 1.8 Ckt. Km 240mm2 U/G XLPE Cable (4X1C). 2) Repl of remaining portion of 17Km with 0.2Sq" SC on DC towers | 452.52 -54.36 458.32 | 856.48 | Revised Estimate Under approval | Paddy -23 |  | 600 | 256.48
27 | 32/WZ/2022-23 Annexure-A | WZ | MKT |  | 31 |  | 66 KV Abohar to Khuian Sarvar 13 KM/ 0.1Sq." on Rp | Replacement of 13KM HRP with 13 KM 0.2 Sq." SC on DC Tower line | 350.48 -39.26 | 311.22 | pending due to dispute at Tl no-2,3,4,24,25,soil testing pending at Tl. No-7,10 . | 2023-24 |  | 94 | 217.22
28 | 57/WZ/2022-23 Annexure-A | WZ | MKT |  |  |  | 66 KV Banwala Hanvanta 1x12.5 MVA,66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | Work in progress | Paddy-2023 |  | 143 | 60.61
29 | 62/WZ/2022-23 Annexure-B | WZ | MKT | 103 |  |  | 66 KV Lambi 1x12.5+1x6.3/8 MVA, 66/11kV | Augmentation of 8 MVA 66/11 KV PTF with 12.5 MVA 66/11 KV. | 85.91 | 85.91 |  | Paddy-2023 |  | 61 | 24.91
30 | 64/WZ/2022-23 Annexure-B | WZ | MKT |  |  |  | 66KV S/S Karni Khera 1x20 MVA,66/11 KV | Additional 6.3/8MVA, 66/11KV PT/F | 203.61 | 203.61 |  | Paddy-2023 |  | 143 | 60.61
31 | 65/WZ/2022-23 Annexure-B | WZ | MKT |  |  |  | 66KV S/S Maur 1x6.3/8 MVA,66/11 KV | Additional 6.3/8MVA, 66/11KV PT/F | 203.61 | 203.61 |  | 2023-24 |  | 143 | 60.61
32 | 75/WZ/2022-23 Annexure-B | WZ | MKT |  | 157 |  | 220 KV Abohar to 66 KV Amarpura/ 15KM/0.1 sq"/HRP LILO at 66 KV Hanumangarh Road Abohar 66 KV Amarpura to 66 KV Sito Guno/ 17.56KM/0.1 sq"/HRP | 1. Augumentation of 15KM/0.1 sq"/HRP with 0.2sq" /SC on DC 2. a) Stringing of 2nd ckt of 1.12KM/0.2sq"/ on existing DC tower for conversion of solid T-off (Abohar- Hanumangarh Road line) to LILO for 66 KV S/S Hanumangarh Road Abohar b) 01 no. new bay at 66 KV Hanumangarh Road Abohar 1. Augmentation of 17.5KM/0.1sq"/ HRP with 0.2sq"/ SC on DC | 404.40 -45.30 10.55 29.00 471.8 -52.85 | 157.03 |  | 2023-24 |  | 48 | 109.03
33 | 76/WZ/2022-23 Annexure-B | WZ | MKT |  | 50 |  | 66 KV S/s Bhai K Khera 1x6.3/8MVA, 66/11KV | Addl.6.3/8 MVA, 66/11KV P/T/F | 203.61 | 203.61 |  | Paddy-2023 |  | 143 | 60.61
34 | 80/WZ/2022-23 Annexure-B | WZ | MKT | 104 |  |  | 66 KV S/s Sikhwala 1X12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 |  | Paddy-2023 |  | 110 | 47.03
35 | 102/WZ/2022-23 Annexure-B | WZ | MKT |  |  |  | New 66KV line from 66KV Sikhwala to 66KV Fatehpur Manian | a).66KV line from Sikhwala to Fatehpur Manian 6KM/0.2 sq"/ SC on DC. b). 1 no. bay at 66KV Sikhwala. c). 1 no. bay at 66KV Fatehpur Manian. | 161.76 58.00 | 219.76 |  | 2023-24 |  | 66 | 153.76
36 | 125/WZ/2022-23 Annexure-C | WZ | MKT |  |  |  | i) New 66KV Line from 66kV S/S Rupana to 66kV S/S Malout Road Muktsar. ii) 66 kV line bays | 1) To errect new link 6 KM/0.2sq inch/ SC on DC 2) 2 no bays (1 no. bay at 66KV S/S Rupana & 1 no. bay at 66KV S/S Malout Road Muktsar) | 161.76 58.00 | 219.76 |  | CE/DS West Bathinda shall take necessary action to include the same in TWL 2022-23. |  |  | 219.76
37 | 41/WZ/2022-23 Annexure-A | WZ | MKT |  |  |  | 66KV Banwala Hanuwanta to Khui Khera new line | 9KM SC on DC new line 0.2Sq " ACSR & one No. at Banwala Hanuwanta and one Bay at Khui Khera | 242.64 58.00 | 300.64 | 45 Stubs OK and 4 No. Towers also errected. | 2022-23 | 210.02 | 90.62
38 | 2/WZ/2022-23 Annexure-A | WZ | BTI |  |  |  | a) 66 KV SC 13.6 KM/0.2sq” line from Jaga Ram Tirath – Nangla Jorkian b) 66 KV SC 16.7 KM/0.2sq” line from Nangla Jorkian - Kahnewal c) LILO of 220 Jhunir - 66 KV Sardulgarh 66 KV line at 66 KV Kahnewal d) 66 KV Bays | (i) 1.5 Km/0.2 Sq." on Multi Ckt towers at Nangla-Jorkian to replace 0.15 Sq." SC on SC line of Raipur-Nangla Jorkian. (ii) Stringing of 2nd Ckt. 1.5 Km 0.2 Sq." 66 KV line on MC towers for Jaga Ram Tirath--Nangla Jorkian Circuit (iii) 12.1 Km/ 0.2 Sq." SC on DC to complete Jaga Ram Tirath--Nangla Jorkian Circuit. 16.7 KM 0.2sq” SC on DC Replacement of Existing 0.15 Sq." SC on SC line (3.4 Km) with 0.2 Sq." DC on DC towers from T-off 0.2 Sq."66 KV S/Stn. Kahnewal to create LILO. 5 No.( 2 No. at Kahnewal,2 No. Nangla Jorkian & 1 No. at Jagga Ram Thirth) | 116.16 10.53 257.85 355.87 96.36 -10.27 140.00 | 966.5 | a) Work stopped due to farmer dispute at TL-42,44,45,45A,5A. B) Work Completed on 25-02-2019. c) Line enrgized on 12.04.2022 |  |  | 500 | 200 | 266.5
39 | 6/WZ/2022-23 Annexure-A | WZ | FZR |  |  |  | a) 66 KV Line from 220 KV Katorewala (Malkatora) - Chak Sherewala SC on HRP-21 KM 0.1/0.15 sq" b) 66 KV line bays | Replacing 21KM SC on H-R.P line with 21 KM 0.2 sq” DC on DC towers line. b) 1 No. at Chak shere wala Side | 764.19 -63.42 29.00 | 729.77 | Estimate for civil work under sanction |  |  | 10 | 420 | 299.77
40 | 7/WZ/2022-23 Annexure-A | WZ | FZR |  |  |  | a) 66 KV Chak Sherewala- Lakhewali SC on SC-6 KM/0.15sq” b) 66 KV line bays | Replacing 6 KM SC on SC Line with 6 KM/0.2 sq” DC on DC towers line. b) 2 No. (1 no. at 66 KV Chak Sherewala and 1 no. at 66KV -Lakhewali) | 218.34 -18.12 58.00 | 258.22 | BN Tower dispute solved. Bay pending |  |  | 181 | 77
41 | 8/WZ/2022-23 Annexure-A | WZ | FZR | 128 |  |  | 220 KV Ghubaya- Fattanwala 66 KV line 31.5 Km/0.15Sq" SC on RP 66 KV line bays | Repl. of first/initial 12 Km SC on SC line from Ghubaya with 12 KM/0.2Sq" DC on DC towers & Stringing of 2nd Ckt from Jallalabad T-off point to Chak Janisar T-off point 12.5Km/0.2Sq" on DC towers. 1 No. 66KV Bay at 66KV Fattanwala to control 66KV Jhariwala. 1 No. 66KV Bay at Ghubaya (for fattanwala) to be planned by PSTCL. | 436.68 -36.24 117. 8 29.00 | 554.44 | Line work completed. 66kv Bay construction at 220 G/S/S Ghubaya and vetted sketch by T.L. Organization has been sent to PSTCL. |  |  | 388 | 166
42 | 12/WZ/2022-23 Annexure-A | WZ | FDK |  |  |  | 132KV KotKapura- Sandhwan 220 KV line. 7.25Km/0.125Sq" SC on RP 66 KV Bays (to be planned by PSTCL) | a) 1 Km/0.2 Sq." on Multi Ckt tower from 220 KV Sandhwan for 132 KV Kotakpura-I b) 5.75 km/0.2 Sq." DC on DC from 220 KV Sandhwan (beyond MC towers) to 132 KV Kotakpura-I (one Ckt for Kotakpura-I –Faridkot & other one for Sandhwan- Kotakpura-I). c) 2 x 0.095 Ckt-km U/G XLPE Cable 240 mm2 for crossing of both Ckts from 132 KV Moga-Muktsar line. d) 3 No. (2 No. at 220 KV Sandahwan and 1 No. at 132 KV Kotkapurato be planned by PSTCL) | 98.19 209.24 42.99 | 350.42 | Sanction of Route plan from TL no 23 to TL no 25 is under process. |  |  | 0 | 150 | 200.42
43 | 14/WZ/2022-23 Annexure-A | WZ | MKT | 27 |  |  | 66 KV Arniwala- 220KV Malkatora (Malout) 66 KV line. 8Km/0.2Sq" on Towers+ 26 Km/0.1Sq' on RP (Total Length 34Km) 66 KV Bay | 1) 3.5 Kms at Malkatora end 4 ckts with 0.2 Sq” on multi Ckt. Towers (1 Ckt to be used for Madhir Line) 2) 22.5 Kms / 0.2Sq” DC on DC 3) 1 No. 66KV Bay at 66 KV S/S Arniwala. | 271.04 637.65 -78.52 28.00 | 858.17 | Work stopped due to Court Case . |  |  |  | 200 | 260 | 398.17
44 | 17/WZ/2022-23 Annexure-A | WZ | BTI | 17 |  |  | 66 KV Talwandi- Maur Line 22 KM/ 0.125 Sq." on RP | 1. 21.6 Ckt Kms (approx.), 0.2 Sq." SC on DC towers (Talwandi Sabo end) to replace existing HRP line. It shall be connected to one of the Ckts on MCT (0.41 Ckt Km) planned under planning no. 5/WZ/ 2020-21 & 2021-22/Annexure-A 2.Stringing of 2nd ckt. On existing 6.5KM SC on DC line to make LILO at Kamalu Swaitch. 3. 1 No. Bay at 66KV Kamalu Swaitch. 4.) Conversion of LE controlled to Breaker controlled at 66KV Kamalu Swaitch. | 582.33 -65.23 61.23 29.00 22.32 | 629.65 | Work stopped due to Court Case . |  |  |  | 300 | 200 | 129.65
45 | 19/WZ/2022-23 Annexure-A | WZ | BTI | 18 |  |  | 66 KV Talwandi- Raman Line 13.3 KM/ 0.125 Sq." on RP | Replacement of 13.3 KM 0.125/HRP with 13.3KM 0.2 Sq." SC on DC Towers | 358.56 -40.16 | 318.4 | Budha Dal Dispute at Tower no 23 and Akal University dispute at TL no 5 & TL no 6. |  |  | 223 | 95
46 | 24/WZ/2022-23 Annexure-A | WZ | FZR | 15 |  |  | i) 66KV line Jhoke Tehal Singh - Mamdot T-off at Rauke Hithar ii) 66KV Bays | Stringing of second Ckt 0.2sq"/12KM from Jhoke Tehal Singh upto T-off Rauke Hithar on DC towers for separation of Raoke Hithar and Mamdot line. b) 1 No. at 66KV Jhoke Tehal Singh c) 1 no. bay at 66 KV Jhok Tehal Singh for 66 KV Mamdot ckt-2 (already planned at 28/WZ/2022-23/ Annex.A.) d) 01 no. bay for 66KV Guruharsahai (already planned at 28/WZ/2022-23/Annex.A.) e) 0.750KM SC on DC 0.2 sq” for shifting mamdot Ckt-1 & Ckt-2 to new location. Due to Bay space constraint at 66KV Jhok Tehal Singh. | 113.04 29.00 20.22 | 162.26 | Line work completed and only bay pending |  |  | 114 | 48
47 | 26/WZ/2022-23 Annexure-A | WZ | FDK | 8 |  |  | New link to create 2nd 66 KV source for 66 KV Faridkot from 220 KV Sandhwan | (i) 6 km 66 KV line 0.2 Sq." SC on DC new line. (ii) 2.4 km 0.2 Sq." DC on MCT to replace Rail pole (0.15 Sq.”) line portion. (One Ckt on MCT for Sandhwan–Faridkot & other for Kotakpura- Faridkot line). (iii) 460 Ckt meter 240 mm2 XLPE Cable for 2nd Ckt at only Faridkot end (First Ckt to be laid through 240 mm2 Cable as deposit work of NHAI). (iv) 2 no. 66 KV bays at 66 KV S/S Faridkot) 1No. Bay at 220 KV S/S Sandhwan to be planned by PSTCL. | 161.8 235.7 -7.25 115.6 58.00 | 563.85 | i) Work already completed ii) Revised Estimate Under Process iii) 1 no CKt is completed |  |  | 395 | 169
48 | 27/WZ/2022-23 Annexure-A | WZ | FZR | 137 |  |  | a) 220KV Mastewala - 66 KV Zira line b) 220 KV S/S Bottianwala -66 KV Zira line (stringing & dismantlement) c) 66 KV bays | a) (i) 1.1Km/0.2Sq"on MultiCkt.Towers from TL 61 to 67 at 66KV S/S Zira end by using existing ROW of 220KV Botianwala-66KV Zira Line. ii) Remaining portion of 7Km /0.2Sq" SC on DC towers from 220KV S/S Mastewal end. b) i)Stringing of 1.1Km/.2Sq"/ SC on multi Ckt. Towers (cost covered in part a) ii) Dismantlement of 1.5Km/0.1Sq" HRP of existing 7Km /0.1Sq" HRP line from 66KV S/S Zira end. c) i) 01 no. new bay at 66 KV S/S Zira for Botianwala line because existing LE controlled bay cannot be converted into to Breaker controled due to space constraints and will be shifted to extended portrion of bus bar. ii) 01 no. at bay 66 KV S/S Zira for Mastewala line. iii) 01 no. bay at 220 KV S/S Mastewala to be planned by PSTCL. iv)) Extension of existing Bus-Bar of conductor 52 Mtr.size 0.4sq" v) 66 KV cable of 143 Meters/240mm sq from Multi Ckt Tower to proposed space for bay | 108.00 -3.32 188.72 -21.14 -4.53 29.00 29.00 26.09 35.95 | 387.77 | 70/70 tower erected and space constraint at 66KV zira S/S and under ground cable has been finalized by the committee for commissioning the line. |  |  | 300 | 87.77
49 | 31/WZ/2022-23 Annexure-A | WZ | MKT | 13 |  |  | 66 KV Muktsar to Fattanwala 13 KM/ 0.125 Sq." on RP | Replacement of 13KM HRP with 13 KM 0.2 Sq." SC on DC Tower line | 350.48 -39.26 | 311.22 | Work in progress |  |  | 218 | 93
50 | 42/WZ/2022-23 Annexure-A | WZ | BTI | 73 |  |  | 66 KV line from 132KV IGC to 66KV KotShamir/8.7Km/0.15sq"/RP | 8.7Km/0.2sq" SC on DC | 234.55 -26.27 | 208.28 | material allocated and shut down apply problem remains same. |  |  | 146 | 62
51 | 46/WZ/2022-23 Annexure-A | WZ | BTI | 130 |  |  | a) i) 66KV line from 66KV Bhagta to 132KV Samadh Bhai/ 25K/0.1sq”/RP. ii) 66 KV Line Bays b) i) 66KV line from 66KV Bhagta to 132KV Samadh Bhai T-off Bhodipura / 6Km/0.2sq”/SC on DC ii) 66 KV Line Bays iii) 66 KV Bus bar c) i) 66KV line from 66KV Bhagta to 132KV Samadh Bhai T-off Tharaj/0.3Km/ 0.2sq”/SC on SC ii) 66 KV Line Bays iii) 66 KV Bus bar d) 66KV line bay for 66KV line from 220KV Bajakhana to 66KV Bhagta/14Km/ 0.2sq”/DC on DC. | Augmentation of existing 66 KV line from 66KV Bhagta to 132KV Samadh Bhai RP line with 25Km/0.2sq”/SC on DC Tower line. & dismantlement of existing Rail Pole line. Conversion of 1 No. isolator controlled bay at 66KV S/s Bhagta end to breaker controlled line. a) Stringing of 2nd circuit on existing DC Tower from T-off 66KV Bhodipura with LILO at 66KV S/s Bhodipura to make existing 6Km/0.2sq”/ SC on DC with DC on DC. b) 1 No. new bay at 66KV S/s Bhodipura. c) Conversion of 1 No. isolator controlled bay at 66KV S/s Bhodipura end to breaker controlled line. d) 66 KV Bus bar at 66 KV S/s Bhodipura LILO at 66KV S/s Tharaj/ Replacement of existing 0.3Km/0.2sq”/ SC on DC with 0.3Km/0.2sq”/DC on DC 1 No. bay at 66KV S/s Tharaj. Conversion of 1 No. isolator controlled bay at 66KV S/s Tharaj end to breaker controlled line. 66 KV Bus bar at 66 KV S/s Bhodipura 1 No. bay at 66KV S/s Bhagta end to make isolator control line to breaker control line. | 674.00 -75.5 22.32 56.52 29.00 22.32 8.5 10.91 -0.90 29.00 22.32 8.50 22.32 | 829.31 | Work in progress |  |  | 200 | 300 | 329.31
52 | 47/WZ/2022-23 Annexure-A | WZ | MKT | 91 |  |  | 66 KV Fatta Khera 1x12.5 MVA, 66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | Work held up due to non availaibility of Breaker |  |  | 143 | 61
53 | 50/WZ/2022-23 Annexure-A | WZ | MKT | 68 |  |  | 66 KV line from 132KV Muktsar to 66KV Lubianwali/15Km/0.125sq"/RP | Replacement of Existing 15KM/HRP line with 15Km/0.2sq" SC on DC | 404.4 -45.3 | 359.1 | Work in progress |  |  | 200 | 159
54 | 59/WZ/2022-23 Annexure-B | WZ | MKT |  | 6 |  | New link of 66 KV Killi Nihal Singh Wala-Bhalaiana line. 66 KV Bays | i) 8.443 km SC on Dc line 0.2 sq/inch ACSR ii) 1 No. Bay at Killi Nihal Singh Wala and 1 no. bay at Bhalalana iii) 60 circuit meter SC on DC 240 mm sq under ground cable. | 227.62 29.00 27.15 | 283.77 | Work in progress |  |  | 100 | 100 | 83.77
55 | 83/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | a) 66 KV Mirze Ke (including 1No. 66 KV Bay) b) 66KV line from 220KV Kot Karor to 66KV S/S Mirze Ke (New) c) 66KV Bays | 1x10/12.5 MVA, 66/11 KV 15.2 KMs / 0.2 Sq" SC on DC towers (1 No. at 220 KV S/Stn Kot Karor to be planned by PSTCL) | 219.92 409.79 ----- | 629.71 | Layout plan yet to be issued. |  |  |  | 200 | 200 | 229.71
56 | 35/WZ/2022-23 Annexure-A | WZ | FDK | 58 |  |  | a) LILO of 66 KV line emanating from 132 KV Kotakpura-I to 66 KV S/S Talwandi Road Faridkot at 66 kV Baba Sheikh Farid. b) 66 KV Line Bays | 100 Ckt meters, 0.2 Sq.”, DC on DC line for creation of LILO of 66 KV line emanating from 132 KV Kotakpura-I to 66 KV S/S Talwandi Road at 66 KV S/S Baba Sheikh Farid. 1 No. new 66 KV line bay at 66 KV S/S Baba Sheikh Farid 1 No. bay at 66KV S/s Baba Sheikh Farid to make isolator control line to breaker control line. | 3.63 29.00 22.32 | 54.95 | [5 empty] | 45 | 9.95
57 | 36/WZ/2022-23 Annexure-A | WZ | MKT |  | 10 |  | a) New proposed 66 KV S/S Ajit Nagar, behind new grain Market, Abohar. Including 1 No. incoming 66 KV bay with isolator (without 66KV Breaker) b) Cost of Land c) Tentative Proportionate cost of 3.5KM backup line to be refunded to MES | 1x20MVA, 66/11 KV | 285.93 40.40 39.40 | 365.73 |  |  |  |  | 0 | 140 | 225.73
58 | 58/WZ/2022-23 Annexure-B | WZ | FDK | 65 |  |  | 220 KV Baghapurana to Nathuwala 13.58 KM/ 0.2/0.15Sq." | Replace with conductor size of 2 Phases of Ckt-1 is 0.15 Sq." and Conductor size of 3rd Phase is 0.2 Sq.". where as conductor size of 2 Phases of ckt-2 is 0.2 Sq." | 95.33 | 95.33 | [5 empty] | 75 | 20.33
59 | 61/WZ/2022-23 Annexure-B | WZ | BTI | 119 |  |  | 66kV HEEREWALA 1x12.5 MVA 66/11 kv | Additional 1x 6.3/8 MVA 66/11 KV PTF | 203.61 | 203.61 | [5 empty] | 150 | 53.61
60 | 66/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | New link for Shifting of load of 66KV Dan Singh Wala and 66KV Goniana circuits from 66KV S/S Malout Road Bathinda to 220KV GNDTP sub station. | 1) New Link DC on DC 0.4 sq" inch conductor of approx. 2.6 Kms of length. 2) 01 number bay at GNDTP (01 number bay is already spare at GNDTP). | 178.28 | 178.28 | [5 empty] | 75 | 103.28
61 | 71/WZ/2022-23 Annexure-B | WZ | MKT |  |  |  | i)New 66 KV line from 66 KV S/S Gilzewala to 66 KV S/S Rupana. ii) 66 KV line Bays 66 KV line from 220 KV Katorewala to 66 KV S/S Gilzewala 18.5 KM/0.2 sq."/SC on DC. ii) 66 KV line Bays | i) 12 KM/0.2 sq"/SC on DC. ii) 2 no. Bays ( 1 no. at 66 KV S/S Gilzewala and 1 no. 66 KV S/S Rupana) i) Stringing of 2nd circuit of 66 KV line from 220 KV Katorewala to 66 KV S/S Gilzewala, 18.5 KM/0.2 sq."/SC on DC. ii) 1 no. 66 KV Bay at 66 KV S/S Gilzewala. iii) 1 no. 66 KV Bay at 220 KV Katorewala to be planned by PSTCL. | 323.52 58.00 174.27 29.00 -- | 584.79 | [5 empty] | 150 | 434.79
62 | 74/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 66KV S/S PanjeKe 12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | [5 empty] | 50 | 107.03
63 | 84/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 66 kV Line from Sardulgarh to 66 kV Sangha 14KM / 0.15sq"/SC on SC/Tower. | a) Replacement/augmentation of existing 66 kV Line from Sardulgarh to 66 kV Sangha from 14KM / 0.15sq"/SC on SC/Tower to 14KM/ 0.2sq" / SC on DC/towers. | 377.4 -42.28 | 335.12 | [5 empty] | 200 | 135
64 | 85/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | Replacement of existing 66 kV Tibbi Khurad Line T-OFF from 66 kV line Jhoke Harihar-FCI CKT-2. | a) Replacement/augmentation of existing Rail pole line of approx. 16 KM/0.125 sq" conductor with 16 KM/SC on DC/0.2sq"/tower line from T-OFF point to 66 kV Sub-Station Tibbi Khurad. | 431.4 -48.32 | 383.08 | [5 empty] | 200 | 183
65 | 86/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 66 kV line from 220 kV Dharmkot to 66 kV Kot Ise Khan 8.6 KM /0.2sq"/65mm sq/RP/SC on DC/T. | a) Replacement/augmentation of existing Rail pole line of approx. 4.6KM (from B to C as per sketch)/65mm sq/Rail-Pole with 4.6KM/ 0.2sq" /SC on DC/ tower. b) Conversion of existing 01 no. isolator controlled Bay to breaker control at 66 kV S/S Kot Ise Khan | 124 -13.89 22.32 | 132.43 | [5 empty] | 100 | 32
66 | 87/WZ/2022-23 Annexure-B | WZ | FDK |  |  |  | 66 kV line from 220 kV Baghapurana to 66 kV Samalsar 16.14 KM (approx.)/0.2sq"/SC on DC/T. | a) Stringing of second circuit of 66 kV line from 220 kV Baghapurana to 66 kV Samalsar 16.14 KM (approx.)/0.2 sq" /SC on DC/ tower on existing DC towers. b) 01 no. Bay at 66 kV S/S Samalsar. c) 01 no. Bay at 220 kV Baghapurana to be planned by PSTCL. | 152.03 29.00 - | 181.03 | [5 empty] | 120 | 61
67 | 88/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 220 kV Kotkaror-66 kV Dagru Line T-OFF Jhandiana 13.5 KM approx/0.2sq" and 65mm sq /SC on DC/T/Railpole. | a) Stringing of 2nd CKT of 2 KM/0.2 sq" on existing DC towers from 220 kV Kotkaror to T-OFF point Jhandeana. b) Replacement/augmentation of existing Rail pole line of approx. 11.5 KM/65mm/ Railpole with 11.5 KM/0.2sq"/DC on DC/T from T-OFF point Jhandeana to 66 kV S/S Dagru. c) 1no. Bay at 66 kV S/S Dagru . d) 1 no. Bay at 220 kV Kotkaror to be planned by PSTCL. | 18.84 418.48 -34.73 29.00 | 431.59 | [5 empty] | 200 | 232
68 | 90/WZ/2022-23 /Annexure-B | WZ | FZR |  |  |  | Augmentation/Replacement of existing conductor of 66 KV line from 220 KV Botiawala to 66 kV Thatha Sahib 6.12 KM/ 0.2sq"/Tower/ DC on DC. | a) Augmentation/Replacement of existing conductor of 66 KV line from 220 KV Botiawala to 66 kV Thatha Sahib 6.12 KM/0.2sq"/Tower/ DC on DC with HTLS (High Temperature Low Sag) conductor/DC on DC on existing Towers. or b) Augmentation/Replacement of existing conductor of 66 KV line from 220 KV Botiawala to 66 kV Thatha Sahib 6.12 KM/0.2sq"/Tower/ DC on DC with 6.12KM/ 0.4sq"/ Tower/ DC on DC | 359.97 -18.48 | 341.49 | [5 empty] | 200 | 141
69 | 91/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | To Provide LILO arrangement at 66KV S/S Civil line, Bathinda | 1. Replacement of T-off portion of 66KV S/S Civil line Bathinda of 1.3KM/0.15 sq' inch/ SC on SC with 1.3KM/ 0.2sq' inch/ DC on DC for making LILO arrangement. 2. 01 no. new bay at 66KV Civil Line Grid. 3. Lying of 240 sq mm U/G cable from existing S60 tower inside the grid to the proposed new bay of length 75 meter x 4 (300 mtr). 4. Lying of (per phase) 240 sq mm U/G cable from the new errected 1st DC on DC tower outside grid to the already exiting bay of length 125 mtr x 4 (500 mtr). 5. To extend the existing 66KV Bus Bar to connect with the new proposed 66KV bay with the help of isolater switch. 6. Shifting of exiting capacitor bank to the new vacant space in the grid. 7. Dismantlement of 1 no. span of 0.15 sq mm conductor from the exiting S60 tower to the exiting bay. | 47.30 (-3.90) 29.00 75.42 125.70 | 273.52 | [5 empty] | 195 | 79
70 | 92/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 66 KV line from 220KV Mansa to 66KV Joga Ralla | Augmentation/Replacement of conductor from 0.2sq" to 0.4 sq" 11.6KM DC on DC with new tower. | 795.41 (-35.03) | 760.38 |  |  |  |  | 160 | 300 | 300.38
71 | 93/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | Augmentation/Replacement of existing conductor of 66 kV line from 220 kV Ghubaya to 66 kV Ladhuka CKT-1, 08 KM/ 0.4sq"/ Tower/DC on DC | Augmentation/Replacement of existing conductor of 66 kV line from 220 kV Ghubaya to 66 kV Ladhuka CKT-1 08 KM/0.4sq"/Tower/ DC on DC (existing) with 08 KM/0.4 sq" HTLS (High Temperature Low Sag) conductor DC on DC on existing Towers. | 655.04 -24.16 | 630.88 | [5 empty] | 300 | 331
72 | 94/WZ/2022-23 Annexure-B | WZ | MKT |  |  |  | Augmentation/Replacement of existing conductor of 66 kV line from 66 kV Ladhuka to 66 kV Rana 15 KM/ 0.2sq"/ Tower/ SC | Augmentation/Replacement of existing conductor of 66 kV line from 66 kV Ladhuka to 66 kV Rana 15KM/0.2sq"/Tower/ SC with 15 KM/0.2 sq" HTLS (High Temperature Low Sag) conductor/SC on existing Towers. | 441.15 -45.3 | 395.85 | [5 empty] | 200 | 195.85
73 | 95/WZ/2022-23 Annexure-B | WZ | BTI |  |  |  | 66KV S/S Jaga Ram Tirth 1x 12.5 MVA 66/11 KV | Additional of P/T/F 12.5MVA | 203.61 | 203.61 | [5 empty] | 180 | 23.61
74 | 96/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 66KV S/S Dhanna Shahid 1x20 MVA 66/11KV | Additional P/T/F 12.5MVA | 203.61 | 203.61 | [5 empty] | 150 | 53.61
75 | 99/WZ/2022-23 Annexure-B | WZ | FZR |  |  |  | 66KV S/S Pojoke, 1x12.5 MVA 66/11 KV | Augmentation of P/T/F T-1, 12.5MVA with 20MVA | 157.03 | 157.03 | [5 empty] | 120 | 37.03
76 | 104/WZ/2022-23 Annexure-C | WZ | FZR |  | 64 |  | 66 KV Ch. Budho ke 1x20 MVA,66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | [5 empty] | 180 | 23.61
77 | 105/WZ/2022-23 Annexure-C | WZ | FZR |  | 59 |  | 66 KV S/S Dhandi Kadim 1x12.5 MVA, 66/11 KV 1x20 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | [5 empty] | 140 | 17.03
78 | 107/WZ/2022-23 Annexure-C | WZ | MKT |  | 57 |  | 66 KV Nandgarh-Ghudda 1X6.3/8 MVA, 66/11 KV 1X12.5 MVA, 66/11 KV | Augmentation of 8 MVA 66/11 KV PTF with 12.5 MVA 66/11 KV. | 85.91 | 85.91 | [5 empty] | 70 | 15.91
79 | 108/WZ/2022-23 Annexure-C | WZ | FDK |  | 22 |  | 66KV Golewala 1X12.5 MVA, 66/11 KV 1X20 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | [5 empty] | 140 | 17.03
80 | 109/WZ/2022-23 Annexure-C | WZ | MKT |  | 62 |  | 66 KV Rupana 1X20 MVA, 66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | [5 empty] | 180 | 23.61
81 | 110/WZ/2022-23 Annexure-C | WZ | BTI |  | 26 |  | 66 kV Dalel Singh Wala 1x10/12.5, 66/11 KV | Additional 1x 12.5 MVA 66/11 KV PTF | 203.61 | 203.61 | [5 empty] | 180 | 23.61
82 | 111/WZ/2022-23 Annexure-C | WZ | BTI | 99 |  |  | 66 KV Aklia Kalan 1x12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | [5 empty] | 140 | 17.03
83 | 112/WZ/2022-23 Annexure-C | WZ | MKT | 114 |  |  | 66 KV S/S Sitto Gunno 1x12.5 MVA 66/11 kv | Additional 1x 12.5 MVA 66/11 KV PTF | 203.61 | 203.61 | [5 empty] | 180 | 23.61
84 | 113/WZ/2022-23 Annexure-C | WZ | MKT | 14 |  |  | 66KV S/S Ghattianwali Jatta 1x6.3/8 MVA, 66/11kV | Augmentation of 8 MVA 66/11 KV PTF with 12.5 MVA 66/11 KV. | 85.91 | 85.91 | [5 empty] | 70 | 15.91
85 | 114/WZ/2022-23 Annexure-C | WZ | BTI | 55 |  |  | 66KV Bay at 66KV S/Stn Kamalu Swaich | One No. Bay | 29 | 29 | [5 empty] | 29 | 0
86 | 115/WZ/2022-23 Annexure-C | WZ | BTI | 56 |  |  | 66KV Bay at 66KV S/Stn Chak Alisher | One No. Bay | 29 | 29 | [5 empty] | 29 | 0
87 | 116/WZ/2022-23 Annexure-C | WZ | MKT | 57 |  |  | 66KV Bay at 66KV Fattanwala | One No. Bay | 29 | 29 | [5 empty] | 29 | 0
88 | 117/WZ/2022-23 Annexure-C | WZ | BTI | 102 |  |  | 66 KV Kishangarh 1X10/12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | [5 empty] | 140 | 17.03
89 | 118/WZ/2022-23 Annexure-C | WZ | BTI |  | 55 |  | 66 KV Nangla Jorkian 1x10/12.5 MVA, 66/11 KV | Augmentation of 12.5 MVA 66/11 KV PTF with 20 MVA 66/11 KV. | 157.03 | 157.03 | [5 empty] | 140 | 17.03
90 | 119/WZ/2022-23 Annexure-C | WZ | FDK |  | 21 |  | 66 KV Chouganwan 1x20 MVA, 66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | [5 empty] | 180 | 23.61
91 | 120/WZ/2022-23 Annexure-C | WZ | MKT |  |  |  | 66 KV Chak shere wala 1x12.5 MVA, 66/11 KV | Addl.12.5 MVA, 66/11kV | 203.61 | 203.61 | [5 empty] | 180 | 23.61
92 | 121/WZ/2022-23 Annexure-C | WZ | BTI |  | 29 |  | 66 kV KAMALU SWAICH 1x20 MVA, 66/11 KV | Additional 1x 12.5 MVA 66/11 KV PTF | 203.61 | 203.61 | [5 empty] | 180 | 23.61
93 | 122/WZ/2022-23 Annexure-C | WZ | BTI |  |  |  | 1.) LILO arrangement at 66KV S/Stns. Pakho-Kalana a)66 KV line from 66 KV S/S Tapa to 66 KV S/S Joga Ralla, T-off point Pakho Kalan. (Existing line Tapa toT-off point Pakho Kalan 11Km/RP/ 0.15 sq”, Joga Ralla toT-off point Pakho Kalan14Km/0.2”/SC on DC and T-off point to 66 KV S/S Pakho-Kalan 1Km/ 0.2 Sq”/ SC on DC b) 66 KV Line Bays Pakho Kalan2. LILO arrangement at 66KV S/Stns. Kotli-Kalan a )66 KV line from 220 KV S/S Mansa to 220 KV S/S Maur T-off 66 KV S/S Kotli-Kalan/4 Km /0.2 sq”/SC on DC b) 66 KV Line Bays | a) Stringing of 2nd ckt. 1Km/0.2 Sq”/SC on DC link from T-off point to 66 KV S/S Pakho-Kalan on existing DC towers for making LILO arrangement at 66 KV S/S Pakho-Kalan. b) 1 No. Bay at 66 KV S/S Pakho-Kalan. a) Stringing of 2nd ckt. 4Km/0.2 Sq”/SC on DC link from T-off point to 66 KV S/S Kotli-Kalan on existing DC towers for making LILO arrangement at 66 KV S/S Kotli-Kalan. b) 1 No. Bay at 66 KV S/S Kotli-Kalan. | 9.42 29.00 37.68 29.00 | 105.1 | [5 empty] | 85 | 20.1
94 | 123/WZ/2022-23 Annexure-C | WZ | BTI |  |  |  | a) New link between 66 KV S/S Kulrian & 66 KV Bareta b) 66KV Bays a) 66KV Chak Ali Sher to 66 KV Kulrian/ 7.5KM/ 0.2sq" /SC on DC b) 66 KV bays | a) 7.9KM/0.2 sq inch/ SC on DC b) 2 no. (One at 66 KV S/S Kulrian and one at 66 KV S/S bareta a) Stringing of second 7.5KM/ 0.2sq"/ SC on DC ciruit on existing DC towers 2 no. (one at 66 KV S/S Kulrian and one at 66 KV S/S Chak Ali Sher) | 213 58.00 70.65 58.00 | 399.65 | [5 empty] | 150 | 249.65
95 | 124/WZ/2022-23 Annexure-C | WZ | BTI |  |  |  | Stringing of 2nd circuit from 220 kV Maur to 66KV Ghaso Khana. | a) Stringing of second circuit of 66 kV line from 220 kV Maur to 66 kV Ghaso Khana 8KM (approx.)./0.2 sq" Point A to D as shown in map on existing DC towers. b) 1 no. Controlling Bay at 66 kV S/S Ghaso Khana. c) To replace 08 no. DC on DC towers with multi circuit towers from point B to C as shown in map. d) 1 no. Controlling Bay at 220 kV S/S Maur to be planned by PSTCL. | 75.36 29.00 124.3 | 228.66 | [5 empty] | 150 | 78.66
96 | 126/WZ/2022-23 Annexure-C | WZ | BTI |  |  |  | 66KV Dhalewa to Borawal line 5Km/ 0.15sq"/ SC on SC/ tower | Replacement/Augmentations of existing conductor of 66KV line from 66KV Dhalewa to Borawal 5Km/ 0.15sq"/ SC on SC/ towers with 5Km/ 0.2sq"/ SC on DC/ towers. | 134.8 -15.10 | 119.7 | [5 empty] | 80 | 39.7
97 | 127/WZ/2022-23 Annexure-C | WZ | FZR |  |  | 45 | 66KV S/S Raoke Hithar, 1x12.5 MVA 66/11 KV | Augmentation of P/T/F T-1, 12.5MVA with 20MVA | 157.03 | 157.03 | [5 empty] | 140 | 17.03
98 | 128/WZ/2022-23 Annexure-C | WZ | FDK |  |  | 25 | 66KV S/S Kot Isse Khan, 2x20 MVA PTF | Augmentation of P/T/F T-1, 20MVA with 31.5MVA | 199.77 | 199.77 | [5 empty] | 170 | 29.77
99 | 129/WZ/2022-23 Annexure-C | WZ | FDK |  |  |  | 66KV S/S Daudhar, 2x12.5 MVA PTF | Augmentation of P/T/F T-2, 12.5 with 20 MVA | 157.03 | 157.03 | [5 empty] | 140 | 17.03
100 | 130/WZ/2022-23 Annexure-C | WZ | FDK |  |  |  | 66KV S/S Dala, 1x12.5 MVA + 1x20 MVA | Augmentation of P/T/F T-1, 12.5MVA with 20MVA | 157.03 | 157.03 | [5 empty] | 140 | 17.03
101 | 131/WZ/2022-23 Annexure-C | WZ | BTI |  |  |  | 220/66 KV Transformer at GHTP, Lehra Mohabit. T-1=160 MVA T-2= 160 MVA | (i) Additional P/T/F 100MVA(220/66) alongwith modification in the existing substation system at 220 KV GHTP. (ii) Construction of 220KV Bay. (iii) Construction of 66KV Bay. (iv)Shifting of 66KV capacitor bank. | 846.99 116.34 29.00 | 992.33 | [5 empty] | 500 | 492.33
102 | Not Planned | WZ |  |  |  |  | 66KV Malout | Addl. 20 MVA 66/11 T/f | 285.93 | 285.93 | [5 empty] | 85 | 200.93
[13 empty] | 280.76 | 8804.046 | 8035.134 | 8816.77 | 4961.2
|  |  |  | 31 | 20 | 4

## SZ
SOUTH ZONE | [14 empty] | Annexure-II
Sr.no | TWL sr.no. 2022-23 | Zone | Circle | MYT 2020-21 | MT 2021-22 | MT 2022-23 | Name of Work | Scope of Work | Estt. Cost (in lacs) | Total Cost | Status | Year | Remarks | Expenditure upto 31.03.2022 (in lacs) | Expenditure in Year 2022-23 (in lacs) | Expenditure in Year 2023-24 (in lacs) | Expenditure in Year 2024-25 (in lacs) | Expenditure in Year 2025-26 (in lacs)
1 | 6/SZ/2022-23 Annexure-A | SZ | Ropar | 140 |  |  | a) 66 KV HRP line from 220 KV Grid Ghulal -66 KV Khamano / Ghungrali (23 KM / 0.1 sq" conductor size) b) one no. 66 KV bay at 220 KV S/Stn Ghulal for firm use c) one No. 66 KV bay at 220 KV S/S Ghulal for PSPCL use. | a) Replacement of existing appox. 4 KM HRP line with 66 KV multi ckt. towers (upto common point for firm and PSPCL) and stringing of one ckt. for firm with 0.15 sq" conductor and 2nd ckt. for PSPCL for 66 KV S/S Khamano / Ghungrali with 0.2 sq" conductor. b) to be provided by PSTCL c) Stringing of third ckt . from 132 KV Ghulal upto common point appox. 4 km and beyond it 10 KM / 0.2 sq" DC on DC from common point as per 'a' upto the T-off point for 66 KV S/S Kotla Shamspur to be provided by PSTCL | 392.76 -12.08 37.68 363.9 | 782.26 | a) bays issue at 220 /132 kv Ghulal. c) Tower line defects clearence in progress by contractor. | 2022-23 Paddy -2023 |  |  | 548 | 234.26
2 | 8/SZ/2022-23 Annexure-A | SZ | Ropar |  |  |  | 220 KV Ghulal-Khamano with T-off for Ghungrali | Augmentation of remaining existing ACSR 9 km with 0.2 sq." by replacement of HRP line with SC on DC towers 66 KV line | 242.64 -27.18 | 215.46 | work held up due to bay issue at Ghulal S/S | 2022-23 |  |  | 150.822 | 64.638
3 | 10/SZ/2022-23 Annexure-A | SZ | Mohali | 3 |  |  | a) 66 KV S/Stn Baltana (New) b) T-off of 66 KV Line from 66 KV S/Stn Mubarikpur to 66 KV S/Stn Dhakoli for new 66 KV S/Stn Baltana c) Cost of Land | 2x20 MVA, 66/11 KV b) (i) 6.5 Km/0.2 sq” SC on DC ii) 200 ckt mtr (Single Ckt) 240 mm2 U/G cable c) Cost of Land | 571.86 175.24 50.28 115 | 912.38 | PTF 20 MVA T-1 S. No. 1302 / 180 Make Atlanta YOM 2019 Charged on 16.07.22 ( PTF T-2 and their Panels are pending . Also Capacitor Banks Pending. | 2022-23 |  | 167.22 | 400 | 150 | 195.16
4 | 17/SZ/2022-23 Annexure-A | SZ | Patiala |  |  |  | Shifting / Raising of height of 66 KV Rajpura Saraibanjara Line at the crossing NH-1 of Amritsar Ludhiana – Delhi section | 0.160 km / 0.2 sq " DC on Multi-Ckt Towers to replace existing DC Towers of Lower Height | 15.71 -0.48 | 15.23 | Work in progress. Tower Material Required. | 2022-23 |  |  | 15.23
5 | 18/SZ/2022-23 Annexure-A | SZ | Ropar | 142 |  |  | a) 66 KV Line from 220 KV S/Stn Ghulal to 66 KV S/Stn Machhiwara 0.2 sq” / 9.299 km, SC on DC) b) 66 KV Line Bays | a) Stringing of 2nd Circuit (0.2 sq” / 9.299 km) on DC Towers b) (i) 1 No. 66 KV Line Bay (with 66 KV Circuit Breakers) at 220 KV Grid Ghulal (ii) 1 No. 66 KV Line Bay (with 66 KV Circuit Breakers) at 66 KV Grid Machhiwara | 87.6 29 | 116.6 | bays issue at Ghulal S/S. | PSTCL Pending |  |  |  | 116.6
6 | 19/SZ/2022-23 Annexure-A | SZ | Sangrur | 143 |  |  | a) 66 KV line from 66 KV S/S Kapial to 66 KV S/S Bhattiwal b) 66 KV bay at 66 KV S/Stn Kapial. c) 66 KV line bay at 66 KV S/Stn Bhattiwal | 3 KM / 0.2 sq" cond. SC on DC towers. 1 No. 66 KV bay. 1 No. 66 KV bay. | 80.9 29 29 | 138.9 | Work in Progress. | 2022-23 |  | 13.76 | 125.14
7 | 20/SZ/2022-23 Annexure-A | SZ | Sangrur |  |  |  | a) 66KV Ghanaur-Dharamgarh line. b) 66 KV line Bays (i) 1 No. at 66 KV S/Stn Ghanour (ii) 1 No. at 66 KV S/Stn Dharamgarh | 7 KM SC/DC line 0.2Sq"ACSR. (i) 1 No. (ii) 1 No. | 188.7 58 | 246.7 | Work in progress. | 2023-24 |  |  | 75 | 100 | 71.7
8 | 21/SZ/2022-23 Annexure-A | SZ | Sangrur | 145 |  |  | a) 66KV Loha Khera-Longowal line. b) 66 KV line Bays (i) 1 No. at 66 KV S/Stn Loha Khera (ii) 1 No. at 66 KV S/Stn Longowal | 8.6 KM SC/DC line 0.2Sq"ACSR. (i) 1 No. (ii) 1 No. | 231.86 58 | 289.86 | Work in Progress. | Paddy-2023 |  |  | 203 | 86.86
9 | 22/SZ/2022-23 Annexure-A | SZ | Sangrur |  |  |  | a) 66KV Lehragaga to Khandebad line T-off for Balran. b) 66 KV line Bays (i) 1 No. 66 KV bay at 66 KV Balran breaker controlled bay. ii) Conversion of 1 no. 66 KV LE controlled bay to 66 KV breaker controlled bay at 66 KV Khandebad | 8.6 KM SC on DC tower line 0.2 Sq"ACSR. 1 No. 1 no. | 231.86 29 22.1 | 282.96 | Work in Progress. | 2022-23 |  | 36.3 | 146.66 | 100
10 | 23/SZ/2022-23 Annexure-A | SZ | Patiala | 146 |  |  | Conversion of existing T-Off (SC on SC / (SC on SC / 0.2 sq" / 2 km) from '66 KV Line from 220 KV Grid Devigarh to 66 KV Grid Bahadurgarh' to 66 KV S/Stn Bhunerheri into 'LILO system at 66 KV S/Stn Bhunerheri ' | a) 2 KM / 0.2 sq'' DC on DC towers (being LILO arrangement) b) One No. 66 KV Line Bay at 66 KV S/Stn Bhunerheri | 72.8 29 | 101.8 | Work in progress | 2022-23 |  | 31.53 | 70.27
11 | 24/SZ/2022-23 Annexure-A | SZ | Patiala | 147 |  |  | Conversion of existing T-Off (SC on SC / 0.2 sq" / 6 km) from 66 KV Line from 220 KV Grid Devigarh to 220 KV Grid Bhateri' to 66 KV S/Stn Bhankar into 'LILO system at 66 KV S/Stn 'Bhankar | a) 6 KM / 0.2 sq'' DC on DC towers (being LILO arrangement) b) One No. 66 KV Line Bay at 66 KV S/Stn Bhankar | 218.3 29 | 247.3 | Work in Progress. | 2023-24 |  | 57.14 | 57 | 100 | 33.16
12 | 26/SZ/2022-23 Annexure-A | SZ | Ropar |  | 75 |  | 132 KV Ropar-Pukhrali line 0.1 sq" / 12 KM; HRP | Augmentation of existing ACSR 12 km with 0.2 sq." by replacement of HRP line with SC on DC towers 66 KV line | 323.5 -36.24 | 287.26 | route plan under observation, | 2023-24 |  |  | 87 | 150 | 50.26
13 | 27/SZ/2022-23 Annexure-A | SZ | Patiala |  |  |  | a) 66 KV S/Stn Roshanpur (New)(with 1 No. 66 KV Line Bay with Isolators only) at new 66 KV S/S Roshanpur b) T-off of existing 66 KV line from 220 KV S/S Devigarh to 66 KV S/Stn Rohar Jagir for new 66 KV S/Stn Roshanpur c (i) 66 KV Line from 220 KV S/Stn Devigarh to 66 KV S/Stn Rohar Jagir (0.15 sq" / SC on SC / 6.78 km from 'T-Off Point of 66 KV Grid Maghar Sahib' upto 66 KV Grid Rohar Jagir) ii) Provision of 2 no. 66 line bays (with 66 KV ckt. breaker) at 66 KV grid S/S Rohar Jagir | a)1 x 12.5 MVA, 66/11 KV b) 8.5 KM/ 0.2 sq" ;SC on DC Towers. c) 0.2 sq" / 6.78 km / DC on DC to replace existing linefrom T-off point of 66 KV grid Maghar Sahib upto 66 KV grid Rohar Jagir. a) Conversion of existing isolator controlled arrangement into 1 breaker at 66 KV S/S Rohar Jagir for incoming 66 KV ckt. from 220 KV grid S/S Devigarh. b) 1 no. addl 66 KV line bay (with ckt. breaker) at 66 KV S/S Rohar Jagir for the proposed 2nd incoming 66 KV ckt. | 219.9 229.2 246.7 -20.47 22.1 29 | 726.43 | b) Line Work completed in 02/2020. c) Line Work completed in 12/2020. | 2022-23 |  | 21.69 | 400 | 200 | 104.74
14 | 29/SZ/2022-23 Annexure-A | SZ | Ropar | 154 |  |  | New 66 KV Link between 66 KV Grid Nurpur Bedi to 66 KV Grid Bhaddi | a) 16 km / 0.2 sq" / SC on DC b) 1 No. I/C 66 KV Line Bay (with 66 KV Circuit Breaker) at 66 KV Grid Nurpur Bedi and 1 No. O/G 66 KV Line bay (with 66 KV Circuit Breaker) at 66 KV Grid Bhaddi. | 431.4 58 | 489.4 | work not started yet, work order for surveying has been held up for approval due to rate issue because of hilly areas | 2024-25 |  |  |  | 147 | 342.4
15 | 30/SZ/2022-23 Annexure-A | SZ | Ropar |  |  |  | 66 KV line from 132 KV Grid Anandpur Sahib to 66 KV Grid Nurpur Bedi (0.1 sq” / 15 km, SC on RP) | a) Stringing of 2nd circuit (15 km / 0.2 sq") on already proposed DC Towers. (These DC towers are being erected by office of CE / TS, PSPCL against the planning at Sr. No. 20/SZ/2018-19/ Annex-A (Works in Progress) of TWL 2018-19 b) 1 No. O/G 66 KV Line Bay (at 132 KV Grid Anandpur Sahib) To be planned / executed by PSTCL c) 1 No. 66 KV Line Bay at 66 KV Grid Nurpur Bedi | 141 29 | 170 | Line temporarily charged on 12/07/2019. 220KV raising completed. 2D-60+9 mtr tower stubbing/erection pending.TL 13 Twisted tower erection and sag work completed | Paddy-2023 |  |  | 100 | 70
16 | 31/SZ/2022-23 Annexure-A | SZ | Sangrur |  | 73 |  | a) Herokalan- Cheema b) 66 KV line Bays i) 1 No. at 66 KV S/Stn Herokalan (ii) 1 No. at 66 KV S/Stn Cheema | 5KM / 0.2 Sq" ACSR (i) 1 No. (ii) 1 No. | 135 29 29 | 193 | Work in Progress. | Paddy-2023 |  |  | 136 | 57
17 | 32/SZ/2022-23 Annexure-A | SZ | Patiala |  |  |  | 66 KV Passiana – Sanaur Line 0.125 sq" / HRP / 1 km (from 220 KV S/Stn Passiana upto TL No. 210) 1 No. 66 KV Line Bay at 220 KV S/Stn Passiana | a) New 66 KV SC on DC / 0.2 sq" / 1 km line (from 220 KV S/Stn Passiana upto TL No. 210) + 7.5 km / 0.2 sq" / SC on DC to replace the existing 66 KV line (from TL No. 210 upto TL No. 235 + from TL No. 243 to TL No. 251) b) 2 km / 0.2 sq"(SC on Multi- Circuit Towers with DC configuration) to replace the existing 66 KV line in wild life sanctuary from TL-235 to TL-243) To be planned / executed by PSTCL. | 26.96 202.2 -22.7 | 206.46 | Work in Progress. Only one no 2D2 tower pending for stubbing and erection, will be completed soon | 2022-23 |  |  | 125 | 81.46
18 | 33/SZ/2022-23 Annexure-A | SZ | Ropar |  |  |  | a) 66 KV S/Stn Gehlewal (New) [including 1 No. 66 KV Line Bay (with isolators only) at new 66 KV S/Stn Gehlewal] b) T-off from existing 66 KV Kohara-Chaunta Line. | 1 x 12.5 MVA, 66/11 KV 2.45 km / 0.2 sq" / SC on DC Towers. | 219.9 66.05 | 285.95 | 66 KV line stands completed since 22/11/2021. Line couldn't be charged due to non-availability of bay. Grid work in progress | 2022-23 |  | 217.69 | 68.26
19 | 41/SZ/2022-23 Annexure-A | SZ | Patiala |  |  |  | 66 KV Line from 220 KV Grid Rajpura to 66 KV Grid Naushera 22 km / 0.2 sq" / 0.1 sq" (HRP / SC on DC) | Augmentation of existing ACSR 22 km with 0.2 sq." by replacement of HRP line with SC on DC towers 66 KV line | 593.1 -66.44 | 526.66 | Work in progress | Paddy-2023 |  |  | 250 | 276.66
20 | 48/SZ/2022-23 Annexure-B | SZ | Barnala |  | 141 |  | 66 KV Line from Dhuri to 66KV S/Stn.Banboura | Replacement of existing 66 KV Line Dhuri-Malerkotla old towery line from 66 KV S/Stn Dhuri to T-Off point Bhanbhora (0.1 sq" / 11 km) and T-Off Point to 66 KV S/Stn Bhanbhora S/C on S/C (0.15 sq" / 5 km) to be replaced with S/C on D/C with 0.2 sq"conductor | 431.4 -48.32 | 383.08 | Work alloted | Paddy-2023 |  |  | 200 | 183.08
21 | 49/SZ/2022-23 Annexure-B | SZ | Patiala |  |  |  | a) 66 KV Line from 220KV S/S Passiana to 66KV S/Stn Patiala 0.1Sq" on HRP/SC Towers | Replacment of portion (5Km) of 66KV Line with 0.2Sq" ACSR from T.L. No. 251 (Sanour-Passiana)to T.L. No. 266 (66KV S/S Patiala of existing0.1 sq" SC on HRP/SC Towers | 135 -15.1 | 119.9 | Work has been stopped by PSTCL as there is proposal of PSTCL to convert 66 KV Old Patiala S/S into 220 KV G/S/S | 2025-26 |  |  |  |  | 36 | 83.9
22 | 50/SZ/2022-23 Annexure-B | SZ | Patiala | 38 |  |  | 66 KV Line from 66 KV Grid Focal Point Rajpura to 66 KV Grid Naushera | a) Underground Cable 240 sq. mm 450 ckt.mtr. (Point A to B) b) Stringing / sagging of second circuit 0.2 sq" 9.4 Km on existing DC Towers (Point B to C) c) 66 KV line Bay at 66 KV S/Stn Focal Point Rajpura (with 66 KV Circuit Breaker) (A-B-C) (nomenclature of points A , B and C as specified in the vetted sketch sent by SE / TL Circle, PSPCL, Patiala vide their office memo no. 2973 / TLC-5 dated 12.07.2019 to CE / TS, PSPCL) | 113.1 88.55 29 | 230.65 | Work is not started yet as Work Order of U/G Cable is pending. | Paddy-2023 |  |  | 162 | 68.65
23 | 51/SZ/2022-23 Annexure-B | SZ | Ropar |  |  | 68 | a) Kizrabad- Majra b) 66 KV line Bays (i) 1 No. at 66 KV S/Stn Kizrabad (ii) 1 No. at 66 KV S/Stn Majra | 8 KM / 0.2 Sq" ACSR (i) 1 No. (ii) 1 No. | 215.7 58 | 273.7 |  | 2023-24 |  |  | 83 | 190.7
24 | 52/SZ/2022-23 Annexure-B | SZ | Ropar |  |  | 69 | a) Kizrabad- Purkhali b) 66 KV line Bays (i) 1 No. at 66 KV S/Stn Kizrabad (ii) 1 No. at 66 KV S/Stn Purkhali | a) 6.941 Km 0.2sq” SC on DC towers b) 66 KV line Bays (i) 1 No. at 66 KV S/Stn Kizrabad (ii) 1 No. at 66 KV S/Stn Purkhali | 187.12 29 29 | 240.12 |  | 2024-25 |  |  |  | 169 | 71.12
25 | 53/SZ/2022-23 Annexure-B | SZ | Ropar |  |  | 71 | a) Behlolpur-Haidon Bet b) 66 KV line Bays (i) 1 No. at 66 KV S/Stn Behlolpur (ii) 1 No. at 66 KV S/Stn Haidon Bet | 8 KM / 0.2 Sq" ACSR/SC on DC (i) 1 No. (ii) 1 No. | 215.7 29 29 | 273.7 |  | 2022-23 |  |  | 100 | 173.7
26 | 55/SZ/2022-23 Annexure-B | SZ | Patiala |  |  |  | 66 Kv line from 66 KV grid S/S Bahadargarh to 66 KV grid S/S Urban Estate, Patiala (0.2sq" DC on DC from 66 KV S/S Bhadargarh upto tower no.3 + 0.1sq" SC on SC 4.35Km from tower no. 3 upto 66 KV grid S/S Urban Estate, Patiala). | 4.35 Km / 0.2sq" / SC on DC to replace the existing 66 KV line (from tower no. 3 upto 66 KV grid S/S Urban Estate , Patiala) | 117.28 -13.137 | 104.143 | Route Survey is in progress. | 2023-24 |  |  | 32 | 72.143
27 | 56/SZ/2022-23 Annexure-B | SZ | Mohali |  |  |  | LILO arrangement of 66KV ckt from 220 KV S/S Phase-7 (Mohali-1) to 66 KV S/S Phase-9 Mohali at 66 KV S/S Sector-71 and 66 KV S/S Sector-68 Mohali. | 1) (a) LILO arrangment of already existing 240 mm2 cable at 66 kv s/stn Sector-71 Mohali (Point B as per attached sketch) double ckt of length approx. 60 mtr including loop and raiser b) 66 kv bays 2 no. at 66 kv S/Stn Sector 71 Mohali 2) (a) LIlO arrangment of already existing overhead line at 66 kv s/stn Sector-68 Mohali(Point C as per attached sketch) Dc on Dc length of approx 54 mtr required 2 no. D-60 towers. b) 66 kv bays 2 nos. at 66 kv S/Stn Sector 68 Mohali . 3) Erection of 1 no. tower near Gurudwara Sahib phase-5 (point A as per attached sketch) to maintain the ground clearance. | 15.084 58 7.5 58 3.5 | 142.084 |  | 2022-12-01 |  |  | 99.4588 | 42.6252
28 | 57/SZ/2022-23 Annexure-B | SZ | Sangrur |  |  |  | a) New 66KV line from 220 KV S/Stn Banga to 66 KV S/Stn Banarsi b) 66 KV Bays | New 66 KV line from 220 KV S/S Bangan to Banarsi / 16 Km /0.2sq” ACSR/ DC on DC 2 no. 66 KV bays at 66 KV S/S Banarsi. 2 no. 66 KV bays at 220 KV S/S Banga (To be executed by PSTCL) One no. 66 KV isolator controlled bay for 66 KV Sailwala at 220 KV S/S Banga to be converted into breaker controlled by (To be executed by PSTCL, planned at Sr. no. 67/SZ/Annex-B/2021- 22). | 582.24 58 | 640.24 | Work in progress | 2022-23 |  | 182.77 | 457.47
29 | 58/SZ/2022-23 Annexture-B | SZ | Sangrur |  |  |  | 66 KV Line from 220 KV Bangan to 66 KV Bhutal | New 12 KM/0.2sq''/SC on DC line by replacement of existing 0.15sq'' SC on SC line | 323.52 -36.24 | 287.28 | Work is under Progress. | 2023.24 |  |  | 87 | 100 | 100.28
30 | 59/SZ/2022-23 Annexure-B | SZ | Sangrur |  |  |  | a) 66 KV Line from 220 KV S/S Dhanoula to 66 KV Badrukhan b) 66 KV Bays | a) Stringing 2nd circuit 24KM /0.2 Sq " on existing Tower line from 220 KV Dhanoula to 66 KV Badrukhan. b) 66 Line bays 1 no at 66 KV Badrukhan 1 no at 220 KV Dhanoula (To be planned by PSTCL) | 226.08 29 | 255.08 | Work alloted | Paddy-2023 |  |  | 150 | 105.08
31 | 60/SZ/2022-23 Annexture-B | SZ | Barnala |  |  |  | 66 KV line from 66KV S/S Pakhoke to Cheema (existing 2.15Km/ 0.125 sq" HRP line from point P to Q as per sketch received) | New 2.15Km/ 0.2 Sq"/SC on DC line by replacement of 2.15 KM 0.125 sq" HRP line on the same ROW (from Pakhoke up to T-5) | 57.964 -6.49 | 51.474 |  | 2023-24 |  |  | 16 | 35.474
32 | 61/SZ/2022-23 Annexure-B | SZ | Mohali |  |  |  | 66 KV S/Stn Phase 9 Mohali ( 2 x 20 MVA, 66/11 KV) | Addl 20 MVA, 66/11 KV | 285.93 | 285.93 |  | 2022-12-01 |  |  | 285.93
33 | 62/SZ/2022-23 Annexure-B | SZ | Ropar |  |  |  | a) 66KV S/S Gaggo (NEW) (Including 1 no complete 66KV line bay) b) Proposed new 1.7 km / 0.2 sq"/ SC on DC towers line T-off from existing 66KV Line from 132 KV Ropar to 66KV Behlolpur 0.1sq’’/HRP 66KV Line from 132 KV Ropar to 66 KV Behlolpur up to proposed site of Gaggo S/Stn. | a)6.3 / 8 MVA or 8/10MVA, 66/11 KV (as per availability) b) New 1.7 km/ 0.2 sq'' SC on DC Towers Line. | 219.92 45.832 | 265.752 | Tender under process | 2023-24 |  |  | 80 | 80 | 105.752
34 | 63/SZ/2022-23 Annexure-B | SZ | Ropar |  |  |  | a) 66 KV S/S Lakhomajra (NEW) (Including 1 no. complete 66 KV line bay) b) Proposed new 2.5 km / 0.2 sq"/ SC on DC towers line T-off from existing 66KV Line from existing 66 KV line from 220 KV Bhateri to Rajpura (66 KV idle line) 0.1sq’’/ 0.2sq” tower Line up to proposed site of Lakhomajra S/Stn. | 8/10MVA or 10/12.5 MVA, 66/11 KV (as per availability) New 2.5 km/ 0.2 sq'' SC on DC Towers Line. | 219.92 67.4 | 287.32 | Layout plan yet to be issued. | Paddy-2023 |  |  | 202 | 85.32
35 | 64/SZ/2022-23 Annexture-B | SZ | Ropar |  |  |  | 66KV S/S Sainsowal Kalan (NEW) (Including 1 no complete 66KV line bay) Proposed new 7.8 km / 0.2 sq"/ SC on DC towers line T-off from existing 66KV Line from 66 KV Machhiwara to 66KV Hedon 0.2sq’’/SC on DC up to proposed site of Sainsowal Kalan S/Stn. | 6.3 / 8 MVA or 8/10MVA, 66/11 KV (as per availability New 7.8 km/ 0.2 sq'' SC on DC Towers Line. | 219.52 210.288 | 429.808 | Land yet to be received | 2023-24 |  |  | 100 | 150 | 179.808
36 | 65/SZ/2022-23 Annexure-'B | SZ | Patiala |  |  |  | a) 66KV S/S BEHLOLPUR (NEW) (Including 1 no. complete 66 KV line bay) b) Existing Multi circuit tower from 220KV Damanheri (Rajpura) point A to C (up to T- off for Sarai banjara) of approximately length of 10Km (as per sketch). c) HRP line approximately 4.5km from T-off for Sarai banjara to Sirhind. d) Proposed new 4 km/0.2 sq"/ SC on DC towers line T-off from existing 220KV Damanheri (Rajpura) to Sirhind Line up to proposed site of Behlolpur S/Stn e) 66KV bay at 220kv S/S Damanheri (Rajpura) | a) 8/10MVA or 10/12.5 MVA, 66/11 KV (as per availability) b) Stringing of circuit with 0.2sq” ACSR conductor on already existing Multi circuit tower SC on DC line from point A to C (up to T- off for Sarai banjara) of approximately length of 10Km (as per sketch). c) Replacement of HRP line with DC on DC line of 0.2sq”/ACSR conductor of approximately 4.5km ( from T-off for Sarai banjara to proposed T-off for Behlolpur). d) New 4km/ 0.2 sq'' SC on DC Towers Line for proposed sub station Behlolpur. Proposed 1nos. 66KV bay at 220KV S/S Damanheri (Rajpura) | 219.52 94.2 163.755 -13.59 107.84 Shall be planned by PSTCL | 571.725 | Land yet to be received | 2024-25 |  |  |  | 172 | 399.725
37 | 67/SZ/2022-23 Annexure-B | SZ | Barnala | 108 |  |  | 66 KV S/Stn Pakhon ( 1 x 20 MVA + 1x 12.5 MVA, 66/11 KV) | 20 MVA to repl 12.5 MVA, 66/11 KV T/F | 157.03 | 157.03 |  | Paddy-2023 |  |  | 110 | 47.03
38 | 68/SZ/2022-23 Annexure-B | SZ | Barnala |  |  |  | a) 66 KV S/S Dhaner (NEW) (Including 1 nos. 66KV line bay ) b) Proposed new 9.6km approx. / 0.2sq"/ SC on DC towers line from 220KV S/S Mehal Kalan up to proposed site of Dhaner S/Stn. | i) 1x10/12.5 MVA, 66/11 KV P/T/F ii ) New 9.6 km approx./ 0.2sq'' SC on DC Towers Line. iii) 66 KV bay at 220 KV S/S Mehal Kalan (To be executed by PSTCL) | 219.92 258.81 | 478.73 | Land yet to be received | 2023-24 |  |  | 144 | 334.73
39 | 69/SZ/2022-23 Annexure-B | SZ | Barnala |  |  |  | a) 66 KV S/S Pharwahi (NEW) (Including 1 nos. 66KV line bay) b) Proposed new 7km (Approx.) / 0.2sq"/ SC on DC towers line T-off from ckt no 1 of existing 12Km/0.2sq’’/66KV DC on DC tower Line from 220KV Dhanoula--- Handiaya, up to proposed site of Pharwahi S/Stn. | i) 1x10/12.5 MVA, 66/11 KV P/T/F ii) New 7 km (Approx.)/ 0.2 sq'' SC on DC Towers Line. | 219.92 188.72 | 408.64 | Land yet to be received | 2023-24 |  |  | 123 | 285.64
40 | 70/SZ/2022-23 Annexure-B | SZ | Ropar |  | 114 |  | 66KV S/S Purkhali 2x12.5 MVA, 66/11 KV | 20 MVA 66/11KV to rep. 12.5 MVA 66/11KV | 157.03 | 157.03 |  | Paddy-2023 |  |  | 110 | 47.03
41 | 71/SZ/2022-23 Annexure-B | SZ | Sangrur | 116 |  |  | 66 KV S/Stn Sekhuwas (1x 20 MVA, 66/11 KV) | Addl 20 MVA, 66/11 KV T/F | 285.93 | 285.93 |  | Paddy-2023 |  |  | 201 | 84.93
42 | 72/SZ/2022-23 Annexure-B | SZ | ROPAR |  |  |  | Additional 20 MVA 66/11 KV P/T/F at 66 KV S/S Gilco valley (1x20MVA) | Additional 20 MVA 66/11 KV P/T/F at 66 KV S/S Gilco valley | 285.93 | 285.93 |  | Paddy-2023 |  |  | 201 | 84.93
43 | 73/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | Augumentation of 20 MVA 66/11 KV P/T/F-2 with 31.5 MVA 66/11 KV P/T/F at 66 KV S/S Dirba (2x20MVA) | Augumentation of 20 MVA 66/11 KV P/T/F-2 with 31.5 MVA 66/11 KV P/T/F at 66 KV S/S Dirba | 199.77 | 199.77 |  | 2023-24 |  |  | 60 | 139.77
44 | 74/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | Augumentation of 20 MVA 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV P/T/F at 66 KV S/S Ghagga (2x20MVA) | Augumentation of 20 MVA 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV P/T/F at 66 KV S/S Ghagga | 199.77 | 199.77 |  | 2023-24 |  |  | 60 | 139.77
45 | 75/SZ/2022-23 Annexure-B | SZ | MOHALI |  |  |  | Providing 2nd source of 66KV supply to 66 KV Ramgarh Bhuda | a) T-OFF FROM 220 KV S/S BANUR TO 66 KV MUBARIKPUR LINE FROM POINT A TO C with 240mm2 Copper cable(Single Ckt) of approx length of 1200 Ckt meter from point A to Point B ( as per attached sketch) b) SC on DC line of 0.2" ACSR on monopoles of approx length of 2550 meter from point B to C. ( as per attached sketch) c) 1 No 66 KV Bay at 66 KV Ramgarh Bhuda | 301.68 573.75 29 | 904.43 |  | 2023-24 |  |  | 272 | 632.43
46 | 76/SZ/2022-23 Annexure-B | SZ | MOHALI |  |  |  | Augumentation of 20 MVA 66/11 KV P/T/F-2 with 31.5 MVA 66/11 KV P/T/F at 66 KV S/S Mubarkpur | Augumentation of 20 MVA 66/11 KV P/T/F-2 with 31.5MVA 66/11 KV P/T/F at 66 KV S/S Mubarkpur | 199.77 | 199.77 | T/F installed.only matching equipment pending | 2022-23 | Completed |  | 199.77
47 | 77/SZ/2022-23 Annexure-B | SZ | PATIALA |  |  |  | Additional 12.5 MVA 66/11 KV P/T/F at 66 KV S/S Alowal (1x20MVA) | Additional 12.5 MVA 66/11 KV P/T/F at 66 KV S/S Alowal | 285.93 | 285.93 |  | Paddy-23 |  |  | 201 | 84.93
48 | 78/SZ/2022-23 Annexure-B | SZ | MOHALI |  |  |  | Augumentation of T-1 12.5 MVA 66/11 KV P/T/F with 20 MVA, 66/11 KV P/T/F at 66 KV S/S Mulanpur Mulanpur (1x20+1x12.5) MVA | Augumentation of T-1 12.5 MVA 66/11 KV P/T/F with 20 MVA, 66/11 KV P/T/F at 66 KV S/S Mulanpur | 157.03 | 157.03 |  | Paddy-2023 |  |  | 110 | 47.03
49 | 79/SZ/2022-23 Annexure-B | SZ | BARNALA |  |  |  | 66 KV Line from 220 KV S/S Handiaya to Barnala (SC/DC 0.2sq" CCC = 380 Amp) | a) Stringing of 2nd ckt DC/DC 0.2sq", 7 Km b) One 66 KV Bay at 220 KV Handiaya c) One 66 KV Bay at 66 KV Barnala | 65.94 29 | 94.94 |  | Paddy-2023 |  |  | 29 | 65.94
50 | 80/SZ/2022-23 Annexure-B | SZ | BARNALA |  |  |  | 66 KV line from 220KV S/S Dhanoula to 66 KV Aspal Kalan (SC/DC 0.15sq" CCC = 320 Amp) | a)Stringing of 2nd ckt on existing SC/DC 0.2sq" 13 km b)One 66 KV Bay at 220 KV Dhanoula c) One 66 KV Bay at 66 KV Aspal Kalan | 350.48 29 | 379.48 |  | 2023.24 |  |  | 114 | 265.48
51 | 81/SZ/2022-23 Annexure-B | SZ | BARNALA |  |  |  | 66 KV line from 220 KV S/S Mehal Kalan to 66 KV Thulliwal (SC/DC 0.2sq" CCC = 380 Amp) | a) Stringing of 2nd ckt DC/DC 0.2sq",Mehal kalan to Thullewal approx 8 Km. b)one 66 KV Bay at 220 KV Mehal Kalan c) One 66 KV Bay at 66 KV Thuliwal | 215.68 29 | 244.68 |  | 2023.24 |  |  | 74 | 170.68
52 | 82/SZ/2022-23 Annexure-B | SZ | BARNALA |  |  |  | 66 kv line from 220 kv s/s Handiaya to 66 kv Dhoula (SC/SC 0.15sq" and 0.15 sq" on SC on DC (CCC = Tower line 320 Amp) | a) Replacement of SC on SC line of 0.15 sq" ACSR conductor with SC on DC line of 0.2 sq" ACSR Conductor of approiximate length of 7 Km from point B to C. b) Replacement of single ckt (1 no ckt) of 0.15 sq" ACSR conductor on existing DC on DC tower of 66 KV Dhoula line of approximate length of 1.6 Km from 220 KV G/S/S Handiaya up to T-off point of 66 KV Varindra Ltd S/S | 188.72 58.224 | 246.944 |  | 2023.24 |  |  | 75 | 171.944
53 | 83/SZ/2022-23 Annexure-B | SZ | PATIALA |  |  |  | Erection of 2nd ckt 66 KV LINE FROM 220 KV S/S Ablowal TO 66 KV RAKHRA (SC/DC 0.2sq" CCC = 380 Amp) | New erection of second circuit of conductor size 0.2sq" length of line 9.44KM on existing SC on DC 66 KV Ablowal-Rakhra line towers already erected. | 88.92 | 88.92 |  | 2023.24 |  |  | 27 | 61.92
54 | 84/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | 66 kv line from 220 kv s/s Kakrala to 66 KV Dyalgarh T-OFF to 66 kv grid Sihal (SC/SC 0.15sq" and 0.15sq" on one circuit on DC on DC CCC = 320Amp) | a) Replacement of 1 no Ckt of 66 KV Dayalgarh S/S of 0.15 sq" Conductor of approximately length of 1.5 KM on existing DC on DC line from 220 KV G/S/S Kakrala upto T-off point of 66 KV Kulraran with 0.2 Sq" b) Replacement of existing SC on SC line of 0.15 sq "Conductor with SC on DC line of 0.2 sq " ACSR conductor of approximately length of 12.75 Km | 54.585 343.74 | 398.325 |  | 2023.24 |  |  | 120 | 278.325
55 | 85/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | To deload 66 kv line from 66 kv s/s Sunam to 66 kv Nagra T-OFF Kaloudi line sc/dc 0.2sq" | a) 66 KV LINE FROM 220 KV S/S BBMB SANGRUR TO 66 KV grid S/S Bhawanigarh which is connceted to 220 KV Bhawanigarh (66 KV line Sunam to Nagra SC/DC 0.2sq" CCC = 380Amp) b) Stringing of 2nd ckt 0.2sq"/ 4.6 Km on SC /DC tower line for LILO arrangement at 66 KV S/S Kaloudi. To connect 66 KV S/S Nagra with 66 KV S/S Bhawanigarh by LILO at 66 KV S/S Kaloudi and 66 KV S/S Nagra connect this proposed 66 Kv ckt solid tap to already existing 66 kV ckt from 66 Kv S/S Nagra to 66 KV S/S Kaloudi. | 43.332 | 43.332 |  | 2023.24 |  |  | 13 | 30.332
56 | 86/SZ/2022-23 Annexure-B | SZ | PATIALA |  |  |  | Augmentation of T-2 12 .5 MVA, 66/11 KV P/T/F- 2 with 20 MVA at 66 KV S/S Bhamana | Augmentation of T-2 12 .5 MVA, 66/11 KV P/T/F- 2 with 20 MVA at 66 KV S/S Bhamana | 157.03 | 157.03 |  | Paddy-2023 |  |  | 110 | 47.03
57 | 87/SZ/2022-23 Annexure-B | SZ | BARNALA |  | 98 |  | Additional 12.5 MVA 66/11 KV P/T/F at 66 KV Lohatbaddi | Additional 12.5 MVA 66/11 KV P/T/F at 66 KV Lohatbaddi | 203.61 | 203.61 |  | Paddy-2023 |  |  | 143 | 60.61
58 | 88/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | 66 KV line from 66 KV S/S Bakhopir to 66 KV Bhalwan (0.2sq" / SC on DC /12Km) b) i) Stringing of 2nd ckt 0.2sq" / 2.5 Km (converting existing SC/DC into DC/DC for proposed LILO arrangement at 66 KV GEHLA ii) One no. 66 KV line bay at Gehla | a) i) Stringing of 2nd ckt 0.2sq" / 12 Km on the existing SC/DC 0.2sq", 12 Km of main line. ii) 2 no. 66 KV line bays one at 66 KV Bakhopir and one at 66 KV Bhalwan b) i)Stringing of 2nd ckt 0.2sq" / 2.5 Km (converting existing SC/DC into DC/DC for proposed LILO arrangement at 66 KV Gehla) ii) One no. 66 KV line bay at Gehla | 113.42 58 23.55 29 | 223.97 |  | Paddy-2023 |  |  | 157 | 66.97
59 | 89/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | a) 66 KV line from 220 KV S/S BBMB Sangrur to 66 KV Bhalwan (POINT A TO C 0.1sq" / HRP / SRP Line 6.5 Km + POINT C TO E 0.125sq" / SC/SC Line Point E TO F DC/DC Line with ckt. 1 FROM BBMB Sangrur TO Bhalwan with 0.2sq" ACSR & CKT 2 FROM Mangwal to Bhalwan with 0.2sq" ACSR) b) Existing point A TO C 0.1sq" HRP /SRP line, 6.5Km + point C TO E 0.125 sq" SC/SC + point E to F DC/DC | 1) Replacement of existing line from point A to B, B to C and C TO E with DC/DC 0.2sq", 13.7 Km. Mother station of 66 KV Bhalwan will be 220 KV BBMB Sangrur | 498.543 -41.374 | 457.169 |  | 2024-25 |  |  |  | 138 | 319.169
60 | 90/SZ/2022-23 Annexure-B | SZ | Ropar |  |  |  | Proposal regarding stringing of 2nd ckt of 66 KV line on SC/DC tower from 220 Kv S/S Kharar to 66 KV S/S Kurali | 1)Stringing of 2nd ckt of 66 KV line on DC tower from 220 Kv S/S Kharar to 66 KV S/S Kurali ON Existing SC/DC LINE 11.296 Km (0.2 sq") 2) 0.230 km 240 sqmm cable . 3) one bay at 66 KV Kurali | 106.4 57.822 29 | 193.222 |  | Paddy-2023 |  |  | 136 | 57.222
61 | 91/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | 66 KV line from 220 KV S/S Kaheru to 66 KV S/S Benra | a) proposed stringing of 4th ckt on mct towers of approx. length 5.2 km from 220 kv kaheru upto T-off point of 66 kv Kanjhla from point A to B as per sketch b) Replacement of existing 4.8Km SC/SC line with DC/DC line from B TO C as per sketch c) 1 no 66 KV line bay at 66 KV Benra & 220 KV Kaheru | 140.192 174.672 29 PSTCL | 343.864 |  | Paddy-2023 |  |  | 241 | 102.864
62 | 92/SZ/2022-23 Annexure-B | SZ | MOHALI |  |  |  | Additional 12.5 MVA T/F at 66 KV Haripur Kurran (Existing 1x20 MVA) | Additional 12.5 MVA T/F at 66 KV Haripur Kurran | 203.61 | 203.61 |  | Paddy-2023 |  |  | 143 | 60.61
63 | 93/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | Regarding new LILO arrangement of 66 kv S/S Sohian road Sangrur from 220 KV BBMB Sangrur to 66 KV S/S Bhawanigarh ckt-1 | i) Laying of 66 KV 240mmsq U/G cable 1.2 KM for LILO arrangement of 66 KV S/S Sohian Road Sangrur ii) One no 66 KV Bay at 66 KV S/S Sohian Road Sangrur | 301.68 29 | 330.68 |  | Paddy-2023 |  |  | 232 | 98.68
64 | 94/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | Replacement of SC/SC line with DC/DC from T-off Jogewal upto 66 kv S/S Banarsi | 1) Replacement of sc/sc line 0.15sq" acsr with dc/dc line of 0.2sq" / 5.38 km acsr from T-off point of 220 kv G/S/S Patran to 66 kv Shergarh line ( point a as per attached sketch) up to 66 kv Banarsi s/s of approximate length 5.38 km ) (on same ROW) 2) One no 66kv bay at Banarsi | 195.77 -16.24 29 | 208.53 |  | 2024-25 |  |  |  | 63 | 145.53
65 | 95/SZ/2022-23 Annexure-B | SZ | ROPAR |  |  |  | 66 KV S/S Bajroor 1X12.5 MVA 66/11 KV (1x12.5 MVA) | Additional 12.5 MVA 66/11 KV P/T/F | 203.61 | 203.61 |  | 2023-24 |  |  | 62 | 141.61
66 | 96/SZ/2022-23 Annexure-B | SZ | ROPAR |  |  |  | 66 KV S/S Jandiali 1x20 MVA, 66/11 KV P/T/F | Augmentation of 20 MVA T/F with 31.5 MVA P/T/F | 199.77 | 199.77 |  | 2022-23 | Work completed in 07/2022. |  | 199.77
67 | 97/SZ/2022-23 Annexure-B | SZ | MOHALI |  |  |  | To deload Kharar Majra line | i) Stringing of 2nd ckt with 0.2sq" ACSR from 66 kv S/S Majra upto T-off point for 66 KV Mullanpur S/S from point a-c 1.4 km as per attached sketch. 2) One no. bay at 66 kv S/S Majra | 13.188 29 | 16.088 |  | 2022-23 |  |  | 16.088
68 | 98/SZ/2022-23 Annexure-B | SZ | SANGRUR |  |  |  | To deload 220 kv S/S Sunam and deloading of 66 kv line cheema ckt-1&2 by shifting OF 66KV S/S Ganduan to 66 KV Chajjli and stringing of 2nd ckt. for making LILO arrangement at 66 KV S/S Satoj and Proposed new 66 KV SC on DC line from 66 KV Chhajali to 66 KV Ganduan | 1) Stringing of 2nd ckt with 0.2sq" ACSR condutor on existing sc/dc line from T-off point A as per attached sketch to 66 KV S/S Satoj of approx. length 4 km 2) one no. bay at 66 KV S/S Satoj 3) new 66kv SC on DC line with 0.2" ACSR conductor of approximately length of 8.5km from 66 kv Chhajali to 66kv Ganduan 4) 1 no 66 kv bay at 66kv Chhajali and 1 no 66 kv bay at 66kv Ganduan s/stn. | 37.68 29 229.16 58 | 353.84 |  | Paddy-2023 2023-24 |  |  | 248 | 105.84
69 | 99/SZ/2022-23 Annexure-B | SZ | BARNALA |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-2 with 31.5 MVA, 66/11 KV P/T/F at 66 KV S/S Barnala (3x20MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-2 with 31.5 MVA, 66/11 KV P/T/F at 66 KV S/S Barnala | 199.77 | 199.77 |  | 2022-23 |  |  | 199.77
70 | 100/SZ/2022-23 Annexure-B | SZ | MOHALI |  |  |  | Providing second source of 66 KV supply to 66KV S/S Baltana | 1) Replacement of DC on DC line of 0.2sq" conductor with DC on DC line of 0.4" ACSR conductor on 220 kv towers (in DC configuration) of approximately length of 1.7 km from 66 kv Mubarakpur upto T-off point of 66 kv Baltana S/S 2) Stringing of 2nd ckt with 0.2 sq" conductor on existing sc on dc line for 66 kv Baltana S/S of approximately length of 6.579 km from point B to C 3) laying of 66 kv single ckt 240mm2 copper cable to tap 2nd ckt for 66 kv S/S Baltana from TL-1 to TL-2 of Baltana line 4) laying of 66kv single ckt 240mm2 copper cable from tl-33 up to 66 kv Baltana S/S 5) 1 no 66 kv bay at Baltana | 116.569 61.974 27.654 52.794 29 | 287.991 |  | 2023-24 |  |  | 87 | 200.991
71 | 135/SZ/2022-23 Annexure-B Amend. No. 02/2022-23 dated 15.06.2022 | SZ | SANGRUR |  |  |  | a)66KV S/S Bus Stand Sangrur (NEW) (Including 1 no. complete 66KV line bay) b)Replacement of 66 KV Line from 220 KV S/Stn BBMB Sangrur to 66 KV S/Stn Samundgarh on HRP with SC on DC line with 0.2 sq inch ACSR 3.2 Km(from point A to B as per sketch c)6 KV 240 MM2 Single ckt,lxC XLPE cable 2.7 Km from point B to Cas per sketch up to proposed site of 66 KV S/Stn Bus Stand Sangrur. d)66 KV line Bay | a) 20 MVA, T/F 66/11 KV b) 3.2 Km HRP line replacement with 0.2 sq inch ACSR SC on DC Tower line. C) 2.7 Km Single ckt 240mm2 IXC XLPE cable (NEW) d) 1 no. | 258.58 90.70 -9.6 556 40.64 | 936.32 |  | 2022-23 |  |  | 300 | 636.32
72 | 111/SZ/2022-23/Shifted from Annex. C to B Amend. No. 04/2022-23 dated 08.07.2022 | SZ | Sangrur |  | 25 |  | 66 KV S/Stn Dugal (1 x 12.5 MVA, 66/11 KV) | Addl 12.5 MVA, 66/11 KV T/F | 203.61 | 203.61 |  | Paddy-2023 |  |  | 143 | 60.61
73 | 137/SZ/2022-23 Annexure-B Amend. No. 06/2022-23 dated 01.08.2022 | SZ | Ropar |  |  |  | Augmentation of existing 6.3/8 MVA 66/11 KV P/T/F with 12.5 MVA at 66 KV S/S Behrampur bet under P&M Circle PSPCL Patiala | Augmentation of existing 6.3/8 MVA 66/11 KV P/T/F with 12.5 MVA | 85.92 | 85.92 |  | Paddy-2023 |  |  | 61 | 24.92
74 | 101/SZ/2022-23 Annexure-C | SZ | Patiala |  |  |  | 66 KV S/Stn Balbera (2 x 20 MVA, 66/11 KV) | Addl 20 MVA, 66/11 KV T/F | 285.93 | 285.93 |  | 2023-24 |  |  | 86 | 199.93
75 | 102/SZ/2022-23 Annexure-C | SZ | Barnala | 69 |  |  | 66 KV Chananwal (1 x 20 MVA, 66/11 KV) | Addl 12.5 MVA, 66/11 KV T/F | 203.61 | 203.61 |  | 2023-24 |  |  | 62 | 141.61
76 | 103/SZ/2022-23 Annexure-C | SZ | Barnala | 35 |  |  | 66 KV S/Stn Kuthala ( 1 x 20 MVA + 1x 12.5 MVA, 66/11 KV) | 20 MVA to repl 12.5 MVA, 66/11 KV T/F | 157.03 | 157.03 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 110 | 47.03
77 | 104/SZ/2022-23 Annexure-C | SZ | Patiala | 47 |  |  | 66 KV S/Stn Gajewas (Aug) 1x12.5+1x20 MVA, 66/11 KV | 20 MVA to repl 12.5 MVA | 157.03 | 157.03 |  | 2024-25 |  |  |  | 48 | 109.03
78 | 105/SZ/2022-23 Annexure-C | SZ | Sangrur | 66 |  |  | 66 KV S/Stn Shatrana (2 x 20 MVA, 66/11 KV) | Addl 20 MVA, 66/11 KV | 285.93 | 285.93 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 201 | 84.93
79 | 106/SZ/2022-23 Annexure-C | SZ | Sangrur | 23 |  |  | 66 KV Grid S/Stn Moonak (2 x 20 MVA, 66/11 KV) | 31.5 MVA, 66/11 KV T/F to replace 20 MVA, 66/11 KV T/F | 199.77 | 199.77 |  | 2023-24 |  |  | 60 | 139.77
80 | 107/SZ/2022-23 Annexure-C | SZ | Patiala | 71 |  |  | 66 KV Grid S/Stn Ghanour (2 x 20 MVA, 66/11 KV) | Addl 12.5 MVA, 66/11 KV T/F | 203.61 | 203.61 |  | 2024-25 |  |  |  | 62 | 141.61
81 | 108/SZ/2022-23 Annexure-C | SZ | SNG |  |  |  | 66 KV S/S Kulara 1x12.5 MVA + 1x20 MVA | Aug. of 12.5 MVA 66/11 KV T/F with 20 MVA 66/11 KV | 157.03 | 157.03 |  | 2023-24 |  |  | 48 | 109.03
82 | 109/SZ/2022-23 Annexure-C | SZ | ROP |  |  |  | 66 KV S/S Majra (2x20 MVA) | Aug. of 20 MVA T/F with 31.5 MVA. 66/11 KV | 199.77 | 199.77 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 140 | 59.77
83 | 110/SZ/2022-23 Annexure-C | SZ | MOH |  |  |  | 66 KV S/Stn. Ramgarh Bhudha (1x20 MVA) | Addl. 20 MVA 66/11 KV T/F | 285.93 | 285.93 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 100 | 185.93
84 | 112/SZ/2022-23 Annexure-C | SZ | Patiala |  |  |  | 66 KV Grid S/Stn Chounth (1 x 12.5 MVA, 66/11 KV) | Addl 12.5 MVA, 66/11 KV T/F | 203.61 | 203.61 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 143 | 60.61
85 | 113/SZ/2022-23 Annexure-C | SZ | Barnala | 46 |  |  | 66KV S/S Sukhpura 2x12.5KVA, 66/11 KV | 1x20 MVA 66/11KV to rep. 1x12.5MVA 66/11KV (T-1) | 157.03 | 157.03 |  | 2023-24 |  |  | 48 | 109.03
86 | 115/SZ/2022-23 Annexure-C | SZ | SANGRUR |  |  |  | Augumentation of 12.5 MVA, 66/11 KV P/T/F-2 with 20 MVA, 66/11 KV at 66 KV S/S Rai Dhrana (1x20+ 1x12.5)MVA | Augumentation of 12.5 MVA, 66/11 KV P/T/F-2 with 20 MVA, 66/11 KV at 66 KV S/S Rai Dhrana | 157.03 | 157.03 |  | 2023-24 |  |  | 48 | 109.03
87 | 116/SZ/2022-23 Annexure-C | SZ | Mohali |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Ph-1, Mohali (3x20 MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Ph-1, Mohali | 199.77 | 199.77 | Work completed | 2022-23 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 199.77
88 | 117/SZ/2022-23 Annexure-C | SZ | Mohali |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-2 with 31.5 MVA, 66/11 KV at 66 KV S/S , Bhabat (2x31.5+1x20 MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-2 with 31.5 MVA, 66/11 KV at 66 KV S/S , Bhabat | 199.77 | 199.77 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 140 | 59.77
89 | 118/SZ/2022-23 Annexure-C | SZ | PATIALA |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Sanour (2x20MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Sanour | 199.77 | 199.77 |  | 2023-24 |  |  | 60 | 139.77
90 | 119/SZ/2022-23 Annexure-C | SZ | MOHALI |  |  |  | Additional 12.5 MVA 66/11 KV P/T/F at 66 KV S/S Dhaidi | Additional 12.5 MVA 66/11 KV P/T/F at 66 KV S/S Dhaidi | 203.61 | 203.61 |  | Paddy-2023 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 143 | 60.61
91 | 120/SZ/2022-23 Annexure-C | SZ | SANGRUR |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-2 with 31.5 MVA, 66/11 KV at 66 KV S/S Nagra (2x20 MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-2 with 31.5 MVA, 66/11 KV at 66 KV S/S Nagra | 199.77 | 199.77 |  | 2023-24 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 60 | 139.77
92 | 121/SZ/2022-23 Annexure-C | SZ | BARNALA |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Thulliwal (2x20 MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Thulliwal | 199.77 | 199.77 |  | 2023-24 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 60 | 139.77
93 | 122/SZ/2022-23 Annexure-C | SZ | BARNALA |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F with 31.5 MVA, 66/11 KV at 66 KV S/S Rangian (2x20MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F with 31.5 MVA, 66/11 KV at 66 KV S/S Rangian | 203.61 | 203.61 |  | 2023-24 | CE/DS South Patiala shall take necessary action to include the same in TWL 2022-23. |  | 62 | 141.61
94 | 123/SZ/2022-23 Annexure-C | SZ | BARNALA |  |  |  | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Katron (2x20 MVA) | Augumentation of 20 MVA, 66/11 KV P/T/F-1 with 31.5 MVA, 66/11 KV at 66 KV S/S Katron | 199.77 | 199.77 |  | 2023-24 & 2024-25 |  |  |  | 60 | 139.77
95 | 124/SZ/2022-23 Annexure-C | SZ | SANGRUR |  |  |  | Stringing of 2nd Circuit on SC/ DC line to 66 KV Gujjran T-off from 220 KV BBMB Sangrur to 66 KV Dirba | 1) Stringing of 2nd circuit with ACSR 0.2sq" /5.4 Km on existing SC on DC line to 66 KV Gujjran T - off point from 220 KV S/S BBMB Sangrur to 66 KV Dirba idle HRP line 2) One no 66 KV Bay at Gujjran | 50.86 29 | 79.86 |  | 2023-24 & 2024-25 |  |  |  | 24 | 55.86
96 | 54/SZ/2022-23 Annexure-B | SZ | Sangrur |  |  |  | 66 KV line bay at 220 KV S/S Banga for 66 KV S/S Sailwala | 1 no. 66 KV line bay with ckt. breaker | To be executed by PSTCL | To be executed by PSTCL | To be executed by PSTCL |  |  |  | 0 | 0
97 | 36/SZ/2022-23 Annexure-A | SZ | Sangrur | 43 |  |  | a) Un-manned 66 KV S/Stn Matoli (New) [including 1 No. 66 KV Line Bay with isolators only at new 66 KV S/Stn Matoli] b) T-off of existing 66 KV line from ‘220 KV S/Stn Patran to 66 KV S/Stn Shergarh (Khanouri)’ for new 66 KV S/Stn Matoli (Un-manned) | 1 x 6.3 / 8 MVA, 66/11 KV 1 KM / 0.2 sq"; SC on DC Towers | 219.92 26.96 | 246.88 | Line work completed and grid work in progress |  |  |  | 180 | 67
98 | 114/SZ/2022-23 Annexure-C | SZ | MOHALI |  |  |  | 66 KV line from 220 KV Banur-Sekhupura-Mubarkpur | A) Stinging of 2nd ckt of 0.2 sq" ACSR conductor on existing SC on DC line of approx length of 1.5km from T-off point to Sekhpura S/S for making LILO arrangement at 66 KV Sekhupura B) 1 NO 66 KV bay at 66 KV S/S Sekhupura | 14.13 29 | 43.13 | [6 empty] | 43.13 | 0
99 | Not Planned | SZ | Barnala |  |  |  | a) 66 KV S/Stn Kala Mehar Barnala (New) b) T-off of existing 0.2 sq" SC/SC Idle 66 KV line from 220 KV S/Stn Handiaya to 66 KV S/Stn Thikriwal for new 66 KV S/Stn Kala Mehar Barnala c) 66 KV Line Bay (at new 66 KV S/Stn Kala Mehar Barnala) | 1 x 20 MVA, 66/11 KV 0.3 KM/ 0.2 sq" SC on DC Towers. 1 No. | 236 6.192 39.23 | 281.422 | [6 empty] | 85 | 196.422
100 | Not Planned | SZ |  |  |  |  | 66KV S/Stn. Hathan | Addl. 12.5 MVA 66/11 KV | 203.62 | 203.61 | [6 empty] | 62 | 141.61
101 | Not Planned | SZ |  |  |  |  | 66KV Naudhrani | Addl. 12.5 MVA 66/11 KV | 203.62 | 203.61 | [6 empty] | 62 | 141.61
102 | Not Planned | SZ |  |  |  |  | Replacement of old 0.4 Sq" conductor of Existing SC on DC line from 220KV Phase-7 Mohali to Phase-1 Mohali with HTLS conductor (DC on DC) | 2 KM | 110 | 110 | [6 empty] | 33 | 77
103 | Not Planned | SZ |  |  |  |  | LILO with 66KV Sector-71 and 66KV Sector-68 with Replacement of old 0.2 Sq" conductor of Existing DC on DC line from 220KV Phase-1 Mohali to Phase-9 Mohali with HTLS conductor (DC on DC) | 9KM | 270 | 270 | [6 empty] | 81 | 189
104 | Not Planned | SZ |  |  |  |  | LILO and Replacement of old 0.2 Sq" conductor of Existing DC on DC line from 220KV Sector-80 Mohali-II to Phase-9 Mohali with HTLS conductor (DC on DC) | 3.282 KM | 99 | 99 | [6 empty] | 30 | 69
105 | Not Planned | SZ |  |  |  |  | Replacement of old 0.2 Sq" conductor of Existing DC on DC line from 66KV Sector-88 Mohali to Phase-8B Mohali with HTLS conductor (DC on DC) | 4.5KM | 135 | 135 | [6 empty] | 40 | 95
106 | Not Planned | SZ |  |  |  |  | Replacement of old 0.2 Sq" conductor of Existing DC on DC line from 220KV Phase-7 Mohali-1 to 66KV Phase-8B Mohali with HTLS conductor (DC on DC) | 5.5KM | 105 | 105 | [6 empty] | 31 | 74
107 | Not Planned | SZ |  |  |  |  | Replacement of old 0.2 Sq" conductor of Existing DC on DC line from 220KV Phase-7 Mohali-1 to 66KV Phase-7 Mohali with HTLS conductor (DC on DC) | 4KM | 120 | 120 | [6 empty] | 36 | 84
[14 empty] | 728.1 | 11685.4088 | 10589.3382 | 3104.204 | 1151.542
|  |  |  | 19 | 6 | 3

## CZ
|  | CENTRAL ZONE | [12 empty] | Annexure-III
Sr.no. | TWL sr.no. 2022-23 | Zone | Circle Name | MYT 2020-21 | MT 2021-22 | MT 2022-23 | Name of Work | Scope of Work | Estt. Cost (in lacs) | Estt. Cost (in lacs) | Remarks | Year | Expenditure upto 31.03.2022 (in lacs) | Expenditure in Year 2022-23 (in lacs) | Expenditure in Year 2023-24 (in lacs) | Expenditure in Year 2024-25 (in lacs) | Expenditure in Year 2025-26 (in lacs)
1 | 2/CZ/2022-23 Annexure-A | CZ | LDH |  |  |  | i)66KV line (New) from 220KV S/S Dhandari Kalan-2 to 66KV S/S Focal Point Phase-7 Ldh. ii) 66 KV line bays | a)0.350m/630mm2/U/G XLPE 66KV cable towards 220KV S/S Dhandari-2 side. b)1.2 Km/0.4" SC on DC Towers line upto 66 KV S/S Focal Point P-7 Ldh. c)0.500m/630mm2/U/G XLPEcable towards 220 KV S/S Dhandari-2 side. 1 Nos. at 66 KV Phase-7 end. Note:2 no 66 kv bays at 220KV S/S Dhandari Kalan-2 to be constructed by PSTCL. | 145.29 62.21 207.55 29 | 444.05 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2022-23 | 1.03 | 310.114 | 132.906
2 | 4/CZ/2022-23 Annexure-A | CZ | LDH |  |  |  | T-Off of 220KV Lalton kalan-- 66KV Giaspura Line for 66KV Alamgir 5.0Kms/ 0.125 Sq" / HRP . | 5.0Kms/0.4 Sq" SC on Ring Main towers to repl. existing line . | 259.20 -15.1 | 244.1 | Dispute persists on TL-17, Also shutdown issue.. | 2023-24 |  | 74 | 170.1
3 | 9/CZ/2022-23 Annexure-A | CZ | KHN |  |  |  | a) Construction of new interconnected 66KV SC on DC line with 0.2sq" conductor between 66KV S/S Sidhwan Bet to Bhundri. b) 66KV Bays | 12.7Km/0.2Sq"/ SC on DC Towers. 2 No. Bays 1 No. Bay at Bhundri & 1 No. Bay at Sidhwan Bet | 342.39 58 | 400.39 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2022-23 | 71.18 | 300 | 29.21
4 | 13/CZ/2022-23 Annexure-A | CZ | KHN |  |  |  | 220KV Malerkotla-Maloud line 12km/0.1 sq" 66KV Bays | Replacement of HRP12Km/0.1sq" line with 12km/0.2sq."/DC on DC towers. 1 No. Bay at Maloud Note :- 1 No. bay at Malerkotla to be planned by PSTCL | 436.68 -36.24 29 | 429.44 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2023-24 |  | 129 | 300.44
5 | 16/CZ/2022-23 Annexure-A | CZ | LDH |  |  |  | 66 KV Latala - Ahmedgarh line 0.15sq.inch/12.4 Kms. SC on SC towers. 66KV Bays | a)Replacement of line with 0.2sq.inch /10Km conductor DC on DC towers from Latala upto T-off point for Latala of 66 KV ine from 220 KV Sahnewal - 66 KV Ahmedgarh. b) Replacement of 66 KV line with 0.2 sq.inch/2.4 Km DC on Multickt. Towers from 66 KV Ahmedgarh to T-off point for Latala of 66 KV from 220 KV Sahnewal-66 kv Ahmedgarh to accommodate 2 ckts. Of Latala-Ahmedgarh and one ckt. of Sahnewal- Ahmedgarh line. 3 Nos (1 No. bay at Latala & 2 No. bays at Ahmedgarh) | 363.90 -30.2 235.66 -7.25 87 | 649.11 | CE/DS(central), PSPCL, Ludhiana to ask the PSTCL to provide the bay. | 2023-24 |  | 195 | 454.11
6 | 20/CZ/2022-23 Annexure-A | CZ | LDH |  |  |  | a)T-off of 220KV Sahnewal -- 66KV Latala-- 66KV Ahmedgarh for 66KV Alamgir (New Line) b) 66KV line bays | 6.0Kms/0.2 Sq"/ SC on DC towers . b) 1 Nos. | 161.76 29 | 190.76 | Dy.CE/TL Circle, Jalandhar informed that forest clearance is pending. | 2022-23 | 9.91 | 180.85
7 | 25/CZ/2022-23 Annexure-A | CZ | KHN. |  | 58 |  | 132 KV Kharar to Badali Ala Singh 66KV Line 16 Km/0.15 sq" / HRP line | Replacement of 0.15 sq" on HRP with 0.2sq.inch SC on DC, 16 Km | 431.36 -48.32 | 383.04 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2022-23 |  | 383.04
8 | 27/CZ/2022-23 Annexure-A | CZ | City East ldh | 33 |  |  | a) 66KV S/S Tibba (NEW) b) New proposed 2.5 km. 66KV underground XLPE Cable 630 mm2 tapping / T-off from existing 66KV line from 220 KV BBMB Jamalpur to 66KV Nurewal DC on DC line ckt. c) 66KVline Bay | a) 1x20MVA, 66/11 KV b)2.5 km/66KV underground XLPE Cable 630 mm2 c) 1 no.66KV line Bay | 302.5 600 29 | 931.5 | To be executed by 31.03.2023. | 2023-24 |  | 280 | 651.5
9 | 36/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | 66 KV line between 220KV Bassi Pathana to 66KV S/S Sarhind T-off to Attewali 0.2sq''/Double ckt/ DCon DC line | a)Stringing for 2nd Ckt. 2.8Km/ 0.2sq."/ ACSR conductor from T-off point to 66KV S/S Attewali b) New 7 nos. DC on DC towers (D2=3nos.,D60=1nos.,D90=1nos. and X type draft towers =2nos.) by replacing single ckt towers b) 66KV line Bay 1 No. at 66KV S/S Attewali | 26.38 29 | 55.38 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2023-24 |  | 17 | 38.38
10 | 37/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | 66 KV line from 220KV S/s Doraha to 66 KV S/s Chawa (existing 9.7Km /0.15sq'' HRP line) | New 9.7Km /0.2sq''/SC on DC tower line by replacing existing 0.15sq''/9.7Km/HRP line on the same ROW (to be run from existing 66KV bay) | 261.512 | 261.512 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2022-23 |  | 183.0584 | 78.4536
11 | 39/CZ/2022-23 Annexure-B | CZ | LDH |  |  |  | 66 KV S/S BHUNDARI 1x10/12.5 MVA | ADDITIONAL 6.3/8 MVA 66/11 KV P/T/F AT 66 KV S/S Bhundari | 203.61 | 203.61 |  | 2023-24 |  | 62 | 141.61
12 | 40/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | 66 KV S/S HARGANA 1x20 MVA | ADDITIONAL 12.5 MVA 66/11 KV P/T/F AT 66 KV S/S HARGANA | 203.61 | 203.61 |  | 2023-24 |  | 62 | 141.61
13 | 42/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | Augmentation of 66kV line from 220kV BBMB Jamalpur to 66kV Chandigarh road line. | Augmentation of existing 0.2 sq" ACSR conductor of 66 Kv line on multi circuit towers from 220kV BBMB Jamalpur Ludhiana to 66 KV s/stn. Chandigarh road, 1.5ckt km with 0.4sq" ACSR | 40.44 | 40.44 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2022-23 |  | 40.44
14 | 48/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | LILO of 66kV line from S/Stn. 220kV Doraha to 66kV Apparel Park-Chawa line at 66kV S/Stn. Apparel Park | a) 30 meter jumper are to be erected from deading Tower no:-38 erected just ouside 66kV S/S Apparel park. b) Erection of 2No. 66kV Bay's at 66kV S/S apparel park. c) Erection of 66kV Bus-bar at 66kV S/S Apparel Park. d) Installation of 2 No D-60 Towers | 20 58 29 20 | 127 | Dy.CE/TL Circle, Jalandhar to inform the target date. | 2023-24 |  | 39 | 88
15 | 51/CZ/2022-23 Annexure-C | CZ | LDH. |  | 89 |  | 66 KV S/S Gill Road 1X31.5 MVA, 2X16/20 MVA, 1x20 MVA | 1x31.5 MVA, 66/11KV to repl. 1x16/20 MVA, 66/11K V | 199.78 | 199.78 | To be shifted to Annex. B by DS organization. | 2023-24 |  | 60 | 139.78
16 | 52/CZ/2022-23 Annexure-C | CZ | KHN |  | 41 |  | 66KV Chaurwala (Aug) 2x20 MVA,66/11 K V | Addl. 3rd 20 MVA T/F 66/11KV | 285.93 | 285.93 | To be shifted to Annex. B by DS organization. | 2023-24 |  | 86 | 199.93
17 | 56/CZ/2022-23 Annexure-C | CZ | LDH |  |  |  | 66 KV S/S SOUTH CITY LUDHIANA 1x20 MVA | ADDITIONAL 20 MVA 66/11 KV P/T/F AT 66 KV S/S SOUTH CITY LUDHIANA | 285.93 | 285.93 | To be shifted to Annex. B by DS organization. | 2023-24 |  | 86 | 199.93
18 | 57/CZ/2022-23 Annexure-C | CZ | LDH |  |  |  | 66 KV S/S DUGRI 1x20 MVA + 1x31.5 MVA | AUGMENTATION OF T-2 20 MVA, 66/11 KV P/T/F WITH 31.5 MVA, 66/11 KV AT 66 KV S/S DUGRI | 199.78 | 199.78 | To be shifted to Annex. B by DS organization. | 2022-23 |  | 199.78
19 | 58/CZ/2022-23 Annexure-C | CZ | KHN |  |  |  | 66 KV S/S ATTEWALI 1x12.5 MVA + 1x20 MVA | AUGMENTATION OF T-2 12.5 MVA, 66/11 KV P/T/F WITH 20 MVA, 66/11 KV AT 66 KV S/S ATTEWALI | 157.03 | 157.03 | To be shifted to Annex. B by DS organization. | 2023-24 |  | 48 | 109.03
20 | 60/CZ/2022-23 Annexure-C | CZ | KHN |  |  | 44 | 66 KV S/S BHARI 3x20 MVA | AUGMENTATION OF T-1 20 MVA, 66/11 KV P/T/F WITH 31.5 MVA, 66/11 KV AT 66 KV S/S BHARI | 199.78 | 199.78 | To be shifted to Annex. B by DS organization. | 2023-24 |  | 60 | 139.78
21 | Not Planned | CZ |  |  |  |  | 66KV Nurewal -II | 5th 20 MVA 66/11KV to be replaced with 31.5MVA,66/11KV, T/F | 199.78 | 199.78 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 199.78
22 | Not Planned | CZ |  |  |  |  | 66 KV Pawa Road (New) | 2x 20MVA,66/11KV, T/F | 625 | 625 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 437.5 | 187.5
23 | Not Planned | CZ |  |  |  |  | 66KV S/S Sewerage Treatment Plant, Ludhiana | 1x12.5MVA, 66/11KV | 285 | 285 | Revise the feasibility as discussed. |  |  |  |  | 199.5 | 85.5
24 | Not Planned | CZ |  |  |  |  | 66KV Kanganwal - II | 20 MVA to 31.5 MVA 66/11KV | 199.78 | 199.78 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 199.78
25 | Not Planned | CZ |  |  |  |  | 66KV S/S Focal Point Phase-4 (New) b)66KV line from Indra park to 66KV S/S Focal Point Phase-4(New) c)Land cost | 1x 31.5MVA,66/11KV, T/F 1.200KMs/0.4Sq." SC on DC 2572 Sq.yard. | 358 42.75 210.9 | 611.65 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 428.155 | 183.495
26 | Not Planned | CZ |  |  |  |  | 66KV Amloh | Addl. 31.5 MVVA, 66/11KV | 300 | 300 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 300
27 | Not Planned | CZ |  |  |  |  | 66KV Mallewal | Addl. 12.5 MVA, 66/11KV | 285.93 | 285.93 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 285.93
28 | Not Planned | CZ |  |  |  |  | 66KV Raiwal | Addl. 12.5 MVA, 66/11KV | 285.93 | 285.93 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 285.93
29 | Not Planned | CZ |  |  |  |  | 66KV Chaura Bazar | AUGMENTATION OF 20 MVA, 66/11 KV P/T/F WITH 31.5 MVA, | 199.78 | 199.78 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 199.78
30 | Not Planned | CZ |  |  |  |  | 66KV Janta Nagar | AUGMENTATION OF 20 MVA, 66/11 KV P/T/F WITH 31.5 MVA, | 199.78 | 199.78 | CE/DS(central), PSPCL, Ludhiana shall take necessary action to include the same in TWL 2022-23. |  |  |  |  | 199.78
31 | 1/CZ/2022-23 Annexure-A | CZ | KHN |  |  |  | a)T-off portion for existing 66KV S/S Ikolaha (to be U/G to 220kV) 0.5km/0.2Sq" SC on SC Towers. b) 66kV line from Jarg upto T-off portion for 66kV Ikolaha portion for 66KV Ikolaha (Prop. U/G to 220kV) 14.5Km/0.125Sq" SC on SC Towers. c)66kV line from Khanna upto T-off portion for 66kV Ikolaha (Prop U/G to 220kV) 6.5Km/ 0.125Sq"/SC on SC Towers. d) 66kV line bays | a) Stringing of 3rd Ckt for Jarg line, 0.5 Km/0.2 Sq.” SC on Multi Ckt. Ikolaha - Bahu Majra line. (planned against sr. no. 12/2017-18) b)14.5 km/0.2 Sq.” SC on DC Towers to repl. existing line (to be extended up to 220 KV Ikolaha through 3rd Ckt. on MCT) c) 6.5km existing line (6.5Km/ 0.125 Sq.") Ikolaha—Khanna to be retained & run from existing 66 KV Bay at 220 KV Ikolaha d)-Deleted'- | 4.71 390.92 -43.79 | 351.84 | a & b) Work stands completed since 08/03/2021 c) NOT FEASIBLE |  |  | 250 | 101.84
32 | 5/CZ/2022-23 Annexure-A | CZ | LDH |  |  |  | a)66 KV Line from 220KV S/S Sahnewal up to T-Off point for 66 KV S/S Alamgir 14KM/0.125Sq"/ SC on HRP. | a)6.645KM/0.2 Sq"/SC on DC Towers to replace existing line. (Line from 220 KV Sahnewal to 66 KV Latala, upto T-off of Alamgir) | 179.15 -20.07 | 159.08 | stubbing and erection work completed, for pending sag shutdown required on kanganwal circuits |  |  | 70 | 89
33 | 6/CZ/2022-23 Annexure-A | CZ | KHN |  |  |  | i)220 KV S/S G-2 to 66 KV Bhari Line (Aug.) ii)66KV line bay at 66KV S/S Bharri | a) Replacement of conductor with 0.2 Sq" on existing structure from TL-1 to TL-10 b) 0.2 Sq"/ SC on DC towers from TL-11 to TL-21 to replace existing H-Rail Pole Line. 1 No. | 16.3 62.3 -7.55 29 | 100.05 | Railway crossing pending, rets line stands completed. Line charged using existing HRP in section of railway. B) New line charged using existing railway crossing |  |  | 70 | 30
34 | 7/CZ/2022-23 Annexure-A | CZ | LDH |  |  |  | 220KV S/S Pakhowal to 66 KV S/S Narangwal, to replace the existing conductor of 0.1sq. inch on rail poles with 0.2 Sq. inch SC on DC towers. | 10km/0.2 Sq." SC on DC Towers to replace existing line. | 269.6 -30.2 | 239.4 | New line has been charged from TL 3 to TL 62 on dated 22-06-2018. 2 no. Towers pending. |  |  | 150 | 89
35 | 10/CZ/2022-23 Annexure-A | CZ | LDH. |  | 148 |  | a)66kv T-off link line from 220kv S/S Ikolaha -66 KV jarg line for Shamspur. (New) b) 66KV Bays | 8 KM/0.2 sq."SC on DC Towers to make ringmain. 1 No. Bay at Shamspur | 215.68 29 | 244.68 | work in progress. Dispute at TL 35 to 40 |  |  | 180 | 65
36 | 29/CZ/2022-23 Annexure-A | CZ | LDH. |  | 48 |  | 66 KV Fountain Chowk 1x31.5 MVA | 1.Existing 31.5MVA to be replaced with 20MVA 2. Addl. 2nd. 20MVA | -134.6 285.9 | 151.3 | Work in progress |  |  | 20 | 101 | 30.3
37 | 32/CZ/2022-23 Annexure-A | CZ | KHN |  |  |  | a) 66 KV S/Stn. Grain Market MGG 3x20 MVA,66/11 KV | 1x31.5MVA, 66/11KV to repl. 1x20 MVA, 66/11 KV T/F | 199.78 | 199.78 | Work pending due to pending control room building extension |  |  | 150 | 50
38 | 34/CZ/2022-23 Annexure-B | CZ | LDH |  | 150 |  | a)66KV Gill Road to Basant Park line 2.3 Km/0.4 sq"SC T + HRP b)66KV Basant Park - Dholewal - 3.2 Km/0.2Sq" HRP c) 66kV line bays | (a)2.3Km/0.4Sq" DC on DC Towers. (b)3.2Km/0.4Sq" DC on DC Towers. 4 No. (one bay at Gill Rd., one bay Millarganj, & two for Basant Park) | 157.71 -6.95 219.42 -9.66 116 | 476.52 | Survey yet to be done |  |  |  | 334 | 143
39 | 38/CZ/2022-23 Annexure-B | CZ | S/U LDH / Central Zone |  |  |  | a)66 KV S/Stn. Barmi (New) b)66KV line 0.180km /0.2 sq"/ DC on DC tower line for LILO arrangement T-off to Pakhowal to Raikot 66KV line ckt.-2 c)66KV line bay | 6.3/8MVA or 8/10MVA ,T/F 66/11 KV (as per availability) New 0.180km /0.2 sq"/ DC on DC tower line 1 no. for LILO arrangement | 255.44 6.55 29 | 290.99 | Work order issued |  |  | 15 | 276 | -0.01
40 | 41/CZ/2022-23 Annexure-B | CZ | LDH |  |  |  | To deload the 66kV DC line from 220kV S/Stn. Gaunsgarh to 66kV S/Stn. Phase-8 & Tajpur road | i) Stringing of third circuit from 220kv Gaunsgarh to TL-31 with 5.6KM ACSR 0.4sq.inch ii) 66kV Cable 630mm2 (1 no. T/F of 66kV Tajpur running from 220kV S/S Gaunsgarh and other from 220kV S/Stn. Kohara.) i) one no 66 KV bay at 220 KV S/S Gaunsgarh (to be planned by PSTCL)z | 93.69 -- | 93.69 |  |  |  |  | 0 | 50 | 43.69
41 | 43/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | Augmentation of conductor of 66kV line from 220kv Lalton Kalan-66kV Gill Road Ckt no. 1 with HTLS conductor | Sagging of 0.4 sq" equivalent HTLS conductor on SC on DC (approx 13Km) | 532.22 | 532.22 |  |  |  |  | 0 | 150 | 382.22
42 | 44/CZ/2022-23 Annexure-B | CZ | LDH |  |  |  | Augmentation of conductor of 66kV line from 220kv Lalton Kalan-66kV Gill Road Ckt no. 2 with HTLS conductor | Sagging of 0.4 sq" equivalent HTLS conductor on SC on DC (approx 9.6Km) | 393.024 | 393.024 | [5 empty] | 100 | 293.024
43 | 45/CZ/2022-23 Annexure-B | CZ | LDH |  |  |  | Augmentation of conductor of 66kV line from 220kv Sahnewal to 66kV Kanganwal ckt.1 with HTLS conductor | Sagging of 0.4 sq " equivalent HTLS conductor DC on DC tower (approx 8.45 Km) | 345.943 | 345.943 | [5 empty] | 145 | 200.943
44 | 46/CZ/2022-23 Annexure-B | CZ | LDH |  |  |  | Augmentation of conductor of 66kV line from 220kv Sahnewal to 66kV Kanganwal ckt.2 with HTLS conductor | Sagging of 0.4 sq " equivalent HTLS conductor DC on DC tower (approx 8.45 Km) | 345.943 | 345.943 | [5 empty] | 145 | 200.943
45 | 47/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | 66kV line from 220kV S/Stn. Amloh to 66kV Bhadson | Stringing of 2nd circuit of 66 KV line on DC tower from 220 kv S/S Amloh to 66 Kv S/S Bhadson on existing SC/DC line 8 Km 1 no 66 KV bay at Bhadson 1 No 66 KV bay at 220 KV Amloh to be constructed by PSTCL | 75.36 29 --- | 104.36 | [5 empty] | 70 | 34.36
46 | 49/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | Back feed and Ringmain of 66 Kv S/S Agoul | a)Erection of 8.3 Km SC on DC 0.2 sq " ACSR 66 KV line (for connecting 66 KV Hiana Kalan- Agoul line). b) construction of 1 No 66 KV bay at Hiana Kalan c) construction of 1 no 66 Kv bay at Agoul d) Construction of 1 No 66 KV Bus-Bar Sactionalising at Hiana kalan | 223.77 29 29 29 | 310.77 | [5 empty] | 140 | 170.77
47 | 50/CZ/2022-23 Annexure-B | CZ | KHN |  |  |  | 66 KV line from 220 KV S/Stn. G-1 to 66 KV S/Stn. Talwara | Augmentation of existing 5.5Km/0.2sq" DC/DC ACSR 66kV line from 220kV S/S G-1 to 66kV S/S Talwara with HTLS conductor on same towers & ROW | 323.51 | 323.51 | [5 empty] | 100 | 223.51
48 | 53/CZ/2022-23 Annexure-C | CZ | KHN |  | 36 |  | 66 KV Tohra 2x20 MVA, 66/11 K V | Addl. 3rd 20 MVA T/F 66/11KV | 285.93 | 285.93 | [5 empty] | 205 | 80.93
49 | 54/CZ/2022-23 Annexure-C | CZ | LDH |  | 32 |  | 66 KV Latala (Aug) 2x20 MVA,66/11 K V | Augmentation of 1x20MVA with 31.5MVA 66/11 K V | 199.78 | 199.78 | [5 empty] | 170 | 29.78
50 | 55/CZ/2022-23 Annexure-C | CZ | LDH |  | 30 |  | 66 KV Sidhwan Bet 2x20 MVA,66/11 K V | 1No. 20MVA, 66/11KV to be replaced with 31.5MVA | 199.78 | 199.78 | [5 empty] | 170 | 29.78
51 | 59/CZ/2022-23 Annexure-C | CZ | LDH |  |  | 8 | 66 KV S/S MALOUD 1x12.5 MVA + 1x20 MVA | AUGMENTATION OF T-1 10/12.5 MVA, 66/11 KV P/T/F WITH 20 MVA, 66/11 KV AT 66 KV S/S MALOUD | 157.03 | 157.03 | [5 empty] | 140 | 17.03
52 | 61/CZ/2022-23 Annexure-C | CZ | KHN |  |  |  | 66 KV S/S BADALI ALA SINGH 1x20 MVA + 1x31.5 MVA | Augumentation of 20 MVA 66/11 KV P/T/F with 31.5 MVA P/T/F AT 66 KV S/S BADALI ALA SINGH | 199.78 | 199.78 | [5 empty] | 170 | 29.78
53 | 62/CZ/2022-23 Annexure-C | CZ | LDH |  |  |  | To deload the 66kV line from 220kV S/Stn. Gaunsgarh to 66kV S/Stn. Indra Park | Constrcution of 1 no. new bus-bar at 66kV S/Stn. Indra Park for shifting the load of 66kv connection Rockman & 20MVA 66/11kV T-3 T/F of 66kV Indra Park | 29 | 29 | [5 empty] | 29 | 0
54 | 63/CZ/2022-23 Annexure-C | CZ | LDH |  |  |  | 66kv S/Stn. Phase-8 1x20 MVA + 1x31.5 MVA | AUGMENTATION OF T-2 20 MVA,66/11 KV P/T/F WITH 31.5 MVA, 66/11 KV AT 66 KV S/S Phase-8 | 199.78 | 199.78 | [5 empty] | 170 | 29.78
55 | 64/CZ/2022-23 Annexure-C | CZ | KHN |  |  |  | 66kV S/S focal Point Mandi Gobindgarh 4x20 MVA | Augmentation of existing any 1no. 20MVA, 66/11kV Power T/F with 31.5MVA or installation of 1 no. new 20MVA 66/11kV Power T/F | 285.93 | 285.93 | [5 empty] | 205 | 80.93
56 | 65/CZ/2022-23 Annexure-C | CZ | KHN |  |  |  | 66kv S/Stn. Apparel Park 1x20 MVA | Augmentation of existing any 1no. 20MVA, 66/11kV Power T/F with 31.5MVA or intallation of 1 no. new 20MVA 66/11kV Power T/F | 285.93 | 285.93 | [5 empty] | 205 | 80.93
[13 empty] | 82.12 | 3700.2824 | 4150.6096 | 5273.425 | 2384.895
|  |  |  | 1 | 9 | 2

## NZ
|  |  |  | NORTH ZONE | [10 empty] | Annexure-IV
Sr.no. | TWL sr.no. 2022-23 | Zone | Circle Name | MYT 2020-21 | MT 2021-22 | MT 2022-23 | Type | Name of Work | Scope of Work | Estt. Cost (in lacs) | Estt. Cost (in lacs) | Status | Year | Expenditure upto 31.03.2022 (in lacs) | Expenditure in Year 2022-23 (in lacs) | Expenditure in Year 2023-24 (in lacs) | Expenditure in Year 2024-25 (in lacs) | Expenditure in Year 2025-26 (in lacs)
1 | 5/NZ/2022-23 /Annex. A | NZ | NWSR |  |  |  | line | a)66KV Behram to 132KV Banga Line 13KM/0.15 /HRP b) 66KV bays 1 No. at 66KV Behram 1 No. at 132KV Banga | 13KM/0.2 sq"/SC on DC towers (2nd Ckt.) 1 No. To be planned by PSTCL | 350.48 29.00 | 379.48 | Work in progress. Re-Orient of bays is required at both ends | 2022-10-31 | 19.56 | 300 | 59.92
2 | 6/NZ/2022-23 /Annex. A | NZ | HSP |  |  |  | line | a)33KV Hariana (U/G &Aug) 1x12.5 MVA, 66-33/11 KV 1x4 MVA, 33/11 KV 1x5 MVA, 33/11 KV b) 33 KV RP Line 9 KM/0.1 Sq" c) 66 KV bays. | a)Aug &U/G to 66KV with20MVA, 66/11 KV to repl 4 & 5 MVA, 33/11 KV b)U/G of existing line to 66KV on existing structure c)2 nos. d)PartialU/gradation of 33KVbus to 66KV at132KV S/S Chohal to feed 33KV Hariana after U/Gto 66KVfrom existing132/66-33KV 20/25/ MVA T/F. | 302.53 7.00 58.00 15.00 | 382.53 | Sag between T.no. 2 to 8 pending due to raising of 132 kV line, rest of the line is energized | 2022-09-15 |  | 382.53
3 | 7/NZ/2022-23 /Annex. A | NZ | HSP |  |  |  | line | 66KV line from 132KV Hoshiarpur--- 66KV Sham Churasi (14.5Km/HRP/0.15sq'') | Aug.of ACSR 14.5km with 0.2sq" by replacement of HRP line with SC on DC towers | 390.92 -43.79 | 347.13 | Work in progress and pending raising work of 132 KV line | 2022-09-15 |  | 347.13
4 | 8/NZ/2022-23 /Annex. A | NZ | HSP |  |  |  | line | 66KV line from 220KV Rehana Jattan -- Panchata (existing 5Km/HRP/towers 0.1sq''/0.125sq'' + (5Km/SC towers 0.125sq'' ) | 5Km/0.2sq''/DC on DC towers upto Panchta T-off from Rehana Jattan to replace HRP/SConSC tower line. 5Km/0.2sq'' /SC on DC towers from T-off to Panchata S/S to replace 0.125sq''/ SC on SC tower line. | 181.95 -15.10 134.80 -15.10 | 286.55 | Route revised according to BOD decision and estimate for raising of 220 KV line under approval | 2022-10-31 |  | 286.55
5 | 9/NZ/2022-23 /Annex. A | NZ | HSP |  |  |  | line | 66KV Line from 220 KV S/S Dasuya--- 66KV S/S Garhdiwal (Aug) (12Km / 0.125Sq" HRP line ) | Aug.of ACSR 12km with 0.2sq" by replacement of HRP line with SC on DC towers | 323.52 -36.24 | 287.28 | Work in progress (Tower in Sugar Mill Randhawa is pending) | 2022-10-31 | 73.1 | 214.18
6 | 13/NZ/2022-23 /Annex. A | NZ | KPT |  |  |  | line | a) 66KV Link line from Nangal Naraingarh S/S to khusropur S/S b) 66KV bays 1 No. at 66KV NangalNaraingarh 1 No. at 66KV khusropur | 10Km / 0.2 Sq"ACSR./ SC on DC tower line 2 Nos | 269.60 58.00 | 327.6 | Work in progress, Dispute at T.no. 2, 3, 4, 5 (Rana Gurjit) | 2022-23 | 27.43 | 210 | 90.17
7 | 15/NZ/2022-23 /Annex. A | NZ | KPT |  |  |  | line | a)66KV Link line from 66KV S/S Nadala to 66KV S/S Bholath b) 66KV bays 1 No. at 66KV Nadala 1 No. at 66KV Bholath | 7 Km/0.2Sq"ACSR./SC on DC tower line 2 Nos | 188.72 58.00 | 246.72 | Work held up, Site dispute at T.no. 15,18,36,41 to 47. (Rana Gurjit) | 2022-23 | 57.25 | 130 | 59.47
8 | 17/NZ/2022-23 /Annex. A | NZ | NWSR |  |  |  | line | Amendment in scope of work Stringing of 2nd ckt on existing 66 KV line from 220 KV Jadla to 66 KV Balachour 1 No. at 220KV Jandla | Stringing of 2nd ckt, 7 KM/0.2 sq" ACSR on existing Jadla-Balachaur DC on DC line up to T. No. 36 for Jadla-Kathgarh line. 1 no. bay at 220 KV S/Stn. Jadla shall be planned by PSTCL To be planned by PSTCL | 65.94 | 65.94 | Work in Progress, planning amendment under process for adding 1 no. tower at 220 KV S/S Jadla due to change in position of bay. | 2022-08-15 | 15.08 | 36 | 14.86
9 | 20/NZ/2022-23 /Annex. A | NZ | KPT | 54 |  |  | line | a)66KV LE bay at 66KV S/S Mehsampur to feed 132 S/S Nakodar | 1 nos. | 14 | 14 | Tender floated for civil work
10 | 21/NZ/2022-23 /Annex. A | NZ | NWSR | 47 |  |  | line | 66 KV line from 66 KV S/S Rahon -- 66 KV Aur (New) b) 66KV bays 1 No. at 66KV Rahon 1 No. at 66KV Aur | a) 9.650 Km/0.2Sq" SC on DC Towers line b) 66KV U/G cable 240mm2 =600mts. 2 No | 260.16 150.84 58.00 | 469 | Work In Progress, | 2022-12-31 | 153.68 | 220 | 95.32
11 | 25/NZ/2022-23 /Annex. A | NZ | HSP |  |  | 64 | line | a) 66 KV line from 220 KV S/s Dasuya to 66 KV S/s Miani (18.702 km/ 0.1 sq."/ HRP line) | i) Replacement of 4.095 km /0.15 sq." conductors on existing towers of Dasuya-Khunkhun (TL1 to 20 erected in the RoW of HRP line) with 0.2 sq." conductor to make Double ckt. Line ii) Replacement of existing rail pole line 14.067 km/0.1 sq." conductor with SC on DC towers with 0.2 sq." conductor. | 38.57 379.25 -42.48 | 375.34 | Work In Progress, Tower material required | 2022-23 | 130.32 | 170 | 75.02
12 | 30/NZ/2022-23 /Annex. A | NZ | KPT | 4 |  |  | line | a) 66KV Line Lohian Kalan---Rupewali Line (New link) b) 66KV bays 1 No. at 66KV Lohian Kalan 1 No. at 66KV Rupewali Line | 7Km/ SC on DC Towers line /0.2Sq"ACSR. 2no. | 188.72 58.00 | 246.72 | Work in progress, Dispute at T.no. 2,3 & 4 (Political Hindrance)(Rana Gurjit) | 2022-23 |  | 175 | 71.72
13 | 31/NZ/2022-23 /Annex. A | NZ | HSP | 92 |  |  | addl | 66KV S/S Kandhala Jattan 1x20 KV 66/11 KV | Addl 6.3/8 MVA, 66/11 KV | 203.62 | 203.62 |  | Paddy 2023 |  | 143 | 60.62
14 | 33/NZ/2022-23 /Annex. A | NZ | HSP | 40 |  |  | new ss | a)66 KV S/S Kalyanpur (NEW) (Including 1 nos. 66KV line bay with line Isolators only) b)Proposed new 7.5km/ 0.2sq"/ SC on DC towers line T-off from existing Bhogpur— Kandhala Jattan line ckt. up to proposed site of Kalyanpur S/Stn. | 12.5MVA, P,T/F 66/11KV New 7.5km/0.2sq'' SC on DC Towers line. | 219.92 202.20 | 422.12 | Line work stands completed and Grid work in progress | 2022-23 | 160.12 | 183 | 79
15 | 37/NZ/2022-23 /Annex. A | NZ | NWSR |  | 2 |  | line | a)66KV Line from 66KVS/S Behram to Dosanj Kalan (New ) b) 66KV bays 1 No. at 66KV Behram 1 No. at 66KV Dosanj Kalan | 8 Km/ SC on DC line 0.2 Sq"ACSR. 2no. | 215.68 58.00 | 273.68 | Work in progress, Tower material required | Paddy 2023 |  | 192 | 81.68
16 | 38/NZ/2022-23 /Annex. A | NZ | HSP | 139 |  |  | line | a) 66KV Line from 66 KV S/S Garshankar-- 66KV S/S Saroya (existing 8.3kM/ 0.15sq'' Single ckt /HRP line) | Aug.of ACSR 8.3km with 0.2sq" by replacement of 0.15sq'' HRP line with SC on DC towers | 223.77 -25.07 | 198.7 | Work in Progress. Tower material required | Paddy 2023 |  | 140 | 58.7
17 | 39/NZ/2022-23 /Annex. A | NZ | KPT | 66 |  |  | line | a)66KV Line from 220 kv kotla Jangan-- 66KV Mallian (U/G) (existing5.840Km/0.2sq'' SC on DC line) | Stringing of 2nd ckt 5.840Km/ 0.2 Sq"ACSR. on existing SC on DC line to make Double ckt. line | 55.0128 | 55.0128 | work in progress | Paddy 2023 |  | 39 | 16.0128
18 | 40/NZ/2022-23 /Annex. A | NZ | HSP |  |  |  | line | 66 KV line from 220 KV S/s Mahilpur to 66 KV S/s Chabewal (existing 9.779 km/ 0. 2 sq."/ SC on DC tower line) | a) Stringing of 2nd ckt. 9.779 km/ 0.2sq."/on existing SC on DC 66KV tower line from 220 KV S/s Mahilpur to 66 KV S/s Chabewal. b) 66 KV bays 2 nos. (i) 1 no. bay at 66 KV S/s Chabewal shall be erected by PSPCL. (ii) 1 no. bay at 220 KV S/s Mahilpur to be erected by PSTCL. | 92.12 29.00 | 121.12 | Total Sagging done. | 2022-10-31 | 3.21 | 82 | 35.91
19 | 44/NZ/2022-23 /Annex. B | NZ | JAL | 36 |  |  | line | a) 66KV New Line from Alawalpur--- 66KV Tanda Road S/S b) 66 KV bays. | a) 5.450Km/DC on DC line 0.4 Sq"ACSR. b) 2 nos. | 373.71 58.00 | 431.71 | ROUTE PLAN UNDER APPROVAL Planning ammendment required sent to CE/TS vide 5561 dt 15.09.2017 | 2024-25 |  |  | 130 | 301.71
20 | 46/NZ/2022-23 /Annex. B | NZ | JAL | 76 |  |  | line | a)66KV Line from 33KV HSP Road--- 33KV Chiheru (New) ( To rep Rail pole line) | 10Km SC on DC 66KV line 0.2 Sq"/ACSR to replace existing 33KV rail pole line | 269.60 -30.20 | 239.4 | Not feasible. ROW Problem | 2023-24 |  | 72 | 167.4
21 | 47/NZ/2022-23 /Annex. B | NZ | KPT | 79 |  |  | line | 66KV line from 132 KV Nakodar---- Mehatpur (exist. 8.980km/ 0.15sq''/towers) | a)Stringing 9Km/0.2sq'' 2nd Ckt. On existing SC on DC towers line b)1.5Km /0.2sq'' 2nd Ckt. on existing SC on DC towers Solid tap on Nakodar--Mehsampur line up to Mehatpur | 84.78 14.13 | 98.91 | Planning needs to be change | 2022-23 |  | 70 | 28.91
22 | 48/NZ/2022-23 /Annex. B | NZ | JAL | 48 |  |  | line | 66KV new link line 1.2Km solid tap to tower no 7 to Kartarpur----Surgical (ckt.-1) up to 66 KV S/Stn. Leather Complex to provide 2nd 66KV power source to 66KV Leather Complex Jalandhar, (exist 630mm2/SC 2.7km,U/G cable) b) 66KV bays 1 No. at 66KV Leather Complex Jal. | a)1.2Km /0.4sq'' single Ckt. new SC on DC towers 1 No. | 62.21 29.00 | 91.21 | Planning needs to be change | 2022-23 |  | 60 | 31.21
23 | 49/NZ/2022-23 /Annex. B | NZ | KPT |  | 82 |  | line | a) 66KV Line from 132KV S/S Kapurthala to Kala Sanghian (Exist.13.578Km Rail Pole line/0.15sq'' ) | Aug.of ACSR 13.578km with 0.2sq"by replacement of HRP line with SC on DC towers | 366.06 -41.01 | 325.05 | Roue under finalization Planning amendment required for UG cable
24 | 50/NZ/2022-23 /Annex. B | NZ | JAL | 74 |  |  | line | a)66KV Line from 33KV Banga Road--- 33KV HSP Road Phgwara (NEW) ( To rep Rail pole line) | 2.4 Km/ SC on DC line 0.2 Sq"ACSR. | 64.704 | 64.704 | i) Line completed ii) 2 bays amendment | 2023-24 |  | 20 | 44.704
25 | 51/NZ/2022-23 /Annex. B | NZ | NWSR | 94 |  |  | line | a)66KV line from 132KV Nawanshar-- 66KVGarshankar (Aug) (ckt1=11.3Km/0.15sq'' ckt2=11.3Km/0.15sq'' & 0.2sq'' both ckts on towers) | Stringing of one ckt 11.5 Km/ DC on DC line 0.2 Sq"ACSR. | 108.33 | 108.33 | Retendering to be done | Paddy 2023 |  | 76 | 32.33
26 | 52/NZ/2022-23 /Annex. B | NZ | NWSR |  |  | 59 | line | i) 66KV Line from 220KV S/S Jadla to 66KV S/S Karawar (Existing 8.33Km/0.15sq'' SC on SC 66KV line) ii) Replacement of existing isolator arrangement at 66KV S/S Karawar iii) 1No. New I/C 66KV line bay (with 66KV circuit breaker) at 66KV S/S Karawar iv) Replacement of existing isolator arrangement at 66KV S/S Bhaddi v) 1No. O/G 66KV line bay (with 66KV circuit breaker) at 220KV S/S Jadla | i) Replacement of existing SC on SC/0.15sq''/8.33Km with DC on DC 66KV line 0.2sq''/8.33Km line ii) Replacement of existing isolator arrangement at 66KV S/S Karawar for existing I/C Jadla line with 1 no. I/C 66KV line bay with circuit breaker iii) 1No. I/C 66KV line bay (with 66KV circuit breaker) at 66KV S/S Karawar iv) Replacement of existing isolator arrangement at 66KV S/S Bhaddi for existing I/C Karawar line with 1 no. I/C 66KV line bay with circuit breaker To be planned by PSTCL | 303.13 22.10 29.00 22.10 | 376.33 | Route plan under approval | 2023-24 |  | 113 | 263.33
27 | 55/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | a) 66KV line from 66 KV Sadhu Ashram to Chabewal b) 66KV line from 66KV S/S Ajjowal to Sadhu Ashram to 66KV S/S Chabewal c) 66KV Bays 2nos. at Sadhu Ashram 1 nos. at Ajjowal 1 nos. at Chabewal | a) 9.787KM/0.2 sq'' SC on DC towers b) 7.711 KM/0.2 sq'' SC on DC towers c)4 nos | 263.86 207.89 116.00 | 587.75 | TO BE COVERED UNDER APDRP Court case being defended by APDRP | 2025-26 |  |  |  | 177 | 410.75
28 | 56/NZ/2022-23 /Annex. B | NZ | NWSR |  |  |  | aug | 66 KV Mola Wahidpur 1x12.5 MVA 66/11 KV 1x6.3/8MVA 66/11 KV | 1x12.5 MVA, 66/11 KV to repl. 1x6.3/8MVA, 66/11 KV | 85.92 | 85.92 |  | Paddy 2023 |  | 61 | 24.92
29 | 57/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | aug | 66 KV Soosan 1x12.5 MVA, 66/11 KV 1x6.3/8MVA 66/11 KV | 1x12.5 MVA, 66/11 KV to repl. 1x6.3/8MVA, 66/11 KV | 85.92 | 85.92 |  | Paddy 2023 |  | 61 | 24.92
30 | 58/NZ/2022-23 /Annex. B | NZ | JAL |  |  | 21 | aug | 66 KV S/Stn. Sarhali Jalandhar T-1 having Capacity 12.5MVA | Augmentation of 12.5 MVA Power T/F T-1 with 20 MVA | 157.04 | 157.04 |  | 2023-24 |  | 48 | 109.04
31 | 59/NZ/2022-23 /Annex. B | NZ | NWSR |  |  |  | addl | 66 KV S/S Dalewal Nawanshahar T-1 having Capacity 6.3/8 MVA | Additional Power T/F (6.3/8 MVA) | 203.62 | 203.62 |  | Paddy 2023 |  | 143 | 60.62
32 | 60/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | aug | 66 KV S/Stn. Hariana Hoshiarpur T-1 & T-2 having Capacity 20MVA and 12.5MVA | Augmentation of Power T/F T-2 Capacity 12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2023-24 |  | 48 | 109.04
33 | 61/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | aug | 66KV S/Stn. Dasuya Hoshiarpur T-1 & T-2 having Capacity 20MVA | Augmentation of 20 MVA Power T/F T-1 with 31.5 MVA | 199.78 | 199.78 |  | 2023-24 |  | 60 | 139.78
34 | 62/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | aug | 66 KV S/Stn. Miani Hoshiarpur T-1 & T-2 having Capacity 12.5MVA and 12.5MVA | Augmentation of Power T/F T-2 Capacity 12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2023-24 |  | 48 | 109.04
35 | 63/NZ/2022-23 /Annex. B | NZ | NWSR |  |  |  | addl | 66 KV S/Stn. Kathgarh, Nawanshahar T-1 having Capacity 20 MVA | Additional Power T/F (6.3/8 MVA) | 203.62 | 203.62 |  | Paddy 2023 |  | 143 | 60.62
36 | 65/NZ/2022-23 /Annex. B | NZ | JAL |  |  |  | line | Replacement of existing 66 KV RHP line from 220 KV S/Stn. Alawalpur to 66 KV S/Stn. Adampur | (i) Replacement of existing 66 KV 8.3 KM RHP line, line with 0.2sq" DC/DC tower line on the same ROW. (ii) 66 KV Bays (2 Nos.) 1 no. at 66KV S/S Adampur & 1 nos. at 220KV S/S Alawalpur (to be planned by PSTCL) | 302.04 -25.07 29.00 | 305.97 |  | Paddy 2023 |  | 215 | 90.97
37 | 66/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | Augmentation of ACSR of RHP line line from 66KV S/Stn. Nasrala to deading tower of 220KV S/S Hoshiarpur to Sham Churasi | Augmentation of ACSR 0.15sq" inch to 0.2sq" SC on DC 4KM. | 107.84 | 107.84 |  | Paddy 2023 |  | 76 | 31.84
38 | 67/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | Augmentation of Existing 66kv Mukerian- Hajipur Rail H Pole Line | i) Existing RHP Line from A to B (length 2.5 Km, Conductor size 0.15 sq. inch) will be converted into DC-DC Tower Line with 0.2 sq. inch conductor on the same row. ii) Stringing of 2nd circuit of existing in the same Row B to C (length 1 KM conductor size 0.2 sq. inch (SC-DC Line) will be carried out as per proposal. iii) Existing RHP Line from C to C' (length 0.5 KM, conductor size 0.15 sq") will be converted into DC-DC tower line with 0.2 sq" conductor on same row. | 90.98 -7.55 9.42 18.20 1.51 | 112.56 |  | 2023-24 |  | 34 | 78.56
39 | 68/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | Augmentation of Existing 66kv Mahilpur- Kot Ftuhi Rail H Pole Line | Replacement of existing 66kv Mahilpur- Kot ftuhi RHP Line ( Conductor size 0.1 sq") by SC/DC tower Line with 0.2sq" Conductor in the same R.O.W, Length= 12.5km. | 337.00 -37.75 | 299.25 |  | 2023-24 |  | 90 | 209.25
40 | 69/NZ/2022-23 /Annex. B | NZ | JAL |  |  |  | line | 66 KV SC/DC line from 220 KV Rehana Jattan | (i) Stringing of 2nd ckt on existing 66 KV Rehana Jattan- Patara SC/DC, 13.40 KM 0.2 sq" line and further solid tapped with 66 KV SC/DC line, 4.50 KM 0.2 sq" for 66 KV Daroli Kalan for creating dual supply source to both the sub-stations. (ii) 66 KV Bays (3 No.) 1 no. 66 KV Bays at 66 KV S/S Daroli Kalan and 1 no. at 66 KV S/s Patara 1 no. 66 KV bay at 220 KV S/S Rehana Jattan (to be planned by PSTCL) | 126.23 121.32 58.00 | 305.55 |  | 2023-24 |  | 92 | 213.55
41 | 70/NZ/2022-23 /Annex. B | NZ | KAP |  |  |  | line | i) 66 KV SC/DC line from 220 KV S/Stn. Kartarpur ii) 66 KV RHP line from 220 KV S/Stn. Kartarpur | (i) New 66 KV SC/DC 0.2 sq", 5.5 KM link line from 220 KV S/Stn. Alawalpur to 66 KV S/Stn. Naugajja & further 66 KV SC/DC 0.2 sq", 6.5 KM line from 66 KV S/Stn. Naugajja to 66 KV S/Stn. Mustfapur. (ii) 66 KV Bays (4 No.) 2 no bay at 66 KV S/s Naugajja 1no. bay at 66 KV S/s Mustfapur 1 no. bays at 132 KV S/S Alawalpur (to be planned by PSTCL) | 148.28 175.24 87.00 | 410.52 |  | 2023-24 |  | 124 | 286.52
42 | 71/NZ/2022-23 /Annex. B | NZ | KAP |  |  |  | line | 66 KV RHP Line from 220 KV S/Stn. Nurmehal | (i) New 66 KV SC/DC 0.2 sq", 7.00 KM link line from 66 KV S/Stn. Bilga to 66 KV S/Stn. Talwan (ii) 01 No. 66 KV Bay at 66 KV S/Stn. Talwan (iii) 1 No. LE Switch at 66 KV S/Stn. Bilga | 188.72 29.00 14.00 | 231.72 |  | 2024-25 |  |  | 70 | 161.72
43 | 72/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | 66 KV RHP Line from 220 KV S/Stn. Dasuya | (i) New 66 KV SC/DC 0.2 sq", 8.00 KM link line from 66 KV S/Stn. Begowal to 66 KV S/Stn. Miani (ii) 66 KV Bays (2 No.) 1 no. at 66 KV S/s Miani & 1 no. at 66 KV S/s Begowal | 215.68 58.00 | 273.68 |  | 2024-25 |  |  | 83 | 190.68
44 | 73/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | 66 KV SC/DC Line from 66 KV S/Stn. Mustfapur | (i) New 66 KV SC/DC 0.2 sq", 10.00 KM link line from 66 KV S/Stn. Kala Bakra to 66 KV S/Stn. Ghug (ii) 66 KV Bays (2 No.) 1 no. at 66 KV S/s Kala Bakra & 1 no. at 66 KV S/s Ghug | 269.60 58.00 | 327.6 |  | 2024-25 |  |  | 99 | 228.6
45 | 74/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | 66 KV SC/DC Line from 220 KV S/Stn. Dasuya | (i) New 66 KV SC/DC 0.2 sq", 9.00 KM link line from 66 KV S/Stn. Kandhala Jattan to 66 KV S/Stn. Khun Khun Kalan (ii) 66 KV Bays (2 No.) 1 no. 66 KV bays at 66 KV S/s Kandhala Jattan and 1 no. at 66 KV S/s Khun Khun Kalan | 242.64 58.00 | 300.64 |  | 2023-24 |  | 91 | 209.64
46 | 75/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | line | 66 KV SC/DC Line from 220 KV S/Stn. Hoshiarpur | (i) New 66 KV DC/DC 0.2 sq", 14.50 KM link line from 66 KV S/Stn. Bullowal to 66 KV S/Stn. Lachowal (ii) 66 KV Bays (2 No.) 1 no. at 66 KV bay at 66 KV S/s Bullowal and 1 no. at 66 KV S/s Lachowal | 390.92 58.00 | 448.92 |  | 2024-25 |  |  | 135 | 313.92
47 | 76/NZ/2022-23 /Annex. B | NZ | NWSR |  |  |  | line | 66 KV SC/DC Line from 132 KV S/Stn. Phillaur | (i) New 66 KV SC/DC 0.2 sq", 7.00 KM link line from 66 KV S/Stn. Apra to 66 KV S/Stn. Dhak Bansian (ii) 1 No. 66 KV Bays at 66 KV S/Stn. Dhak Bansian | 188.72 29.00 | 217.72 |  | 2023-24 |  | 66 | 151.72
48 | 77/NZ/2022-23 /Annex. B | NZ | NWSR |  |  |  | new ss | a) 66 KV Pathlawa (including 1 No. 66 KV Bay) b) 66kV line from 220KV Banga Molawahidpur line c) 66KV Bays | 1x20 MVA, 66/11 KV b) Stringing of 2nd circuit of 6 Km/0.2 sq.” on the existing SC on DC Towers i.e. Upto tower no.19 of 66 KV Banga- Molawahidpur line. c) 0.2 sq.”/6 Km, construction of new link of 66 KV of SC on DC Towers up to the proposed site of 66 KV Pathlawa (1 No. at 220 KV S/Stn Banga to be planned by PSTCL) | 302.53 56.52 161.76 | 520.81 | Layout plan yet to be issued. | 2023-24 |  | 157 | 363.81
49 | 78/NZ/2022-23 /Annex. B | NZ | KPT |  |  |  | new ss | a) 66 KV Bhagatpur (including 1 No. 66 KV Bay) b) 66kV line T-off from existing 66KV line from Hothian to Kapurthala | a) 1x20 MVA, 66/11 KV b) Erection of 0.2 sq.” 1.5 Km, new link of 66 KV SC on DC Towers up to the proposed site of 66 KV Bhagatpur tapped from existing 66KV line from Hothian to Kapurthala. | 302.53 40.44 | 342.97 | Layout plan yet to be issued. | 2024-25 |  |  | 103 | 239.97
50 | 79/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | new ss | a) 66 KV S/S Sansarpur (NEW) (including 1 No. 66 KV Bay) b) Proposed New 15 km/02.sq" SC on DC towers line from existing 66KV S/S Dasuya. c) 66 KV Line Bay | a) 6.3/8 MVA or 8/10 MVA, (as per availability), 66/11 KV b) New 15km/ 0.2sq’’ SC on DC Towers. 1 no. bay at 66 KV Dausya. | 219.92 404.40 29.00 | 653.32 | Layout Plan issued, bearing capacity got tested and civil design drawings awaited | 2023-24 |  | 196 | 457.32
51 | 80/NZ/2022-23 /Annex. B | NZ | HSP |  | 61 |  | aug | 66 KV S/s Kot Fatuhi 1x12.5 MVA 66/11KV, 1x20 MVA 66/11KV | 20 MVA to replace 12.5MVA 66/11KV | 157.04 | 157.04 |  | Paddy 2023 |  | 110 | 47.04
52 | 81/NZ/2022-23 /Annex. B | NZ | KPT |  | 28 |  | aug | 66 KV S/S Nadala (Aug) 1x12.5 MVA 66/11 KV, 1x10/12.5 MVA 66/11KV | 20MVA to repl. 12.5MVA, 66/11KV | 157.04 | 157.04 |  | Paddy 2023 |  | 110 | 47.04
53 | 82/NZ/2022-23 /Annex. B | NZ | HSP |  |  |  | aug | 66 KV S/S Nasrala 1x12.5 MVA 1x12.5 MVA, 66/11 KV | 1x12.5 MVA, 66/11 KV to replace with 20 MVA, 66/11 KV | 157.04 | 157.04 |  | Paddy 2023 |  | 110 | 47.04
54 | 86/NZ/2022-23 /Shifted from Annex.C to B vide Amendment no. 03/2022-23 dated 30.06.2022 | NZ | JLD |  | 73 |  | aug | 66 KV S&SC, JLD (Aug.) 2x20 MVA 66/11 KV 1x31.5 MVA 66/11 KV | 2nd 31.5 MVA to repl. 20 MVA,66/11 KV | 199.78 | 199.78 |  | 2023-24 |  | 60 | 139.78
55 | 83/NZ/2022-23 /Annex.C | NZ | KPT | 115 |  |  | aug | 66 KV Shankar 1x20 KV 66/11 KV 1x12.5 MVA 66/11 KV | 20 MVA to repl.12.5 MVA, 66/11 KV | 157.04 | 157.04 |  | 2023-24 |  | 48 | 109.04
56 | 84/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66 KV Attowal 1x20 KV 66/11 KV 1x12.5 MVA 66/11 KV | 20 MVA to repl.12.5MVA 66/11 KV | 157.04 | 157.04 |  | 2023-24 |  | 48 | 109.04
57 | 85/NZ/2022-23 /Annex.C | NZ | KPT |  | 43 |  | aug | 66KV Begowal (Aug.) 2x12.5MVA,66/11KV | 20 MVA to repl. 12.5MVA,66/11 KV | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
58 | 87/NZ/2022-23 /Annex.C | NZ | KPT |  | 68 |  | aug | 66KV Bilga (Aug.) 1x20 KV 66/11 KV 1x12.5 MVA 66/11 KV | 20MVA to rep. 12.5MVA,66/11 KV | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
59 | 88/NZ/2022-23 /Annex.C | NZ | KPT |  |  | 42 | line | a)66KV Line from Sultanpur--- Jakhopur line LILO at 66KV S/S Lohian Kalan (New link) b) 66KV bays 2 No. at 66KV Lohian Kalan | 0.4Km/ DC on DC towers line/0.2 Sq" ACSR at 66KV S/S Lohian Kalan for LILO 2no. | 14.56 58.00 | 72.56 |  | Paddy 2023 |  | 51 | 21.56
60 | 89/NZ/2022-23 /Annex.C | NZ | KAP |  |  | 49 | aug | 66 KV S/Stn. Dainwind under P&M Division, PSPCL, Kapurthala T-1 & T-2 having Capacity 12.5MVA and 20MVA | Augment the Power T/F T-1 Capacity 12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
61 | 90/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66KV S/Stn. Ghug Hoshiarpur T-1 having Capacity 6.3/8MVA | Augmentation of 6.3/8MVA P/T/F with 12.5MVA | 85.92 | 85.92 |  | 2024-25 |  |  | 26 | 59.92
62 | 91/NZ/2022-23 /Annex.C | NZ | NWSR |  |  |  | addl | 66 KV S/Stn. Bhaddi Nawanshahar T-1 having Capacity 12.5MVA | Additional Power T/F (6.3/8 MVA ) | 203.62 | 203.62 |  | 2024-25 |  |  | 62 | 141.62
63 | 92/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | addl | 66KV S/Stn. Hazipur Hoshiarpur T-1 having Capacity 20MVA | Additional 12.5 MVA P/T/F | 203.62 | 203.62 |  | 2024-25 |  |  | 62 | 141.62
64 | 93/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | aug | 66 KV S/Stn. Samrai Kapurthala T-1, & T-2 having Capacity 6.3/8MVA and 20MVA | Augmentation of Power T/F T1 Capacity 6.3/8 MVA with 12.5 MVA | 85.92 | 85.92 |  | 2023-24 |  | 26 | 59.92
65 | 94/NZ/2022-23 /Annex.C | NZ | NWSR |  |  |  | addl | 66 KV S/Stn. Balachaur Nawanshahar T-1 & T-2 having Capacity 20MVA | Additional Power T/F, 66 KV/11 KV, 12.5 MVA | 203.62 | 203.62 |  | 2024-25 |  |  | 62 | 141.62
66 | 95/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66 KV S/Stn. Chabbewal Hoshiarpur T-1 & T-2 having Capacity 20MVA | Augmentation of Power T/F T-1 Capacity 20 MVA with 31.5 MVA | 199.78 | 199.78 |  | 2024-25 |  |  | 60 | 139.78
67 | 96/NZ/2022-23 /Annex. C | NZ | JAL |  |  |  | aug | 66 KV S/Stn.Tanda road Jalandhar T-1, T-2, T-3 & T-4 having Capacity 20MVA, 20MVA, 20MVA & 31.5MVA | Augmentation of Power T/F T-3 20 MVA with 31.5 MVA | 199.78 | 199.78 |  | 2022-23 |  | 140 | 59.78
68 | 97/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | aug | 66 KV S/Stn.Babrik Chowk, Jalandhar T-1 having Capacity 20MVA | Augmentation of 20 MVA Power T/F T-1 with 31.5 MVA | 199.78 | 199.78 |  | 2024-25 |  |  | 60 | 139.78
69 | 98/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | addl | 66KV S/Stn. Ghogra Hoshiarpur T-1 having Capacity 20MVA | Additional 12.5MVA P-T/F | 203.62 | 203.62 |  | 2024-25 |  |  | 62 | 141.62
70 | 99/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | aug | 66 KV S/Stn. Bhago Budha, Kapurthala T-1 & T-2 having Capacity 12.5MVA and 20MVA | Augmentation of Power T/F T-1 Capacity 12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
71 | 100/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66 KV S/Stn. Garhdiwala, Hoshiarpur T-1 & T-2 having Capacity 20MVA | Augmentation of Power T/F T-2 Capacity 20 MVA with 31.5 MVA | 199.78 | 199.78 |  | 2024-25 |  |  | 60 | 139.78
72 | 101/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66KV S/Stn. Jaijon Doaba Hoshiarpur T-1 having Capacity 12.5MVA | Augmentation of 12.5MVA with 20MVA P-T/F | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
73 | 102/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | aug | 66KV Substation,Leather Complex, PSPCL, Jalandhar T-1 & T-2 having Capacity 20MVA | Augmentation of T-1 20MVA with 31.5 P-T/F | 199.78 | 199.78 |  | 2024-25 |  |  | 60 | 139.78
74 | 103/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | aug | 66 KV S/Stn. Ucha, Kapurthala T-1 & T-2 having Capacity 12.5MVA & 6.3/8MVA | Augmentation of Power T/F T-2 Capacity 6.3/8 MVA with 12.5 MVA | 85.92 | 85.92 |  | 2024-25 |  |  | 26 | 59.92
75 | 104/NZ/2022-23 /Annex.C | NZ | NWSR |  |  |  | aug | 66 KV S/Stn. Aur, Nawanshahar T-1 & T-2 having Capacity 12.5MVA and 20MVA | Augmentation of Power T/F T-1, 66 KV/11 KV, 12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
76 | 105/NZ/2022-23 /Annex.C | NZ | HSP |  |  | 4 | aug | 66 KV S/Stn. Bullowal Hoshiarpur T-1 & T-2 having Capacity 12.5MVA and 12.5MVA | Augmentation of Power T/F T-2 Capacity 12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
77 | 106/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | aug | 66 KV S/Stn. Hoshiarpur road, Phagwara, Jalandhar T-1 & T-2 having Capacity 12.5MVA and 20MVA | Augmentation of 12.5 MVA Power T/F T-1 with 20 MVA | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
78 | 107/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | aug | 66 KV S/Stn. Radial Jalandhar T-1, T-2 & T-3 having Capacity 20MVA, 20MVA and 12.5MVA | Augmentation of 12.5 MVA Power T/F T-3 with 20 MVA | 157.04 | 157.04 |  | 2023-24 |  | 48 | 109.04
79 | 108/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | aug | 66 KV S/Stn. Sports & Surgical Complex Jalandhar T-1, T-2 & T-3 having Capacity 20MVA, 20MVA and 31.5MVA (70/NZ/2020-21 & 2021-22/ Annex-C) | Augmentation of Power T/F T-2 Capacity 20 MVA with 31.5 MVA | 199.78 | 199.78 |  | To be deleted
80 | 109/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66 KV S/Stn. Saila Khurd Hoshiarpur T-1, & T-2 having Capacity 20MVA and 10/12.5MVA | Augmentation of Power T/F T-2 Capacity 10/12.5 MVA with 20 MVA | 157.04 | 157.04 |  | 2024-25 |  |  | 48 | 109.04
81 | 110/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | aug | 66 KV S/Stn. Bham Hoshiarpur T-1 & T-2 having Capacity 12.5MVA and 6.3/8MVA | Augmentation of Power T/F T-2 Capacity 6.3/8 MVA with 12.5 MVA | 85.92 | 85.92 |  | 2024-25 |  |  | 26 | 59.92
82 | 111/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | line | Replacement of old idle rail pole line solid tapped from 66 KV BBMB- Barringa Ckt.-II, Jalandhar | (i) Replacement of old idle rail pole line 0.6 KM with 0.2sq" SC/DC tower line and replacement of ACSR 0.15sq" with 0.2sq" of existing 2.0 KM DC/DC tower line from 66 KV S/Stn. Barringa. (ii) 66 KV Bay (1 No. at 66KV S/S Barringa) | 88.96 -7.85 29.00 | 110.11 |  | 2023-24 |  | 34 | 76.11
83 | 112/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | line | 66 KV new line from 66KV S/S Pitara to 66KV S/S Chaheru | (i) New 66 KV SC/DC, new 66KV link 0.2sq" 8.50 KM link line from 66 KV S/Stn. Patara to 66 KV S/Stn. Chaheru (ii) 66 KV Bays (2 Nos.) 1 no. at 66KV Pitara and 1 no. at 66KV Chaheru | 229.16 58.00 | 287.16 |  | 2024-25 |  |  | 87 | 200.16
84 | 113/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | line | 66 KV RHP Line from 220 KV S/Stn. Nurmehal from 66 KV S/Stn. Bilga | (i) New 66 KV 0.2sq" SC/DC, 8.00 KM link line from 66 KV S/Stn. Muthada Khurd to 66 KV S/Stn. Bilga (ii) 66 KV Bays (2 No.) 1 no. at 66 KV S/Stn. Muthada and 1 no.66 KV S/Stn. Bilga | 215.68 58.00 | 273.68 |  | 2024-25 |  |  | 83 | 190.68
85 | 114/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | line | 66 KV line Solid tapped from 66KV Bhogpur- Bholath line | (i) LILO arrangement of 0.90 KM 66 KV 0.2sq", DC/DC on existing 66 KV RHP Line from Bhogpur-Begowal for 66KV S/S Chowk Bajaj. (ii) 66 KV Bays (2 No.) at 66KV S/S Chowk Bajaj | 32.75 58.00 | 90.75 |  | Paddy 2023 |  | 64 | 26.75
86 | 115/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | line | 66 KV SC/DC Line from 220 KV S/Stn. Nurmehal from 66 KV S/Stn.Samshabad | (i) LILO arrangement of 0.2 KM, 0.2sq", DC/DC existing 66 KV SC/DC Line from Nurmehal-Mehsampur for Shamshabad. (ii) 66 KV Bays (2 No.) at 66KV S/S Samsabad | 7.28 58.00 | 65.28 |  | 2024-25 |  |  | 20 | 45.28
87 | 116/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | line | 66 KV RHP Line from 220 KV S/Stn. Nurmehal to 66 KV S/Stn. Samrai | (i) New 66 KV 0.2sq" SC/DC, 7.00 KM link line from 66 KV S/Stn. Sarhali to 66 KV S/Stn. Samrai (ii) 01 No. 66 KV Bay at Samrai (iii) 1 No. LE Switch at 66 KV S/Stn. Sarhali | 188.72 29.00 14.00 | 231.72 |  | 2025-26 |  |  |  | 70 | 161.72
88 | 117/NZ/2022-23 /Annex.C | NZ | KAP |  |  |  | line | 66 KV SC/DC Line from 66 KV S/Stn. Mehatpur to 66 KV S/Stn. Parjian Kalan | (i) New 66 KV 0.2sq" SC/DC, 8.00 KM link line from 66 KV S/Stn. Bangiwal to 66 KV S/Stn. Parjian Kalan (ii) 66 KV Bays (2 No.) 1 no. at 66KV S/S Parjian and 1 no. at 66KV S/Stn. Bangiwal | 215.68 58.00 | 273.68 |  | 2025-26 |  |  |  | 83 | 190.68
89 | 118/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | line | LILO arrangement of 66 KV DC/DC existing 66 KV SC/DC Line from 132 KV S/Stn. Chohal to 66 KV S/Stn. Hariana for Ajjowal. | (i) LILO arrangement of 0.5 KM 66 KV 0.2sq" DC/DC existing 66 KV SC/DC Line from 132 KV S/Stn. Chohal to 66 KV S/Stn. Hariana for Ajjowal. (ii) 66 KV Bay (1 No.) at 66KV Ajjowal | 18.20 29.00 | 47.2 |  | Paddy 2023 |  | 34 | 13.2
90 | 119/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | line | LILO arrangement of 0.3 KM 66 KV DC/DC existing 66 KV Line from 220 KV S/Stn. Hoshiarpur to 66 KV S/Stn. Sadhu Ashram for Focal Point Hoshiarpur. | (i) LILO arrangement of 0.3 KM 66 KV 0.2sq" DC/DC existing 66 KV Line from 220 KV S/Stn. Hoshiarpur to 66 KV S/Stn. Sadhu Ashram for Focal Point Hoshiarpur. (ii) 66 KV Bays (2 No.) at 66 KV S/Stn. Focal Point Hoshiarpur | 10.92 58.00 | 68.92 |  | Paddy 2023 |  | 49 | 19.92
91 | 120/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | line | 66 KV SC/DC Line from 220 KV S/Stn. Mahilpur to 66 KV S/Stn. Bham | (i) New 66 KV 0.2sq" SC/DC, 6 KM link line from 66 KV S/Stn. Badla to 66 KV S/Stn. Bham (ii) 66 KV Bays (2 No.)1 no. at 66KV S/Stn. Badla and 1 no. at 66KV S/Stn. Bham | 161.76 58.00 | 219.76 |  | 2025-26 |  |  |  | 66 | 153.76
92 | 121/NZ/2022-23 /Annex.C | NZ | HSP |  |  |  | line | 66 KV SC/DC line tapped from 66 KV Bhogpur-Bullowal to 66 KV S/Stn. Soosan | (i) New 66 KV 0.2sq" SC/DC, 8.00 KM link line from 66 KV S/Stn. Sham Churasi to 66 KV S/Stn. Soosan (ii) 66 KV Bays (2 No.)1 no. at 66KV S/Stn. Sham Churasi and 1 no. at 66 KV S/Stn. Soosan | 215.68 58 | 273.68 |  | 2025-26 |  |  |  | 83 | 190.68
93 | 122/NZ/2022-23 /Annex.C | NZ | JAL |  |  |  | line | 66kv SC/DC Line Tapped from 66kv Alwalpur- Adampur to 66kv S/S Nangal Salala | 66kv 0.2sq" SC/DC, 8 KM Line from 66kv S/S Kala Bakra to 66kv S/S Nangal Salala | 215.68 | 215.68 |  | 2024-25 |  |  | 65 | 150.68
94 | 123/NZ/2022-23 /Annex. C | NZ | JAL |  |  | 17 | line | 66KV SC/DC line from 220KV S/S Badshahpur to 66KV S/S Chitti. | Stringing of 2nd circuit 0.2 sq" on existing 6.570 Km SC/DC line. 66KV bays.(2Nos.) 1No. each at 66KV S/S Badshahpur and 66KV S/S Chitti. | 61.89 58.00 | 119.89 |  | 2025-26 |  |  |  | 36 | 83.89
[14 empty] | 639.75 | 6346.39 | 6855.7068 | 4825.12 | 1191.48
|  |  |  | 14 | 7 | 7

## BZ
|  | BORDER ZONE | [12 empty] | Annexure-V
Sr.no. | TWL sr.no. 2022-23 | Zone | Circle Name | MYT 2020-21 | MT 2021-22 | MT 2022-23 | Name of Work | Scope of Work | Estt. Cost (in lacs) | Total Cost | Status | Year | Remarks | Expenditure upto 31.03.2022 (in lacs) | Expenditure in Year 2022-23 (in lacs) | Expenditure in Year 2023-24 (in lacs) | Expenditure in Year 2024-25 (in lacs) | Expenditure in Year 2025-26 (in lacs)
1 | 3/BZ/2022-23/ /Annex.A | BZ | GSP |  |  |  | a)66KV Bijliwal (NEW) b)66KV line from 220KV Kotli Surat Malli to Bijliwal | a)1x20 MVA 66/11 KV b)10/KM/0.2 sq" SC on DC towers | 302.53 269.60 | 572.13 | line charged on dtd. 28.03.15 from dera baba nanak.line forest clearance awaited | 2022-11-30 |  | 0.08 | 200 | 69.52
2 | 4/BZ/2022-23/ /Annex.A | BZ | S/U ASR |  |  |  | 66 KV line Bagga Kalan to Harsha Chinna (New) b) 66 KV bays 1 No. at 66 KV Bagga Kalan 1 No. at 66 KV Haarsha Chinna | 6KM/0.2sq"/SC on DC towers 2 Nos. | 161.76 58.00 | 219.76 | Work in progress | 2022-23 |  | 33.88 | 185.88
3 | 7/BZ/2022-23/ /Annex.A | BZ | ASR |  |  |  | Erection 2nd 66KV line ckt. from 220KV Naraingarh to 66KV Hall Gate a) From Tower no. 1 to 6 Multi ckt tower exists (1.4 km/0.2 sq") 2 ckts exists b) From Tower no. 6 to 33 Double ckt tower exists 6.75km/ 0.2 sq" c) From Tower no. 33 to 46 1.43km/0.2sq" on SC towers d) From Tower no. 46 to 55 66KV Cable 240mm2 (1.37km) e) From Tower no. 55 to 65 1.46km/0.2 sq" on SC towers f) From Goal Bagh to Hall Gate 66KV Cable 240mm2 (0.450km) g) 66 KV Bays 1 No. at 66 KV Hall Gate 1 No. at 220 KV Naraingarh | Stringing of 3rd ckt 1.4km/0.2sq" on existing multickt towers. Stringing of 3rd ckt 6.75km/0.2sq" after replacement of DC towers with multickt. towers. 1.43km,2nd ckt of 0.2sq" to be strung after replacement of SC towers with DC towers. Addl.66KV Cable SC 1.37km/ 240mm2 (Exist.66KV O/H line SC on SC to be retained) 1.46km/0.2 sq" DC on DC towers Addl.66KV Cable SC 0.450km/ 240mm2 to make 240mm2 U/G Cable D C 1 No. 1 No. (To be planned by PSTCL) | 9.83 522.72 -20.38 30.47 -4.32 186.32 41.38 -4.41 61.20 28.00 | 850.81 | NOC from MC and Army is required. Dispute 8-B, 8-C, Re-orient. of bay is required at N/G | 2022-23 |  | 72.38 | 545 | 233.43
4 | 8/BZ/2022-23/ /Annex.A | BZ | ASR |  |  |  | 66KV line from 220KV Patti to 220KV Chohla Sahib 18 KM/0.1sq"/HRP | a) Aug of ACSR 18 km with 0.2sq." by replacement of HRP line with DC on DC towers | 655.02 -54.36 | 600.66 | work completed. Bay pending at chola sahib | 2023-24 |  |  | 181 | 419.66
5 | 9/BZ/2022-23/ /Annex.A | BZ | TTN |  |  |  | a) 66KV line from 220KV S/S Khassa to 66KV S/S Attari (NEW) b) 66KV bays. 1 No. LE bay at 66 KV Attari 1 No. at 220 KV Khassa | a) Aug of ACSR 9.058km with 0.2 sq." by replacement of HRP line with DC on DC towers b) 0.168 ckt-Km 66KV U/G cable 240mm2 single ckt. (cable Already erected) 1 No. 1 No. (To be planned by PSTCL) | 329.62 -27.36 42.24 14.00 | 358.5 | Bay pending at Attari end, cable pending at AIR premises | 2022-23 |  | 6.99 | 245 | 106.51
6 | 10/BZ/2022-23/ /Annex.A | BZ | TTN |  |  |  | a) New 66 KV link line from 220 KV S/Stn Rashiana to existing 66 KV S/Stn. Khadur Sahib b) 66KV bays 1 No. at 66 KV Khadoor Sahib 1 No. at 220 KV Rashiana | a) 9KM/0.2sq" SC on DC Towers (New link line) 1 No. 1 No. (To be planned by PSTCL) | 242.64 29.00 | 271.64 | Work in progress. | 2022-23 |  | 16.2 | 175 | 80.44
7 | 11/BZ/2022-23/ Annex.A | BZ | TTN |  |  |  | a)66KV line from 220KV Patti-- 66KV Harike 17km. /0.1sq" on HRP Note:Existing RP line to be dismantled with the concurrence of CE/Operation (Border) Asr. | a)Stringing of 2nd ckt. 2km/0.2sq"on existing DC towers for 66 KV Patti --Toot Line b)13km/ 0.2sq" /SC on DC towers | 18.84 350.48 | 369.32 | WORK IN PROGRESS, STUBBING OF TNO. 11 HELD UP DUE TO SITE DISPUTE, Double Ckt sag between tower no. 1 to 11 is pending rest of the line is energized, Planning amendment sent | 2023-24 |  |  | 111 | 258.32
8 | 13/BZ/2022-23/ Annex.A | BZ | TTN |  |  |  | 66KV line from 220KV Rashiana to 66KV F.P TTN. 0.15sq''/HRP +0.2sq''/Towers b) 66KV bays 1 No. at 132 KV Tarn Taran 1 No. at 220 KV Tarn Taran | 10Km/0.2sq'' DC on DC towers upto 132 KV TaranTarn To be planned by PSTCL To be planned by PSTCL | 363.9 | 363.9 | Work in progress. | 2022-23 |  | 4.72 | 250 | 109.18
9 | 16/BZ/2022-23/ Annex.A | BZ | S/U ASR | 75 |  |  | 66KV Ram Dass---- Fatehgarh Churian 15.5 KM/0.125 Sq" HRP | 15.5 KM/0.2 Sq" SC on DC Towers as 2nd ckt | 417.88 | 417.88 | Work in progress | 2023-24 |  |  | 126 | 291.88
10 | 17/BZ/2022-23/ Annex.A | BZ | GSP | 11 |  |  | a) 66KV Line from 220KV Wadala Granthian--- 66KV Udho Nangal (Aug) | i) 18Km/ 0.2Sq" Aug.of ACSR on existing Tower line ii)Existing line Rusted Towers, to be replaced with new towers as below:- Tower no 17,19,29,33,35,37,59, Tower no 65,69=2 nos D-30 Tower no 51A =D-60 | 169.56 70.00 14.00 7.00 | 260.56 | Tendering under process | 2023-24 |  |  | 79 | 181.56
11 | 21/BZ/2022-23/ Annex.A | BZ | TTN | 67 |  |  | a) 66KV Line from 66KV S/S Amarkot --- 66KV S/S khemkaran 11Km/0.1Sq" / HRP line/ towers | Aug of ACSR 11 km with 0.2 sq" by replacement of HRP line with SC on DC towers | 296.56 -33.22 | 263.34 | Work in progress Bay work already completed. | 2022-23 |  | 131.63 | 92 | 39.71
12 | 24/BZ/2022-23/ Annex.A | BZ |  |  |  |  | a)66KV S/S Kot Dhandhal (NEW) (Including 1 nos. 66KV line bay with line Isolators only at new 66KV S/S Kot Dhandhal) b)5.9km /0.2sq"/SC on DC towers 66KV line,T-off from existing HRP 66KV line 0.125sq" from Tibber to 66KV Kahnuwan line circuit. | 1x12.5 MVA, 66/11 KV P,T/F New 5.9km/0.2sq" SC on DC towers line | 219.92 159.06 | 378.98 | Grid work in progress. Route for line work under approval | 2024-25 |  |  |  | 114 | 264.98
13 | 25/BZ/2022-23/ Annex.A | BZ | GSP |  |  |  | a) 66 KV S/s Thatha (New) b) Proposed feeding line: 4 km/0.2 sq. inch/ SC on DC new 66 KV line, T-off from 66 KV line Fatehgarh Churian- Majitha line upto the proposed site of new prop.66 KV S/s Thatha. | 1x6.3/8 MVA, 66/11 KV New 4 km/0.2 sq."/SC on DC 66 KV line | 219.92 107.84 | 327.76 | Tower line work is completed. only gantry span is pending. Only T/F awaited. | 2022-23 |  | 247.89 | 56 | 23.87
14 | 26/BZ/2022-23/ Annex.A | BZ | TTN |  | 20 |  | a) 66KV Line from 66 KV Chogawan --- 66KV kakkar 12.82Km/0.1/0.15Sq" HRP line/ towers | Aug of ACSR 13 km with 0.2 sq." by replacement of HRP line with SC on DC towers | 350.48 -39.26 | 311.22 | work is in progress | 2023-24 |  |  | 94 | 217.22
15 | 27/BZ/2022-23/ Annex.A | BZ | GSP | 71 |  |  | a) 66KV Line from 132KV Sarna to 66KV S/S Dina nagar(Toll plaza Jakolari rail pole no 71 to 149) 9Km/0.125Sq" /HRP line Note:- Rail pole no 1 to 70 already replaced with SC on DC towers line | Aug of ACSR 9 km with 0.2sq" by replacement of HRP line (RP 71 to149) with SC on DC towers | 242.64 -27.18 | 215.46 | Work in progress | Paddy 2023 |  |  | 151 | 64.46
16 | 28/BZ/2022-23/ Annex.A | BZ | ASR |  | 34 |  | a)66KV line from 220KV Majitha---Nag Kalan, Mudal SC on DC line & Mudal to Verka HRP Link line b) 66KV bays. 1 No. at 66 KV Nag Kalan 1 No. at 220 KV Majitha | 2ndCircuit 12.864 Km/0.2Sq" ACSR. on DC towers line . 1 No. To be planned by PSTCL | 121.18 29.00 | 150.18 | Majitha - Nag kalan & Nag kalan - Mudhal completed
17 | 29/BZ/2022-23/ Annex.A | BZ | TTN |  | 85 |  | a) 66KV Line from 220kv Chohla Sahib to 66KV Gandiwind (NEW) b) 66KV Bays 1 No. at 66 KV Gandiwind 1 No. at 220 KV Chola Sahib | a)5.766 Km / 0.2 Sq" ACSR Stringing of 2nd Ckt on DC towers of existing line. 1 No. To be planned by PSTCL | 54.32 29.00 | 83.32 | Work completed. Bays pending at both ends |  |  | 5.19 | 78.13
18 | 31/BZ/2022-23/ Annex.B | BZ | GSP |  | 67 |  | 66KV Batala Radial--220KV Wadala Granthian line 11 KM/0.125sq''/RP line | a)Repl.of 66KV RP line between 220KV Wadala Granthian--- 132KV Batala line with 3 KM/ 0.2Sq" SC on DC Towers. b)Repl. of existing T- off Line for 66 KV Batala City 7KM/0.2 Sq" SC on DC Towers | 80.88 -9.06 188.72 -21.14 | 239.4 | Route survey under approval | Paddy 2023 |  |  | 168 | 71.4
19 | 32/BZ/2022-23/ Annex.B | BZ | TTN | 69 |  |  | a) 66KV line from 220KV Patti to 66KV Toot 17KM/0.2sq''/ SC on DC line b) 66KV Bay 1 No. at 66 KV Toot 1 No. at 220 KV Patti | Stringing of 2nd Ckt.17Km/ 0.2sq'' on existing DC towers line in order to make DC on DC towers line | 160.14 29.00 | 189.14 | Planning amendment required | Paddy 2023 |  |  | 133 | 56.14
20 | 33/BZ/2022-23/ Annex.B | BZ | S/U ASR | 85 |  |  | 66KV line from 132KV Kathunangal to 66KV Nawanpind 10KM/0.1sq''/ HRP | Aug of ACSR 10 km with 0.2 sq." by replacement of HRP line with SC on DC towers Line | 269.60 -30.20 | 239.4 | Survey done | 2024-25 |  |  |  | 72 | 167.4
21 | 35/BZ/2022-23/ Annex.B | BZ | TTN | 78 |  |  | a) 66KV Line from 132KV Kathunangal to Tarsika 7Km/0.15Sq" /HRP line | Aug of ACSR 4.1 km with 0.2 sq." by replacement of HRP line ( RP 44 to 105) with SC on DC towers | 110.54 -12.38 | 98.16 | Survey done | 2024-25 |  |  |  | 30 | 68.16
22 | 36/BZ/2022-23/ Annex.B | BZ | TTN | 100 |  |  | a) 66KV Line from 132KVS/S Bhikhiwind to Sur Singh/Gagobua 7.990Km/0.2Sq"/SC on DC tower line b) 66 KV Bays 1 No. at 66 KV Sur Singh 1 No. at 132 KV Bhikhiwind | a)Stringing of 2nd Ckt/ 0.2Sq" 7Km ACSR on existing DC Towers Bhikhiwind to SurSingh portion to make DC on DC line 1 No. To be planned by PSTCL | 65.94 29.00 | 94.94 | Planning amendment required | 2023-24 |  |  | 29 | 65.94
23 | 37/BZ/2022-23/ Annex.B | BZ | GSP |  | 107 |  | a) 66KV Line from 220KV Tibber to 66KV Kahnuwan 0.460+7Km/0.125Sq"/ exist.HRP line | i)New7Km/0.2Sq"/SC on DC towers line from T-off point of this line near Tibber to 66KV S/S Kahnuwan to replace existing rail pole line ii)New 0.460Km/0.2Sq"/DConDC towers line from 220KV S/S Tibber to T-off point of Babehali & Kahnuwan line 1 ckt for Kahnuwan & 1 ckt for Babehali to replace existing rail pole line | 188.72 -21.14 16.74 -1.39 | 182.93 | Route under approval | 2023-24 |  |  | 55 | 127.93
24 | 38/BZ/2022-23/ Annex.B | BZ | ASR |  | 3 |  | a) 66KV Nawan Pind --- Focal Point, Mehta Road, Vallah new Link line b) 66KV bays. 1 No. at 66 KV Nawan Pind 1 No. at 66 KV Focal Point | 10KM/0.2Sq"ACSR./ SC on DC towers link line 2 Nos. | 269.60 29.00 29.00 | 327.6 | Route under approval | 2023-24 |  |  | 99 | 228.6
25 | 39/BZ/2022-23/ Annex.B | BZ | ASR |  | 14 |  | 66 KV line from 220 KV Khasa to 66KV Sarai Amanat Khan (NEW) 15.27KM/ 0.15sq” HRP line/ 0.2sq” towers (47/BZ/ 2020-21 & 2021-22/ Annex-B) | Augmentation of ACSR 15.270 KM with 0.2sq” by replacement of HRP line with SC on DC tower and erection of 3no. Multi ckt towers at 220KV Khasa end including dismantlement of 2no. Existing DC towers. | 411.68 -46.12 196.38 | 561.94 | Survey under process | 2024-25 |  |  |  | 169 | 392.94
26 | 40/BZ/2022-23/ Annex.B | BZ | GSP |  |  |  | a) 66KV line from 132 KV S/Stn. Gurdaspur to 66 KV Jaura Chhitran existing SC on DC towers line 0.2sq''/10.3Km b) 66KV line bays | a) Stringing of 2nd circuit 10.3 km/0.2sq'' on existing SC on DC towers from 132 KV Gurdaspur to 66 KV Jaura Chhitran b) 1 no. 66 KV bay at 66 KV S/s Jaura Chhitran. Note:- 1 no. 66 KV bay at 132 KV S/s Gurdaspur shall be planned by PSTCL. | 97.03 29.00 | 126.03 |  | Paddy 2023 |  |  | 89 | 37.03
27 | 41/BZ/2022-23/ Annex.B | BZ | TTN |  |  | 14 | a) 66KV Line from 132KV Tarntaran to 66 KV Manochahal/Jhamka 13Km/0.15 sq" /HRP line | a) Aug of ACSR 11 km with 0.2 sq." (from tower no 9 upto manochahal) with SC on DC towers by replacement of existing 0.15 sq''/11Km HRP line on the same right of way | 296.56 -33.22 | 263.34 |  | 2024-25 |  |  |  | 80 | 183.34
28 | 42/BZ/2022-23/ Annex.B | BZ | GSP |  |  |  | a) 66KV New line from 220 KV S/s Tibber to 66 KV S/s Ranjit Bagh/Purana Shalla upto village Bhulle Chak (on RoW adjoining to existing DC on DC line) b) 66KV bays. 1 No. at 66 KV bay at 220 KV S/s Tibber (to be planned by PSTCL) | 8 KM/0.2Sq"ACSR on SC on DC towers link line 1 No. at 66 KV bay at 220 KV S/s Tibber (to be planned by PSTCL) | 215.68 | 215.68 |  | 2023-24 |  |  | 65 | 150.68
29 | 43/BZ/2022-23/ Annex.B | BZ | TTN |  |  |  | 66 KV Sub Station Deo-Bath T-1 having capacity of 12.5 MVA | Augmentation of Power T/F, 12.5 MVA with 20MVA | 157.04 | 157.04 |  | Paddy 2023 |  |  | 110 | 47.04
30 | 44/BZ/2022- 23/Annex.B | BZ | S/U ASR |  |  |  | 66 KV Sub Station Dhadhe T-1 having capacity of 12.5 MVA | Augmentation of Power T/F, 12.5 MVA with 20MVA | 157.04 | 157.04 |  | 2023-24 |  |  | 48 | 109.04
31 | 45/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 66 KV Sub Station Improvement Trust Gurdaspur T-1 having capacity of 12.5 MVA | Augmentation of Power T/F , 12.5 MVA to 20 MVA | 157.04 | 157.04 |  | 2022-23 |  |  | 157.04
32 | 46/BZ/2022- 23/Annex.B | BZ | S/U ASR |  |  |  | 66 KV Sub Station Jasterwal T-1 and T-2 having capacity of 12.5 MVA and 20 MVA | Augmentation of Power T/F T-1, 12.5 MVA to 20 MVA | 157.04 | 157.04 |  | Paddy 2023 |  |  | 110 | 47.04
33 | 47/BZ/2022- 23/Annex.B | BZ | TTN |  | 119 |  | 66 KV Sub Station Kacha Pakka T-1 and T-2 having capacity of 20 MVA and 20 MVA | Addl. Power T/F, 12.5 MVA | 203.62 | 203.62 |  | Paddy 2023 |  |  | 143 | 60.62
34 | 48/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 66 KV Sub Station Shehzada Kalan T-1 having capacity of 12.5 MVA | Additional Power T/F, 12.5 MVA | 203.62 | 203.62 |  | Paddy 2023 |  |  | 143 | 60.62
35 | 49/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | New 66 kv line from 132 kv s/stn Batala to 66 kv Jaura Singha on SC on DC towers 0.2 sq. inch, having length of approx. 7 km along with new 1 no. Bay at 66 kv s/stn Jaura Singha and 1 no. at 132 kv s/s Batala | A). Erection and stringing of new 66 KV link line, 10 KM SC on DC towers with ACSR 0.2 Sq inch between 132 KV S/Stn. Batala and 66 KV S/Stn. Jaura Singha. B). 66 kv Bays for new link line. i) 1 no. at 66 KV Jaura Singha. ii) 1 no. at 132 KV Batala to be planned by PSTCL. | 269.60 29.00 | 298.6 |  | 2024-25 |  |  |  | 90 | 208.6
36 | 50/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 1) Erection & Stringing a new 66 KV link line between 66 KV S/Stn. Dinanagar to 66 KV S/Stn Bahmani approx.. length 11.5 KM on SC on DC towers along with 2 No. 66 KV bays at 66 KV Dinanagar and 66 KV Bahmani. | A) Erection & Stringing of new 66 KV link line from 66 kv S/Stn. Dinanagar to 66 KV S/Stn. Bahmani, approx. length of 11.5 km 0.2 sq" on SC on DC towers. (Point C to D) B) 2 no. 66 kv Bays for new link line at 66 KV S/stn Dinanagar and 66 KV S/stn Bahmani. | 310.04 58.00 | 368.04 |  | 2023-24 |  |  | 111 | 257.04
37 | 51/BZ/2022- 23/Annex.B | BZ | S/U ASR |  |  |  | New 66 kv line from 66 kv s/stn Jasterwal to 66 kv Ajnala on SC on DC towers 0.2 sq. inch, having length of approx. 10 km along with new 1 no. Bay at 66 kv s/stn Jasterwal and 1 no. at 66 KV S/Stn. Ajnala. | A). Erection and stringing of new 66 KV new link line, 10 KM SC on DC towers with ACSR 0.2 Sq inch between 66 KV S/Stn. Jasterwal and 66 KV S/Stn. Ajnala. (Point A to B). B). To construct 2 No. 66 KV Bays (1 no. at 66 KV S/Stn Jasterwal and 1 no. at 66 KV S/Stn Ajnala) | 269.60 58.00 | 327.6 |  | 2024-25 |  |  |  | 99 | 228.6
38 | 52/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 1). A new 66 KV Link line 12 KM SC on DC towers with ACSR 0.2 Sq inch from 66 KV S/Stn. Buchenangal to 66 KV S/Stn. Kalanaur. | A). Erection and stringing of new 66 KV link line, 12 KM SC on DC towers with ACSR 0.2 Sq inch between 66 KV S/Stn. Buchenangal and 66 KV S/Stn. Kalanaur. B). To construct 2 No. 66 KV Bays (1 no. at 66 KV Bhuchenangal and 1 no. 66 KV Kalanaur) | 323.52 58.00 | 381.52 |  | 2024-25 |  |  |  | 115 | 266.52
39 | 53/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 1) Erection & Stringing of 11 KMs/ SC on DC towers with ACSR 0.2 sq inch to replace existing HRP line with ACSR 0.1 / SC towers (Small- Toweri’s) from 132 kv Gurdaspur to 66 kv Ranjit Bagh. | a) Erection & Stringing of 11 KMs/ SC on DC towers with ACSR 0.2 sq inch to replace existing HRP line with ACSR 0.1 / SC towers (Small- Toweri’s) from 132 kv Gurdaspur to 66 kv Ranjit Bagh. (Point A to B) b) To construct of 1 No. 66 KV Bay at 66 KV S/Stn Ranjit Bagh for new proposed ring-main system. C) To dismantle existing HRP line after erection of new line as the line would be errected on the same right of way. | 296.56 29.00 -33.22 | 292.34 |  | 2023-24 |  |  | 88 | 204.34
40 | 54/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 3) Erection & Stringing a new 66 KV link line from 66 kv S/Stn. Udanwal to 66 KV S/Stn. Ghuman, approx. length of 7 km be constructed on SC to DC towers along with new 2 no. 66 kv Bays at 66 kv s/stn Udanwal and 66 kv s/stn Ghuman. | A) Erection & Stringing a new 66 KV link line from 66 kv S/Stn. Udanwal to 66 KV S/Stn. Ghuman, approx. length of 7 km 0.2sq." be constructed on SC to DC towers. (Point B to C) B) 2 no. 66 kv Bays ( 1 no. at 66 kv S/stn Udhanwal and 1 no. at 66 kv S/stn Ghuman) | 188.72 58.00 | 246.72 |  | 2024-25 |  |  |  | 75 | 171.72
41 | 55/BZ/2022- 23/Annex.B | BZ | S/U ASR |  |  |  | Erection of 1 no. 66Kv bay Varpal- Manawala Ckt-1 & Ckt-2 | Erection of 1 no. 66KV SF-6 VCB control bay instead of isolator control bay Varpal-Manawala Ckt-1 at 66KV S/S Manawala. | 22.1 | 22.1 |  | 2022-23 |  |  | 22.1
42 | 56/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | 1) Erection & Stringing of 11 KM/ SC on DC tower with ACSR 0.2 Sq inch to replace existing HRP line with ACSR 0.1/0.125 sq inch from 132 KV S/Stn. Shri Hargobinpur to 66 KV S/Stn. Ghuman. | a) Erection & Stringing of 11 KM/ SC on DC tower with ACSR 0.2 Sq inch to replace existing HRP line with ACSR 0.1/0.125 sq inch. (Point A to B) B) To Dismantle existing HRP line after erection of new line as the line would be errected on the same right of way. | 296.56 -33.22 | 263.34 |  | 2023-24 |  |  | 80 | 183.34
43 | 57/BZ/2022- 23/Annex.B | BZ | GSR |  |  |  | SC on HRP line with ACSR 0.125 Sq. inch – 8 KM (approx.) from 220 KV Kotli Surat Malhi to 66 KV Kalanaur | 1. Replacement of 8 KM/ SC on DC tower with ACSR 0.2 Sq. inch. 2. To dismantle existing HRP line after erection of new SC on DC line as the line would be errected on the same right of way. | 215.68 -24.16 | 191.52 |  | 2024-25 |  |  |  | 58 | 133.52
44 | 58/BZ/2022- 23/Annex.B | BZ | TTN |  |  |  | 66 KV S/Stn. Sur-Singh to 66 KV S/Stn Chabal with Gagobua Tapping (66 KV Line, Sur-Singh- Gagobua/Chabal) approx. length 12 KM on HRP with ACSR 0.125 sq inch. | A) Erection & Stringing of 66 KV line between 66 KV S/Stn. Sur-Singh to 66 KV S/Stn Chabal with also Gagobua Tapping approx.. length 12 KM .2 sq" on SC on DC towers to replace existing HRP with ACSR 0.125 sq inch. (Point A to B as per attached sketch) B) To Dismantle existing HRP line after erection of new SC on DC tower line as the line would be errected on the same right of way. | 323.52 -36.24 | 287.28 |  | 2024-25 |  |  |  | 87 | 200.28
45 | 62/BZ/2022-23 Annex.B | BZ | TTN |  | 52 |  | 66KV Gandiwind 1x12.5MVA,66/11KV | 1x 20 MVA to repl. 1x12.5MVA, 66/11 KV | 157.04 | 157.04 |  | 2023-24 |  |  | 48 | 109.04
46 | 63/BZ/2022-23 Annex.B | BZ | S/U ASR |  |  |  | 66 KV Sub Station Focal Point Amritsar T-1 1x12.5MVA 66/11KV T-2 10/12.5MVA 66/11 KV | Augmentation of Power T/F, T-1 12.5 MVA with 20MVA 66/11KV | 157.04 | 157.04 |  | 2022-23 |  |  | 157.04
47 | 64/BZ/2022- 23/Annex.C | BZ | GSP | 118 |  |  | 66 KV Buche Nangal 1x12.5MVA 66/11KV | 20MVA to rep.12.5MVA 66/11 KV | 157.04 | 157.04 |  | 2023-24 |  |  | 48 | 109.04
48 | 65/BZ/2022- 23/Annex.C | BZ | GSP | 113 |  |  | 66KV Ranger Nangal 1x6.3/8 MVA, 66/11 KV 1x6.3/8 MVA, 66/11 KV | 12.5 MVA to repl MVA 6.3/ 8, 66/11 KV | 85.92 | 85.92 |  | 2023-24 |  |  | 26 | 59.92
49 | 66/BZ/2022- 23/Annex.C | BZ | S/U ASR |  | 93 |  | 66 KV Sub Station Bagga Kalan T-1 having capacity of 12.5 MVA | Augmentation of Power T/F, 12.5 MVA with 20MVA | 157.04 | 157.04 |  | 2023-24 |  |  | 48 | 109.04
50 | 67/BZ/2022- 23/Annex.C | BZ | GSR |  |  |  | 1) New 66 kv line from 66 kv s/s Said Mubarak to 66 kv s/s F.P Batala, approx. length of 04 km be constructed on SC to DC towers along with new 1 no. 66 kv Bay at 66 kv s/stn Said Mubarak and 1 no. bay at 66 kv s/s F.P Batala. | A). Erection and stringing a new 66 KV link line, 04 KM SC on DC towers with ACSR 0.2 Sq inch between 66 KV S/Stn. Said-mubarak and 66 KV S/Stn. Focal Point Batala. B). To construct 2 No. 66 KV Bays (1 no. at 66 KV Said-mubarak and 1 no. 66 KV Focal Point Batala) | 107.84 58.00 | 165.84 |  | 2023-24 |  |  | 50 | 115.84
51 | 68/BZ/2022- 23/Annex.C | BZ | TTN |  |  |  | SC on HRP line with ACSR 0.15 Sq. inch – 7 KM (Approx.) from 220 KV Varpal to 66 KV S/Stn Sangna. | 1. Replacement of 7 KM/ SC on DC tower with ACSR 0.2 Sq. inch. 2. To dismantle existing HRP line after erection of new SC on DC line as the line would be errected on the same right of way. | 188.72 -21.14 | 167.58 |  | 2024-25 |  |  |  | 51 | 116.58
52 | 69/BZ/2022- 23/Annex.C | BZ | GSR |  |  |  | 66 KV Sub Station Dinanagar T-1 1x20MVA 66/11 KV T-2 10/12.5MVA 66/11 KV | Augmentation of Power T/F, T-2 10/12.5 MVA with 20MVA 66/11KV | 157.04 | 157.04 |  | 2023-24 |  |  | 48 | 109.04
[14 empty] | 518.96 | 4644.19 | 5454.48 | 2402.64 | 0
|  |  |  | 10 | 10 | 1

## Works being planned (hidden)
Works being planned
Annexure-VI
Sr.no. | Circle | Name | Tentative Cost in FY 2024-25 (In lac) | Tentative Cost in FY 2025-26 (In lac)
1 | Sangrur | 66KV S/S Khanouri |  | 256.75
2 | Ropar | 66KV S/S Bhukri |  | 785
3 | Barnala | 66KV S/S Bhullerheri |  | 437.64
4 | Sangrur | 66KV S/S Harkishanpura |  | 480
5 | Sangrur | 66KV S/S Khadial |  | 338
6 | Sangrur | 66KV S/S Kadial |  | 319.1
7 | Sangrur | 66KV S/S Kudni |  | 745
8 | Sangrur | 66KV S/S Banwala |  | 354
9 | Sangrur | 66KV S/S Power colony Sangrur |  | 330
10 | Mohali | 66KV S/S Mubarikpur (repl. 20 to 31.5 MVA) (Amendment no. 7/2022-23) |  | 199.7
11 | Khanna | 66KV S/S Mathi |  | 360
12 | Sub-Urban Ludhiana | 66KV S/S Bhamipur |  | 397
13 | Sub-Urban Ludhiana | 66KV S/S Gidderwindi |  | 450
14 | Sub-Urban Ludhiana | 66KV S/S Kaunke Kalan |  | 612
15 | Sub-Urban Ludhiana | 66KV S/S Basian Bet |  | 566
16 | Sub-Urban Ludhiana | Augmentation of 66 KV line from 220 KV Jagraon to 66 KV Agwar Loppon with 0.2sq" equivalent HTLS conductor |  | 387
17 | Sub-Urban Ludhiana | Augmentation of 66 KV line from 66 KV Agwar Loppon to 66 KV Rasulpur with 0.2sq" equivalent HTLS conductor |  | 571.5
18 | Sub-Urban Ludhiana | Augmentation of 66 KV line from 220 KV Jagraon to 66 KV Rasulpur with 0.2sq" equivalent HTLS conductor |  | 783
19 | Amritsar | 66KV S/S Mohakampura |  | 630
20 | Gurdaspur | 66KV S/S Shikar Machian |  | 314.28
21 | Kapurthala | 66KV S/S Littran |  | 466.285
22 | Amritsar | 66KV S/S 97 Acre Scheme |  | 629.35
23 | Taran Tarn | 66KV S/S Mehndipur |  | 447.03
24 | Hoshiarpur | 66KV S/S Kahri |  | 267.91
25 | Gusrdaspur | 66KV S/S Jakrian |  | 294.06
26 | Jalandhar | 66 KV S/S Chuharwali |  | 518.21
27 | Faridkot | 66KV S/S Machaki Khurd |  | 479.72
28 | Faridkot | 66KV S/S Khosa Pando |  | 573.516
29 | Sri Mukatsar Sahib | 66KV line from 66KV Baja Marar to 66KV Lubanianwali |  | 381.52
30 | Sri Mukatsar Sahib | 66KV line from 132KV Sarainaga to 66KV Bhuttiwala |  | 406.44
31 | Sri Mukatsar Sahib | 66KV line from 132KV Sarainaga to 66KV Baja Marar |  | 271.64
32 | Bathinda | 66KV Gill Kalan (Addl. 20 MVA) |  | 285.93
33 | Bathinda | 66KV line from 220KV Mansa to 66KV Mansa |  | 140.57
34 | Bathinda | New link between 66KV Chowke to 66KV Jeond (2nd source supply) |  | 354.56
35 | Faridkot | 66KV line from 66KV grid Chugawan to Focal Point Moga |  | 622.08
36 | Sri Mukatsar Sahib | 66Kv line from 66KV grid Hanumangarh Road Abohar to Abohar |  | 513.94
37 | Sri Mukatsar Sahib | 66KV line from 220KV Katorewala to Malout |  | 966.172
38 | Bathinda | To deload 66KV line from 66KV Mansa to 66KV Kot Dharmu |  | 102.668
39 | Bathinda | LILO from ring main 66KV IGC to 66KV Paras ram Nagar by adding 2nd cable from T-off point. |  | 582.08
40 | Bathinda | New link between 66KV Civil line to 66KV Hanuman Chowk Bathinda |  | 1315
41 | Faridkot | New link between 66 KV line from 22 0 KV Singhawala to 66 KV Dala and 220 KV Singhawala to 66 KV Gajjanwala |  | 785.92
42 | Tarn Taran/Rayya | 66 KV Derdeo | 595
43 | Tarn Taran/ City Division Taran | 66 KV Palasur | 595
44 | Tarn Taran/Bhikhiwind | 66 KV Dasuwal | 595
45 | TARN TARAN/PATTI | 66 KV MAMMANKE | 595
46 | Tarn Taran/Rayya | 66 KV Bania | 595
47 | Suburban Amritsar/ Jandiala Guru | 66 KV Dashmesh Nagar | 595
48 | Suburban Amritsar/ Jandiala Guru | 66 KV Gadli | 595
49 | Suburban circle/East Asr | 66 KV Shri Guru Ramdass Urban Estate Ajnala Road | 595
50 | Suburban circle/East Asr | 66 KV Mohkampura | 595
51 | City Amritsar Circle/City Center Divn. | 66 KV Khankot | 595
52 | Gurdaspur/Dhariwal | 66KV AGWAN | 595
53 | Gurdaspur/Dhariwal | 66 kv Jaffarwal | 595
54 | Gurdaspur/Qadian | 66 kv Aulakh kalan | 595
55 | Gurdaspur/ Gurdaspur | 66 KV Power colony Gurdaspur | 595
56 | Gurdaspur/Sub Batala | 66 KV Marar | 595
57 | Khanna/Sirhind | 66 KV Mathi | 595
58 | Khanna/Sirhind | 66 KV Behrampur | 595
59 | Khanna/Sirhind | 66 kV Sampli | 595
60 | Khanna/Amloh | 66 kv Badali | 595
61 | Khanna/Doraha | 66 kV Babe Shaheedamn Rajgarh | 595
62 | Khanna/Doraha | 66 kV Focal Point Mehdoodan | 595
63 | Khanna/Doraha | 66 kV Dhamot | 595
64 | Khanna/Mandi Gobindgarh | 66 kV Wazirabad | 595
65 | KHANNA | 66 kV Rattanheri (City-1) | 595
66 | KHANNA | 66 kV Kalaal Majra (City-1) | 595
67 | KHANNA/KHANNA | 66KV BAGLI (Chawa) | 595
68 | KHANNA/KHANNA | 66KV ISSRU (Jarg) |  | 595
69 | Suburban Circle Ludhiana/ Lalton Kalan | Village Khadoor |  | 595
70 | Suburban Circle Ludhiana/ Lalton Kalan | Village Rurka/Dehlon |  | 595
71 | Suburban Circle Ludhiana/ Lalton Kalan | Village Sangowal/ Jaspal Bangar |  | 595
72 | SUBURBAN / ADDA DAKHA | 66 KV BASSIAN BET |  | 595
73 | D S suburban circle Ludhiana | KAUNKE KALAN |  | 595
74 | D S suburban circle Ludhiana | CHEEMNA |  | 595
75 | Sub-Urban Ludhiana | 66KV Gidderwindi |  | 595
76 | Sub Ldh/Raikot | 66KV Bhamipura |  | 595
77 | Suburban LDH | 66 KV Cedaar Textile LTD. Vill. Akberpur Channa |  | 595
78 | Suburban LDH | 66 KV S/S Vill. Chhapar. |  | 595
79 | City East | 66 KV S/S, Tibba Road Ludhiana |  | 595
80 | City East | 66 KV S/S, Sec-32 Ludhiana |  | 595
81 | City East | Noorewal -2 |  | 595
82 | City East | Dana Mandi |  | 595
83 | City East | HAWAS |  | 595
84 | City East | Bajra |  | 595
85 | CITY WEST / AGGAR NAGAR | 66KV DANA MANADI AYALI |  | 595
86 | CITY WEST / MODEL TOWN | 66 KV RAILWAY SHAM NAGAR |  | 595
87 | CITY WEST / JANTA NAGAR | 66KV LOHARA |  | 595
88 | Hoshiarpur | 66 KV Kahri-Sahri |  | 595
89 | Hosiarpur | 66KV Sohalpur |  | 595
90 | JALANDHAR / EAST | 66 KV S/S TANDA ROAD NO-2 NEW |  | 595
91 | JALANDHAR / MODEL TOWN | 66 KV S/S PARTAPURA |  | 595
92 | JALANDHAR / MODEL TOWN | 66 KV S/S AGI |  | 595
93 | Kapurthala | Shala Nagar |  | 595
|  | Total | 15470 | 35190.571 | 50660.571

## Deposit works (hidden)
WORKS TO BE PLANNED | [8 empty] | Annexure - F
Sr.no | TWL sr.no. 2022-23 | TWL sr.no. 2021-22 | zone | Circle Name | MYT 2020-21 | MYT 2021-22 | MYT 2022-23 | Name of Work | Scope of Work | Estt. Cost (in lacs) | Status
1 | 125/SZ/2022-23 Annexure-D | 99/SZ/2020-21 & 2021-22/Annex-D | SZ | Mohali |  |  |  | a) 66 KV Line from 220 KV S/S Kharar to 220 KV S/S Banur (21 KM / 0.125 sq") b) 2 Nos. 66 KV Line Bays at 220 KV S/Stn Banur | a) Replacement of balance portion from M/s APIL upto 220 KV S/Stn Banur to be coverted into Multi Ckt. Towers (13 KM) b) To be planned / executed by PSTCL | 1006.72 | Work already completed.
2 | 126/SZ/2022-23 Annexure-D | 100/SZ/2020-21 & 2021-22/Annex-D | SZ | Mohali |  |  |  | a) 66 KV Grid IT City, Sector 82-A, Mohali (NEW) b) New Link (0.2 sq"/ 70 metres span with new Tower TL-A D-60 ) to be constructed from Tower no. TL-26 2D-30 of "existing 66 KV Multi-Ckt T-Off Line from Banur-Ansal Line for Airport" upto Gantry at proposed 66 KV S/Stn IT City Sector 82-A, Mohali c) 1 No. 66 KV Line Bay at proposed new 66 KV Grid IT City, Sector 82-A, Mohali | a) 20 MVA, 66/11 KV b) 0.2 sq" / 70 metres span with 1 no. new Tower TL-A D-60 c) 1 No. | 258.6 1.74 28 | Sub-Station commisssioned in 02/2020
3 | 127/SZ/2022-23 Annexure-D | 101/SZ/2020-21 & 2021-22/Annex-D | SZ | Patiala | 42 |  |  | New 66 KV Grid Rajindra Hospital, Patiala on co-sharing basis with PSPCL. 66 Kv line Bays | a) 1x20 MVA, 66/11 KV (entitled for PSPCL). b) 1x10/12.5 MVA, 66/11 KV (entitled for Rajindra Hospital, Patiala c) Overhead 66 KV line 400 mtr/0.2sq” ACSR/S/C on D/C + b) 2015 mtr 66 KV U/G cable of 240 mm2 d) 2 nos. 66 KV bays (1no. bay will be constructed at 66 KV S/S Shakti Vihar and 1 no. bay will be constructed at new proposed 66 Kv S/S Rajindra Hospital | 258.58 8.52 + 274.04 56 | Sub-Station commisssioned on 29.06.2021
4 | 128/SZ/2022-23 Annexure-D | 102/SZ/2020-21 & 2021-22/Annex-D | SZ |  | 135 |  |  | a) 66 KV New Focal Point Nabha Grid S/Stn of PSPCL inside PSIEC, Nabha (including 1 No. 66 KV Line Bay with 66 KV Circuit Breaker at this new 66 KV Grid) b) Additional 66 KV Line Bay along with 66 KV Circuit Breakers for making LILO arrangement at this new proposed 66 KV Grid. c) Shifting of existing 66 KV line Nabha-Hiana Kalan to provide LILO arrangement for 'proposed 66 KV Grid New Focal Point Nabha of PSPCL inside PSIEC, Nabha' | a) 1 x 20 MVA, 66/11 KV T/F b) 1 No. c) Errection of 1 no. D-30 & 2 no. D-60 towers and erection of 2 no. gantries of approximately 35 mtrs & 11 mtr length with conductor size of 0.2sq” (As per attached sketch). | 258.6 28 17 | S/Stn. charged on 25.10.2021
5 | 129/SZ/2022-23 Annexure-D | 103/SZ/2020-21 & 2021-22/Annex-D | SZ | Mohali |  |  |  | 66 KV MCT line from 220 KV S/S Banur to 66 KV S/S Ansal and t-off on MCT 1) For double ckt. 0.2sq" for 66 KV S/S International Airport, Mohali. 2) T-off for double ckt. 0.2sq" for 66 KV S/S IT City and 66 KV S/S Aerocity -1 | 1 no. 66 KV bay at 220 KV S/S Banur for International Airport, Mohali ckt. 2. Note:- 1 66 KV bay is already planned /errected forAirport Mohali ckt 1 and 1 66 KV bay for International Airport, Mohali ckt 2 shall be planned by PSTCL. 66 KV bays for International Airport, Mohali ckts are . covered under deposit works | Nil
6 | 130/SZ/2022-23 Annexure-D | 104/SZ/2020-21 & 2021-22/Annex-D | SZ | Ropar |  |  |  | 66 KV T-off line from 220 KV S/S Kohara to M/S Maha Lakshmi Feeder for M/S T.K Steels village Paharuwal, Chandigarh Road, Ludhiana. | New 0.195Km/ 0.2sq” ACSR SC on DC towers 66KV line T-off from existing 220KV Kohara to M/S Maha Lakshmi 66KV Feeder | 26.07
7 | 131/SZ/2022-23 Annexure-D | 105/SZ/2020-21 & 2021-22/Annex-D | SZ | Ropar |  |  |  | 66 KV line from 66 KV S/S Bhagpur to M/s Renny Strips Pvt. Ltd. village Mangarh Machhiwara Road Kohara by laying 66 KV U/G cable 240 mm2/2.714 ckt. Km (Deposit Work). | a) 2.714 ckt Km / 240 mm2 U/G cable. b) 66 KV line bay at 66 KV S/S Bhagpur. | 999 28 | Straight joint work in progress
8 | 132/SZ/2022-23 Annexure-D | 106/SZ/2020-21 & 2021-22/Annex-D | SZ | Ropar |  |  |  | Extension of load of M/s Sharmanji Yarns Pvt. Ltd. Lakhowal Road, Kohara (Deposit Work) | Augmentation of 0.2sq” ACSR with 0.4sq” /0.240 Km of existing 66 KV Allied recycling feeder emanating from 220 KV S/S Kohara by erecting 2 nos. MCT from Kohara up to existing T-off Point for M/s Sharmanji Yarns Pvt. Ltd. | 64 | Line charged in 02/2022.
9 | 133/SZ/2022-23 Annexure-D | 108/SZ/2020-21 & 2021-22/Annex-D | SZ | Ropar |  |  |  | New 66 KV line for extension of load of M/s Vividha Infrastructure village Chamaru (Deposit Work). | 240mm2 single ckt U/G copper cable of approx length of 227 ckt meter from existing 66 KV line from 66 KV S/S Focal Point Rajpura to M/s Asian Fine Cement. | 78.7
10 | 134/SZ/2022-23 Annexure-D Amend. No. 08/2022-23 dated 17.08.2022 | 109/SZ/2020-21 & 2021-22/Annex-D | SZ | ROPAR |  |  |  | 66 KV S/Stn for PSIEC project of Hi tech cycle valley village Dhannasu Ludhiana 66KV line from new proposed 400KV PSTCL S/S for 66KV S/S PSIEC project of Hi Tech Cycle Valley village Dhannasu Ludhiana | a)20MVA 66/11 KV Power T/F along with allied electrical equipments b) 2 no. 66KV outgoing line bays at 400 KV proposed PSTCL sub station c) 2 no. 66KV incoming line bays at 66KV PSIEC S/Stn d)New 66KV line outgoing bay from new proposed 66KV PSIEC S/S to new 66KV S/S S/S for HECPL area e) Civil Works:- i) tentative cost of building under standard conditions ii) Tentative cost of Civil work for one no landing and one no outgoing 66 KV bay f) 0.050 Km / 0.4sq“ ACSR DC on DC | 190 82 82 37 100 15 5 | Civil Allotment Done with work to be started.Route plan under process
11 | 136/SZ/2022-23 Annexure-B Amend. No. 05/2022-23 dated 13.07.2022 |  | SZ | ROPAR |  |  |  | Provision of 66 Kv supply by erection of separate 66 KV bay and new 66 KV link line for M/s Sharman ji yarns Kohara from 220 KV S/Stn. Kohara (Deposit Work) | 1) Erection of new 0.2 sq" ACSR from (A-B) after Shifting of existing 0.4 sq" ACSR from point (A-B) to point (C-D) (as per sketch). 2) Shifting of 0.2 sq" ACSR of 66 KV Maha Laxmi feeder from point C and first MCT to Proposed new gantry (E to F as per sketch). 3) 1 No new 2D-2+03 m between First and Second No. tower emanating from 220 KV Kohara so as to erect 3 No. lines on MCT towers (as per sketch). 4) 1 No 66 KV bay at 220 KV S/S Kohara. (To be constructed by PSTCL). | 20.5 45.00
12 | 124/NZ/2022-23 /Annex.D | 73/NZ/2020-21 & 2021-22/Annex-D | NZ | HSP |  |  |  | New 66 KV line from M/s Bhogpur Sugar Mills Ltd., Bhogpur to 66KV S/S Soosan b) 66KV bay 1 No. at 66 KV S/S Soosan | a)7.5Km/0.2Sq" SC on DC 66KV Towers line 1no. | 159.83 28.00
13 | 125/NZ/2022-23 /Annex.D | 74/NZ/2020-21 & 2021-22/Annex-D | NZ | HSP |  |  |  | Augmentation of ACSR from 0.15sq'' to 0.2sq'' of existing Tower/Rail pole 66KV line from 66KV S/S Mukerian paper mill (M/s Indian Scrose Ltd GT road Mukerian) To MHP-4 (132KV S/S Unchi Bassi) | a) Augmentation of ACSR from 0.15 sq'' to 0.2sq''/8Km of existing 66KV HRP/Tower line from 66KV S/Stn. Mukerian paper mill to MHP-4 (132KV S/S Unchi Bassi) b)2 nos.P Q type towers will be replaced with 1 nos.- D-2+6m tower 2 nos.- D-30+6m tower due to excavation of surrounding land. | 56.16 2.00
14 | 126/NZ/2022-23 /Annex.D | 75/NZ/2020-21 & 2021-22/Annex-D | NZ | HSP |  |  |  | 66 KV line from 66 KV S/s Chabewal to M/s Ludhiana Beverages Pvt. Ltd. Mehlanwali | a) New 7.157 km/0.2 sq." / SC on DC tower line from 66 KV S/s Chabewal up to consumer premises. b) 1 no. 66 KV bay at 66 KV S/s Chabewal | 238.62 28.77
15 | 70/BZ/2022 23/Annex.D | 58/BZ/2020-21 & 2021-22/Annex-D | BZ | GSP |  |  |  | a)66KV S/S 155 Acre Puda Scheme Batala road Gurdaspur (NEW) b) 0.07km/SC on DC 66KV line,T-off from existing Gurdaspur to Babehali, 0.125sq"/Rail pole 66KV ideal line circuit c) 66KV line bay at new grid | 20 MVA, 66/11 KV P,T/F 0.07km/SC on DC 66KV tower line 1 no. | 258.59 1.49 28.00
16 | 66/CZ/2022-23 Annexure-D | 53/CZ/2020-21 & 2021-22/Annex-D | CZ | LDH |  |  |  | a)66 KV S/Stn. Mega Food Park Ladhowal (New). b)66KV line 1.4 Km, 0.2 sq."SC on DC tower line from 220 KV S/Stn. Ladhowal (under construction) to SC on DC Tower line from 220KV S/S Ladhowal to 66 kv S/S Mega Food Park Ladhowal. c) 66 KV line bays. | 20 MVA T/F 66 /11 KV 1.4 Km 1 nos. | 262.8 34.86 28.77
17 | 67/CZ/2022-23 Annexure-D | 54/CZ/2020-21 & 2021-22/Annex-D | CZ |  |  |  |  | a)66 KV line from 66 KV S/s Talwara to M/s Rasik Industries, Talwara Road, Mandi Gobindgarh. (RID no. 19943) b)66kV line bay. | a)66 KV underground cable of size 240 mm2, S/ckt. and length of 941* Ckt. metres from 66 KV S/s Talwara to M/s Rasik Industries. b)1 no. new 66 KV bay at 66 KV S/s Talwara. | 398.5 28.77
18 | 68/CZ/2022-23 Annexure-D | 55/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna/ Central Zone |  |  |  | T-off 66 KV line from 220KV S/S G-3 Mandi Gobindgarh to M/s Sanjiv Bhatia line – M/s Punjab Steel for M/s Dashmesh Castings Pvt. Ltd village Jalalpur Amloh road MGG | New 1.167Km/ 0.2Sq"/ ACSR SC on DC 66KV Towers Line (Narrow base towers) | 124 | Route Plan as per revised feasibility under approval
19 | 69/CZ/2022-23 Annexure-D | 56/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna/ Central Zone |  |  |  | 66 KV line from 66 KV S/S Grain Market to M/s Kisco Casting India Ltd. Guru ki Nagri, MGG laying 66KV under ground cable size 240mm2 (deposit work) | a)New 0.158 ckt-Km/ 240mm2 66KV underground cable from proposed gantry for Kisco b) 66KV bay 1no. at 66KV S/S Grain Market | 125 28
20 | 70/CZ/2022-23 Annexure-D | 57/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna/ Central Zone |  |  |  | New proposed 66KV T-off line 0.2sq’’ ACSR/ SC on DC 0.045ckt-Km for new connection to M/s Sunshine Concast Ambe Majra, Chhatarpur road from existing M/s Aman Alloys 66KV idle line 0.2sq” from 220KV S/S G-1, Mandi Gobindgarh (Deposit work) | New 0.045 Ckt-Km 0.2sq” ACSR SC on DC 66KV line | 48.29 | Dismantlement pending
21 | 71/CZ/2022-23 Annexure-D | 58/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna/ Central Zone |  |  |  | New proposed 2.998 ckt-Km / 0.2sq” ACSR /SC on DC 66KV tower line from 66KV S/S Jalalpur to M/s Shree Ganesh Edibles Pvt. Ltd., Village Shahpur under circle Khanna (Deposit Work ) | a) New 2.998 ckt Km/ 0.2sq” ACSR /SC on DC 66KV tower line b) 66KV line bay at 66KV S/S Jalalpur | 135 28 | work is under progress, Revised route under process
22 | 72/CZ/2022-23 Annexure-D | 59/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna/ Central Zone |  |  |  | New proposed 66KV line 0.045 ckt Km / 0.2sq” ACSR / SC on DC 66KV tower from existing 66KV Modern feeder emanating from 220KV S/S G-1 MGG for connection of M/s Prabhat Heavy Forging Pvt. Ltd. , village Ajnali GT road Sarhind side under circle Khanna (Deposit Work) | New 66KV line 0.045 ckt Km / 0.2sq” ACSR / SC on DC 66KV tower line | 25.5 | EOT has been complleted. Sagging completed. Jumpering pending due to shutdown on Modern Steel Line
23 | 73/CZ/2022-23 Annexure-D | 61/CZ/2020-21 & 2021-22/Annex-D | CZ | City west circle Ludhiana /Central Zone |  |  |  | New connection of M/s SRV Steel Pvt.Ltd. unit -2 village Bhagwanpura, Tehsil Dehlo, Ludhiana by tapping existing 66KV line M/s Garg Acrylics line 0.2sq’’ emanating from 220KV S/S Sahnewal (Deposit Work) | New 0.510mts/0.2Sq" ACSR SC on DC 66KV Towers line | 69.59 | Work order issued
24 | 74/CZ/2022-23 Annexure-D | 62/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna /Central Zone |  |  |  | New connection of M/s Ambey Industries GT road Sarhind side Mandi Gobindgarh new 66KV T-off line under deposit work from existing 66KV Idle Aman Alloys line 0.2sq’’ emanating from 220KV S/S G-1 MGG | New 1.752Km/ 0.2Sq" ACSR SC on DC 66KV Towers line | 139.86 | Work in progress
25 | 75/CZ/2022-23 Annexure-D | 63/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna /Central Zone |  |  |  | Releasing 66KV new connection to M/s Vayu Products Pvt Ltd. Village Chourwala by laying 66KV underground cable 4x1/C 240mm2 100m emanating from 66KV S/S Chourwala (Deposit Work ) under circle Khanna | a) New 100 ckt mts. /66KV 240mm2 underground cable single circuit from 66 KV Chourwala b)1nos. 66KV bay at 66KV S/S Chourwala to feed load of M/s Vayu Products Pvt Ltd | 52 28.8 | Work completed in 04/2022
26 | 76/CZ/2022-23 Annexure-D | 64/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna /Central Zone |  |  |  | New proposed 0.149 Ckt-Km/ 66KV underground cable 240mm2 to feed load of M/s Nabha Steel & Metals GT road Mandi Gobindgarh by tapping existing 66KV Raghav –Nabha feeder emanating from 220KV S/S G-1 MGG having existing 0.2sq’’/3.6Km from point A to B under circle Khanna (Deposit Work ) | New 0.149 Ckt-Km/ 66KV underground cable 240mm by tapping existing 66KV Raghav –Nabha feeder | 62
27 | 77/CZ/2022-23 Annexure-D | 65/CZ/2020-21 & 2021-22/Annex-D | CZ | City west circle Ludhiana /Central Zone |  |  |  | Extention of load to M/s Maruti Alloys village Dugri P.O Rajgarh by tapping existing 66KV Garg Acrylics line emanating from 220KV S/S Sahnewal with replacement of the existing tower TL-14 & TL-14/1 to Multi circuit towers for erection of 3rd ckt with 0.2sq’’ (Deposit Work) under city west circle Ludhiana | Erection of new 3 nos Multi circuit towers with length of line is 0.114km SC /0.2sq’’/ ACSR to feed load of M/s Maruti Alloys | 82.26
28 | 78/CZ/2022-23 Annexure-D | 66/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna /Central Zone |  |  |  | a) New proposed 0.102 Ckt-Km/ 66KV underground cable 240mm2 to feed load of M/s Gian Casting Pvt. Ltd. ,Near 66kV Sub-Station Grain Market , Mandi Gobindgarh under DS Circle Khanna (Deposit Work) | a) New 0.102 Ckt-Km/ 66KV underground cable 240mm2 (Single Circuit) b) 1 No. 66kV Line Bay at 66kV S/Stn. Grain Market Mandi Gobindgarh. | 56.6 28.5
29 | 79/CZ/2022-23 Annexure-D | 67/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna /Central Zone |  |  |  | a) New proposed 0.884 Ckt-Km/ 66KV underground cable 240mm2 emanating from 220kV S/Stn. G-4 , Mandi Gobindgarh to feed the load of M/s Salasar Casting Pvt. Ltd., Village Mulanpur Kalan, Sirhind Side, Mandi Gobindgarh under DS Circle Khanna (Deposit Work ) | a) New 0.884 Ckt-Km/ 66KV underground cable 240mm2 from 220kV S/Stn. G-4,Mandi Gobindgarh (Single Circuit) b) 1 No. 66kV Line Bay at 220kV S/Stn. G-4 Mandi Gobindgarh.(To be planned and constructed by PSTCL) | 247.6 28
30 | 80/CZ/2022-23 Annexure-D | 68/CZ/2020-21 & 2021-22/Annex-D | CZ | Khanna /Central Zone |  |  |  | New proposed 0.660 Ckt-Km/ 66KV underground cable 240mm2 by solid tapping existing 66kV Garg Acrylics line emanating from 220kV Sahnewal after erecting 1No. BN+6 meters tower to feed the load of M/s Ajar Amar Steel Concast, Village Dugri, Tehsil Payal, Distt. Ludhiana under DS Circle Khanna (Deposit Work ) | New 0.660 Ckt-Km/ 66KV underground cable 240mm2 by solid tapping existing 66kV Garg Acrylics line emanating from 220kV S/Stn. Sahnewal after erecting 1 No. BN+6 meter tower. (Single Circuit) | 231.37 | U/G cable execution in progress under supervision of this office. Execution tendere has been floated by TL Division, Ludhiana which opened on 16/05/2022
31 | 81/CZ/2022-23 Amendment no. 01/2022-23 dt. 13.06.2022 | 69/CZ/2020-21 & 2021-22/Annex-D | CZ | KHN |  |  |  | Extension of load for M/s JMK Industries Village Wazirabad by laying U/G cable size 240 mm2 from 220KV S/S MGG G-4 (Deposit work) | Laying of U/G cable size 240 mm2 length 2.010 ckt Km Erection of CN tower outside the premises of firm and putting sag 0.2sq" ACSR /0.03 Ckt Km 66KV Bay at 220KV S/S MGG G-4 to be constructed by PSTCL | 563.53 17.54 28.77
32 | 132/WZ/2022-23 Annexure-D | 123/WZ/2020-21 & 2021-22/Annex-D | WZ | BTI |  |  |  | a) 220 KV Talwandi sabo -66 KV jodhpur pakhar, T-off for HPCL Refinery Raman line b) DC tower at the crossing of Jodhpur Refinery & 66 KV Jaga Ram Tirath | 0.9 Km/0.2Sq" on DC towers 1. no.Bay | 25.50 28.00
33 | 133/WZ/2022-23 Annexure-D |  | WZ | BTI |  |  |  | 66KV HPCL Ethonal Bio Refinery line | a) Errection of new 66KV line with ACSR 0.2sq" inch 4.5 KM eminated from new proposed 66KV S/S Jiwan Singh Wala. b) 1 nos. 66Kv bay at 66KV S/S Jiwan Singh Wala | 121.32 29.00
[5 empty] | 2 | 0 | 0