PUNJAB STATE ELECTRICITY REGULATORY COMMISSION

SCO NO. 220-221, SECTOR 34-A, CHANDIGARH

Petition No. 16 of 2011

Date of Order: 20.04.2011

In the matter of :    	Petition for  review of order of PSERC dated 6.1.2011 in Petition No.34 of 2010 regarding installation of CT/PT metering equipment by Open Access customers.

AND

In the matter of:              Punjab State Power Corporation Limited, Patiala

Present:                  	Smt.Romila Dubey, Chairperson

Shri Virinder Singh, Member

Shri Gurinderjit Singh, Member

ORDER

PSPCL has filed this petition for review of Order dated 6.1.2011 passed by the Commission in Petition No.34 of 2010 . It is stated in the petition that as per order of the Commission, PSPCL was to notify the approved vendors for the CTs/PTs of the required accuracy within one month of the  issue of the  order and testing of metering equipment is to be carried out within two days. The petitioner has stated that Expression of Interest  (EOI) was floated by the petitioner for empanelment of firms  for private sale of CT/PT units of required accuracy class to prospective open access customers, but in response thereto no firm has been found technically suitable  as per the requirement of technical specifications. It is further stated that fresh tenders were being floated for the purpose but the time required for empanelment of firms shall be about four months and  time for receipt of ABT meters and CT/PT units from  firms against fresh Tender Enquiry shall  be about five months. It is also stated that it is not possible to carry out test within two days on account of  reasons mentioned below and would require atleast five days time for testing.

- Four types of test are performed in the ME Labs for active energy import and export and it requires nearly 27 hrs. (3 days).

- For Start Test, Creep test, Dial Test, Temper Tests and accuracy tests after temper tests, another one day is required.

- After all these tests, data is downloaded and is studied for tamper loggings. Thereafter, meter is cleared for sealing and it takes another one day.

It is prayed in the petition that time for empanelment may be extended to four months and time for receipt of ABT meters and CT/PT units from firms already empanelled for private sale may be fixed as five months. It is also prayed that time for testing of metering equipment may be fixed as five days. The petition was fixed for hearing on 29.3.2011 on which date arguments were heard and the petitioner requested for time for filing additional information. The petitioner filed  additional information  on 1.4.2011 and filed the  relevant documents for empanelment of 2 No. firms M/s L&T Meters Ltd. and M/s Wallaby Metering Systems, Chennai for private sale of ABT meters to Open Access Consumers alongwith a copy of Commercial Circular issued by PSPCL. It is further stated that the present capacity of testing of ABT meters by the Metering Organization at a time is of three meters in each ME Lab at Ludhiana, Jalandhar and Patiala and only three meters of the same current ratio can be tested at a time in each ME Lab. It is also stated that the above said three Labs are being upgraded by installing three new test benches and capacity of these three Labs at Jalandhar, Patiala and Ludhiana will increase for testing of twenty meters in each lab.

In view of the reasons mentioned in the petition and the additional information filed by the petitioner, it is hereby ordered that four months time from the date of this order is allowed for empanelment of vendors for CT/PT of the required accuracy class to prospective open access customers. Till then the status quo will be maintained both for existing as well as new applicants seeking open access. Time for testing of metering equipment is  fixed as five days instead of two days.  This petition is disposed of accordingly.

Sd/-					Sd/-				  Sd/-

(Gurinderjit Singh)	                       (Virinder Singh)	                   (Romila Dubey)

Member		                       Member  		                   Chairperson

Chandigarh

Dated: 20.04.2011