Directives of 3rd quarter Ending December 2019 for FY 2019-20__

| 6.1 Reduction in T&D losses | PSPCL is directed - to achieve the distribution loss trajectory approved by the Commission. | - PSPCL is striving hard to achieve the trajectory of distribution losses as approved by Hon'ble PSERC. As per provisional data of PSPCL upto 31.12.2019, PSPCL has registered 11.21 % Distribution Losses upto Dec-2019 which has been decreased by -0.31% from last year corresponding period. To reduce distribution losses to minimum level PSPCL is taking following measures. Shifting of meters outside consumer premises: Name of Scheme; Scope of Work; Progress of meters shifted outside consumer premises from 01-10-2019 to 31-12-2019; Total balance meters to be Shifted as on 31-12-2019; Nos. of Meters where Severe Resistance from Kissan Unions and Public is being Faced; Meters that can be shifted without any Resistance; Schedule for Shifting of Balance Meters. 2019-20; 2020-21. R-APDRP (Part-B ); 0.06; 0; 0.06; 0; 0.06; 0.06; -. DDUGJY; 0.10; 0.01; 0.09; 0; 0.09; 0.09; -. IPDS; 0.47; 0.16; 0.31; 0; 0.31; 0.31; -. In House; 5.04; 0.03; 5.01; 2.11; 2.90; 0.97; 4.01*. TOTAL; 5.67; 0.20; 5.47; 2.11; 3.36; 1.43; 4.01. - The work of shifting of balance meters under RAPDRP (Part-B), IPDS and DDUGJY schemes shall be completed by 31-03-2020. - Estimates for 2.39 Lac Meters comes under scope of In-house meter shifting have been prepared under 6 Circles and Tendering is under progress for labour outsourcing. - Replacement of Balance Electromechanical Meters with Electronic Meters :- During 3rd quarter of FY 2019-20, 0.53 lac. Electromechanical Meters have been replaced with Electronic meters. Now, total 4.37 Lac Electromechanical meters are balance to be replaced with Electronic meters as on 31-12-2019 as under :- Description; SAP area; Non-SAP area; Total; Schedule of Replacement of Meters. 2019-20; 2020-21 (Up to Sept-2020). Balance as on 31.12.2019; 167145; 269555; 436700; 46624; 390076. - PSPCL will replace balance electromechanical meters as per above schedule. - Clearance of Key Exceptions :- - As per reports of billing Cycle-5 (Bi-Monthly ) and Cycle-10 (Monthly), the summary of key exceptions under PSPCL is as under:- Year; (N); (L); (R); (D); (M); (G); (S); (F); (I+P-Code); Total. Up to 2018; 248; 39; 944; 1558; 23; 2; 533; 1004; 506; 4857. For 2019; 32602; 4705; 33297; 70890; 2200; 187; 11425; 13423; 17363; 186092. Total; 32850; 4744; 34241; 72448; 2223; 189; 11958; 14427; 17869; 190949. - All key exceptions pertaining to year 2018 will be cleared by the end of March-2020. - Key exceptions pertaining to year 2019 where no meters are required shall be cleared by June-2020. The remaining key exceptions where meters are required for clearance of key exceptions shall be cleared by Sept-2020. - Checking of Theft :- - To curb the theft of electricity during FY 2019-20, upto December 2019, 1381175 nos. connections has been checked by Distribution Organization and Enforcement Wing of PSPCL. Out of which 128139 nos. cases of theft and UUE have been detected and penalties to the tune of Rs. 157.55 Cr. Have been imposed on consumers who were involved in power theft. Nos. of Connections Checked by DS Offices.; Nos. of theft Cases Detected; Penalty Imposed ( In Lacs). Border; 320417; 14814; 1894. North; 159760; 8718; 638. West; 82990; 9189; 1599. South; 149119; 15689; 2334. Central; 147242; 17023; 1553. Enforcement; 521647; 62706; 7736.69. TOTAL; 1381175; 128139; 15754.69. - Commissioning of New 66 KV Sub Stations :- In order to reduce the length of long HT lines and for improvement in voltage level, 8 Nos. new 66 KV Substations has been commissioned during FY-2018-19. In addition to these 11 Nos. new 66 KV Substations has already been commissioned upto 12-2019 and 5 no. new 66 KV Substations shall be commissioned upto 03-2020. - Installation of Whole Current Smart Meters and RF Meters :- Three Phase Whole Current Smart Meters: PSPCL is procuring 96,000, 3-Phase Whole Current Smart Meters, which can be used either in post-paid or pre-paid mode. For this tender enquiry no. MQP-145 has been floated by PSPCL and 3 no. firms namely M/s L&T Ltd., M/s HEPL & M/s Genus Power Infrastructure Ltd. have participated in the tender and presently, the sample maters are being tested for technical parameters by Sample Testing Committee at ME Lab, Jalandhar. Out of these, approx. 52,000 meters are proposed to be installed on AP consumers being fed from 250 no. Feeders identified under DBTE Scheme. Rest of the meters will be installed on Industrial and Commercial connections having sanctioned load greater than 20 KW and upto 25 KW. It is also pertinent to mention that above mentioned tender enquiry stipulates smart meter either on 4G or NBIOT based on 4G technology with fall back on 3G/2G, which no other state utility has procured as yet. RF Meters (Three Phase and Single Phase): RF Meters eliminate manual intervention in taking readings of meters and to capture/communicate real time data. Tender had been floated for procurement of 90,000 no. Single Phase RF Meters (MQP-155) and a different tender for procurement of 30,000 no. Three Phase Meters shall be floated soon. These meters shall be installed//commissioned in Agar Nagar Special Division, Ludhiana City. These meters shall be installed in cluster. The due date of opening of Tender Enquiry No. MQP-155/PO(M) is on Tender Enquiry is 18.03.2020 and pre-bid meeting for same was held on 03.02.2020. - Feeder Segregation: All the feeders have been segregated under PSPCL except Kandi feeders which are being segregated/AP consumer metering in Kandi Areas under DDUGJY scheme at the cost of Rs. 191.19 Crores. Due to stiff resistance from AP consumers and Kissan Unions the work was stalled. However with intervention of Punjab Govt. and PSPCL management the pace of work has now pickedup. The work of 4 no. Feeders after load segregation have been physically completed. However, these new feeders are yet to be energized which shall be done after attending few observations of Chief Electrical inspector and coordination with DS Organisation. The balance works of Segregation of Kandi Area Feeders are expected to be completed by 11-2020. - Release of AP connections on HVDS system: Under PSPCL, out of total no. of 13.83 Lac AP connections, 6.43 Lac AP connections are now running on HVDS system. PSPCL releases all new AP connection on HVDS system. 3011 no. AP connections have been released on HVDS system during this FY. - Augmentation of undersize conductor: To reduce I2R losses, undersized conductors are being augmented with higher size under DDUGJY scheme and IPDS Scheme as below :- Sr No; Description; Unit; Total Scope; Work Completed; %age work completed. 1; Augmentation of conductor on HT Lines.; Ckt. KM; 4218.1; 3258.8; 77.26%. 2; Augmentation of conductor on LT Lines.; Ckt. KM; 910.1; 653.41; 71.80%. The balance work is to be completed by the end of March-2020. PSPCL is being take above measure to reduce the Distribution Loss with in trajectory approved by the Hon’able PSERC. In addition to above, It is requested to the hon'ble commission that PSPCL may be allowed to regulate the supply of high loss feeders. |
| --- | --- | --- |
| 6.1 Reduction in T&D losses 6.1 Reduction in T&D losses | (ii) carry out energy audit of at least one circle and submit the report by March 2020. - (iii) - To reduce the losses of divisions with distribution loss level above 25% to below 15% during FY 2019-20. | Generation GHTP Leha Mohabat. The Energy Audit of all the 4 No. Units of GHTP, Lehra Mohabbat was carried out by BEE-accredited energy auditor M/s Siri Exergy & Carbon Advisory Services Pvt. Ltd., Hyderabad from 05-12-2018 to 17-12-2018. Its report has been submitted to Punjab Energy Development Agency (PEDA), Chandigarh and the Bureau of Energy Efficiency (BEE), New Delhi. Sr. No.; Recommended Action; Steps Taken. 1; VFD's for CEP's (Stage-I).; Already one stage of one of the two CEP’s for each Unit has been removed. Hence, there is no need for installation of VFD’s on CEP’s of Stage-1.. 2; Pump Coating for CW pumps (Stage-I).; The expenditure for coating of one pump is Rs. 6-7 Lac while the lifespan of coating is 3 years. Due to less running of Units, the payback period is very long. Hence pump coating is not economical and this idea has been dropped.. 3; Pump Coating for BACW pumps (Stage-I); -do-. 4; Installing Efficient Capacity Controller and Demand Controller for Air Compressors (Stage-I); Budgetary offers have been received from the suppliers. Quotations have been called for further action.. 5; Installing Efficient Capacity Controller and Demand Controller for Air Compressors (Stage-II); -do-. 6; Cost Economics by improving insulation for Steam pipes/Boilers; Insulation has been improved at all vulnerable points.. 7; Cost Economics of Temp. Optimisation for ACs.; Action has been taken by increasing the temperature set points of the ACs.. 8; Cost Economics by using Efficient LED Street Lights; The action has been taken and a total 4900 No. lights have been replaced with efficient LED lights.. 9; Reduction of Air Leakage in Boiler-1 & 2; All the leakage points traced during Air Tightness Tests (ATT) have been plugged. This is a repetitive exercise done as per requirement.. 10; Reduction of Air Leakage in Boiler-3.; -do-. GGSSTP Ropar Energy Audit has been completed and energy audit report has been submitted to BEE and PEDA on 21.11.2019. Hydel Projects ASE PSPCL (Energy Audit) Protection Division No.1 PSPCL, Amritsa has asked for carrying out energy audit of UBDC project, Malikpur. GENERATION AUX. &GT (MUs) SHANAN; Remarks/Action Plan. MONTH; Target; GEN.; AUX; %; GT; %; 1.Auxiliary losses are within permissble limit. 2.G.T. losses are higher than the permisible limit due to installation of single phase T/Fs instead of 3 phase T/Fs for the reason of space constraints.. Apr-19; 50; 62.407; 0.014; 0.02; 0.847; 1.36. May-19; 72; 79.718; 0.015; 0.02; 1.166; 1.46. Jun-19; 72; 76.733; 0.015; 0.02; 1.169; 1.52. Jul-19; 72; 79.655; 0.015; 0.02; 1.067; 1.34. Aug-19; 72; 73.465; 0.015; 0.02; 1.069; 1.46. Sep-19; 45; 63.620; 0.014; 0.02; 0.944; 1.48. Oct-19; 25; 30.509; 0.011; 0.036; 0.485; 1.590. Nov-19; 16; 19.412; 0.011; 0.057; 0.260; 1.339. Dec-19; 13; 17.120; 0.013; 0.08; 0.272; 1.59. Jan-20. Feb-20. Mar-20. TOTAL; 437; 502.639; 0.123; 0.02; 7.279; 1.45. GENERATION AUX. &GT (MUs) UBDC; Remarks/Action Plan. MONTH; Target; GEN.; AUX; %; GT; %; Auxiliary losses are within permissble limit. .. Apr-19; 0.00; 21.768; 0.061; 0.28; 0.070; 0.32. May-19; 0.00; 47.062; 0.088; 0.19; 0.161; 0.34. Jun-19; 0.00; 52.562; 0.086; 0.16; 0.178; 0.34. Jul-19; 0.00; 55.145; 0.093; 0.17; 0.184; 0.33. Aug-19; 0.00; 50.459; 0.087; 0.17; 0.169; 0.33. Sep-19; 0.00; 55.259; 0.093; 0.17; 0.185; 0.33. Oct-19; 0.00; 19.872; 0.069; 0.35; 0.041; 0.20. Nov-19; 0.00; 19.065; 0.075; 0.393; 0.040; 0.210. Dec-19; 0.00; 31.339; 0.108; 0.345; 0.124; 0.396. Jan-20; 0.00. Feb-20; 0.00. Mar-20; 0.00. TOTAL; 0.00; 352.531; 0.760; 0.22; 1.152; 0.33. GENERATION AUX. &GT (MUs) RSD; Remarks/Action Plan. MONTH; Target; GEN.; AUX; %; GT; %; Auxiliary losses are within permissble limit.. Apr-19; 90; 164.170; 0.330; 0.20; 0.210; 0.13. May-19; 180; 282.240; 0.550; 0.19; 0.390; 0.14. Jun-19; 190; 268.400; 0.550; 0.20; 0.340; 0.13. Jul-19; 200; 206.351; 0.467; 0.23; 0.221; 0.11. Aug-19; 200; 273.786; 0.479; 0.17; 0.431; 0.16. Sep-19; 180; 184.498; 0.359; 0.19; 0.254; 0.14. Oct-19; 100; 93.505; 0.181; 0.19; 0.129; 0.14. Nov-19; 90; 98.081; 0.208; 0.21; 0.118; 0.12. Dec-19; 80; 115.541; 0.242; 0.21; 0.142; 0.12. Jan-20. Feb-20. Mar-20. TOTAL; 1310; 1686.572; 3.366; 0.20; 2.235; 0.13. GENERATION AUX. &GT (MUs) ASHP; Remarks/Action Plan. MONTH; Target; GEN.; AUX; %; GT; %; Auxiliary losses are within permissble limit.. Apr-19; 20; 25.596; 0.025; 0.10; 0.045; 0.17. May-19; 74; 83.027; 0.067; 0.08; 0.127; 0.15. Jun-19; 74; 85.405; 0.070; 0.08; 0.127; 0.15. Jul-19; 81; 78.540; 0.075; 0.10; 0.122; 0.16. Aug-19; 81; 88.695; 0.077; 0.09; 0.135; 0.15. Sep-19; 70; 85.799; 0.074; 0.09; 0.130; 0.15. Oct-19; 34; 59.378; 0.063; 0.106; 0.123; 0.207. Nov-19; 28; 16.641; 0.016; 0.096; 0.061; 0.367. Dec-19; 42; 10.832; 0.026; 0.24; 0.041; 0.38. Jan-20. Feb-20. Mar-20. TOTAL; 504; 533.913; 0.493; 0.09; 0.910; 0.17. GENERATION AUX. &GT (MUs) MHP; Remarks/Action Plan. MONTH; Target; GEN.; AUX; %; GT; %; 1. Auxiliary losses are within permissble limit. 2. Power generated is carried to LV side of Generator Unit to step up Transformer through the 11 KV Aluminium cables (size- 500mm² at PH-1&2 and 800mm² at PH-3&4) for each Phase, i.e. Total 6 No. Aluminium cables have run load with length of each cable 105 meter. The losses in these cables are also contributing to GT Losses. 3. G.T. losses are higher as theT/Fs installed at PH-1,PH-2,PH-3 &PH-4 of Mukerian Hydel Project are very old and were commissioned during 1983,1988 & 1989. 2Nos. GTs of 15MW machines at PH-1&2 have been replaced in May-June, 2018. and 3 nos. GTs. of 19.5MW machines at PH-3&4 have been replaced in Apr-May-2019.other GTs will be replaced in phased manner. Further 2 nos. Power T/Fs of capacity 40/50MVA & 50MVA,132/66kv, 1 no. T/F of 8/4/4MVA, 132/11kv are also installed at MPH-4 which also contribute to GT losses at MPH-4. 4. Work for replacement of 132KV CT/PTs as per State Grid Code is in progress.. Apr-19; 10; 12.161; 0.136; 1.12; 0.170; 1.40. May-19; 10; 92.756; 0.285; 0.31; 1.351; 1.46. Jun-19; 94; 109.109; 0.438; 0.40; 1.592; 1.46. Jul-19; 112; 113.835; 0.438; 0.38; 1.719; 1.51. Aug-19; 116; 105.530; 0.440; 0.42; 1.455; 1.38. Sep-19; 116; 144.052; 0.487; 0.34; 2.023; 1.40. Oct-19; 116; 113.497; 0.428; 0.38; 1.448; 1.28. Nov-19; 116; 114.191; 0.385; 0.34; 1.480; 1.30. Dec-19; 116; 109.011; 0.415; 0.38; 1.391; 1.28. Jan-20. Feb-20. Mar-20. TOTAL; 806; 914.142; 3.452; 0.38; 12.629; 1.38. (iii) Divisions with Losses more than 25%. As per energy audit of FY 2019-20, 12 nos. divisions under PSPCL has registered distribution losses more than 25 % which are summarized as under :- Detail of No. of Feeders Category wise. Sr. No.; ZONE; CIECLE; DIVISION; %age LOSSES; Cat-1; Cat-2; Cat-4; UPS; AP3p3w; Total. 1; Border; S/U Asr; West Amritsar; 33.18; 9; 0; 9; 24; 89; 131. 2; Border; S/U Asr; S/U Amritsar; 31.21; 15; 8; 3; 31; 87; 144. 3; Border; S/U Asr; Ajnala; 31.62; 6; 0; 4; 29; 93; 132. 4; Border; Tarntaran; City Tarntaran; 25.85; 15; 1; 2; 18; 78; 114. 5; Border; Tarntaran; Patti; 40.28; 17; 0; 1; 18; 105; 141. 6; Border; Tarntaran; Bhikhiwind; 47.14; 5; 0; 4; 22; 89; 120. 7; South; Sangrur; Patran; 30.24; 13; 3; 2; 21; 111; 150. 8; South; Sangrur; Lehragaga; 26.03; 27; 0; 0; 17; 136; 180. 9; West; Bathinda; Bhagta Bhai Ka; 26.46; 17; 0; 1; 18; 137; 173. 10; West; Ferozepur; Zira; 29.22; 24; 1; 0; 40; 156; 221. 11; West; Faridkot; Baghapurana; 27.72; 9; 0; 0; 23; 109; 141. 12; West; Muktsar; Malout; 33.28; 25; 1; 0; 29; 56; 111. To reduce the Distribution loss PSPCL is taking following measures to reduce the losses below 15%. - Checking of Theft: The main reason of losses under these divisions is huge power theft. Most of these divisions fall under the border belt which is the epicenter of power theft. PSPCL is striving hard to curb theft in these divisions by conducting surprise raids. It is pertinent to mention that sometimes PSPCL employees have been Gheraoed and Manhandled by local public and various kissan unions during checking of connections under these divisions. However, PSPCL is striving hard to check power theft in these areas. Moreover, People pertaining to these areas are making aware about the consequences of power theft by holding meetings with local leaders and public. Sr. No.; ZONE; CIECLE; DIVISION; No. of Connections Checked; Cases Detected; Leakage of Revenue Detected (In Lacs). 1; Border; S/U Asr; West Amritsar; 19220; 1462; 220.68. 2; Border; S/U Asr; S/U Amritsar; 24562; 1307; 208.78. 3; Border; S/U Asr; Ajnala; 19981; 1228; 200.81. 4; Border; Tarntaran; City Tarntaran; 11344; 884; 152.37. 5; Border; Tarntaran; Patti; 10691; 754; 260.17. 6; Border; Tarntaran; Bhikhiwind; 6966; 736; 177.16. 7; South; Sangrur; Patran; 3719; 2035; 269.41. 8; South; Sangrur; Lehragaga; 4103; 1134; 144.42. 9; West; Bathinda; Bhagta Bhai Ka; 1212; 356; 75.82. 10; West; Ferozepur; Zira; 16046; 846; 170.12. 11; West; Faridkot; Baghapurana; 5129; 463; 119.15. 12; West; Muktsar; Malout; 1836; 388; 188.01. - Shifting of Meters outside the consumer premises: The status of shifting the meters outside consumer premises of these high loss divisions is as below. Name of Division; Total Meters to be Shifted; Nos. of Meters where severe resistance from Kissan Unions and Public being faced; Meters that can be shifted without any Resistance; Schedule for shifting of Balance Meters. 2019-20; 2020-21. West Amritsar; 2281; 0; 2281; 500; 1781. S/U Amritsar; 11291; 2500; 8791; 3000; 8291. Ajnala; 899; 899; 0; 0; 899. City Tarntaran; 9229; 1436; 7793; 700; 8529. Patti; 10980; 5673; 5307; 600; 10380. Bhikhiwind; 5173; 2968; 2205; 500; 4673. Patran; 3143; 3143; 0; 0; 3143. Lehragaga; 26113; 26113; 0; 0; 26113. Bhagta Bhai Ka; 9933; 9933; 0; 0; 9933. Zira; 1216; 0; 1216; 400; 816. Baghapurana; 24697; 24697; 0; 3000; 21697. Malout; 11909; 0; 11909; 5000; 6909. - Replacement of Electromechanical meters with Electronic meters: The status of replacement of electromechanical meters under these high loss divisions is as below. Name of Division; Total Electromechanical meters to be replaced; Schedule for replacement of Balance Electromechanical Meters. 2019-20; 2020-21. West Amritsar; 488; 488; 0. S/U Amritsar; 3130; 3130; 0. Ajnala; 0; 0; 0. City Tarntaran; 0; 0; 0. Patti; 820; 680; 140. Bhikhiwind; 0; 0; 0. Patran; 2195; 800; 1395. Lehragaga; 5936; 300; 5636. Bhagta Bhai Ka; 1511; 511; 1000. Zira; 903; 903; 0. Baghapurana; 5800; 3425; 2375. Malout; 3145; 2010; 1135. *Note: Stiff resistance faced from Kisan Union to replace Electromechanical Meters. |
| 6.1 Reduction in T&D losses | - to complete shifting of meters outside consumer premises within 6 months of the issue of this Tariff Order. | iv)Update status of meter shifted is as under: a): Meter Shifting Progress related to APDRP Areas Sr. No.; Name of Contractor; Quantity as per IOs Issued; Shifted up-to 31.12.19; Balance to be shifted; Target Date March 2020. 1; M/s L&T (02 No. Towns); 240945; 240945; 0; 0. 2; M/s Godrej (16No. Towns); 193951; 193951; 0; 0. 3; 15 Nos. Towns; 499774; 493744; 6030*; 6030. 4; M/s Nucon Switchgear Pvt. Ltd. (07 Nos. Towns); 68577; 68577; 0; 0. 5; M/s Shreem Electric Ltd. (06 No. Towns); 82550; 82550; 0; 0. Total; 1085797; 1079767; 6030; 6030. *In Amritsar town for shifting of meter outside consumer premises, the contractor M/s UBI Tech Faridabad has left the work by shifting 127043 no. of meters out of the total scope of work of 202791 no. of meters. For remaining 75848 pending no. of meters, 31476 is to be carried out departmentally with labour outsourced and the balance 44372 no. of meters have been included in the scope of the IPDS scheme for Amritsar city. As per the latest status received from the office of Dy. CE/DS, Sub-Urban Circle, Amritsar, 25446 nos. meters have been shifted outside the consumer premises out of total 31476 nos. upto 31.12.2019 and the balance meters will be shifted at the end of month March 2020. Under IPDS scheme, there is a provision for shifting 1,15,064 no. meters outside the consumer premises. Upto 31.12.2019, 83931 no. meters have been shifted by the turnkey contractor and the target has been set to get the balance meters shifted by March, 2020. b) Meter Shifting Progress related to Non-APDRP Areas: Shifting of energy meters outside the consumers premises are covered under following 3 no. schemes: - 19 nos. T&D Loss reduction schemes: Work of shifting of 20.81 lac meters identified in Phase-1 under 19no. T&D loss Reduction Schemes stand completed. - 18 Nos. T&D Loss reduction Schemes: Out of 17.29 Lac meters, complete work of 7.94 Lac connections entrusted to this office stands completed and balance work of Balance work of 9.35 Lac meters out of 17.29 Lac meters covered in Phase-II is being monitored and executed by DS Organization as such its progress and target for completion may be given by the office of Dy.CE/Tech to Director/Distribution, PSPCL, Patiala. - DDUGJY Scheme: Under DDUGJY scheme, 27033 nos. meters have been identified for shifting of meters, out of which work of 18355 nos. meters stand completed as on 31.12.19. Balance work is likely to be completed by March, 2020 - Status of shifting of meters outside consumer premises ending 12-2019 is as under: Name of Scheme; Scope of Work; Progress of meters shifted outside consumer premises from 01-10-2019 to 31-12-2019; Total balance meters to be Shifted as on 31-12-2019; Nos. of Meters where Severe Resistance from Kissan Unions and Public is being Faced; Meters that can be shifted without any Resistance; Schedule for Shifting of Balance Meters. 2019-20; 2020-21. R-APDRP (Part-B ); 0.06; 0; 0.06; 0; 0.06; 0.06; -. DDUGJY; 0.10; 0.01; 0.09; 0; 0.09; 0.09; -. IPDS; 0.47; 0.16; 0.31; 0; 0.31; 0.31; -. In House; 5.04; 0.03; 5.01; 2.11; 2.90; 0.97; 4.01*. TOTAL; 5.67; 0.20; 5.47; 2.11; 3.36; 1.43; 4.01. - *The work of shifting of balance meters under RAPDRP (Part-B), IPDS and DDUGJY schemes shall be completed by 31-03-2020. *Estimates for 2.39 Lac Meters comes under scope of In-house meter shifting have been prepared under 6 Circles and Tendering is under progress for labour outsourcing. |
| 6.1 Reduction in T&D losses | - To replace all single phase electro-mechanical meters with electronic meters during FY 2019-20 | (v) Replacement of Balance Electromechanical Meters with Electronic Meters :- - The status of progress of replacement of electromechanical meters with Electronic meters mentioned is reproduced as under :- Description; SAP area; Non-SAP area. Balance as on 31.03.2018; 231448; 374703. Balance as on 30.06.2018; 223024; 370713. Balance as on 30.09.2018; 209371; 364997. Balance as on 31.12.2018; 202508; 359934. - From 31-12-2018 to 31-12-2019, PSPCL has replaced 125742 number Electromechanical Meters as under :- Sr No; Area; Nos. of Meters Replaced.. 1; SAP Area; 35363. 2; Non SAP Area; 90379. 3; Total; 125742. Now, total 4.37 Lac electromechanical meters are balance to be replaced with electronic meters as on 31-12-2019 as under :- Description; SAP area; Non-SAP area; Total; Schedule of Replacement of Meters. 2019-20; 2020-21 ( Up to September-2020). Balance as on 31.12.2019; 167145; 269555; 436700; 46624; 390076. PSPCL will replace balance electromechanical meters as per above schedule. |
| 6.2 Metering | - 100% Metering The Commission directs the distribution licensee to implement the mandate of the Act regarding 100% metering of consumers by the end of next MYT control period. | (i) 100% Metering Although The Electricity Act provides for 100% metering of all consumers but installation of meters on a category of consumers which are being provided free power by GoP will not serve any purpose except recording energy, as meters have already been provided on all feeders. In case 100% metering on AP feeders is carried out, there is no doubt this would certainly make AP energy accounting more accurate but this scheme would also require considerable investment in manpower and equipments keeping in view the large expanse of network and may not justify the return on investment. Regarding the direction of the commission to provide 100% metering to all consumers within five years starting from April 2018. It is submitted as follows:- - Feeders supplying power to Agriculture Pump Sets have been segregated and are metered. Each month meter readings of all these feeders are submitted to hon’ble regulator. - For reducing DS losses specifically in AP, a key initiative has been implementation of HVDS which is a more direct measure that helps in loss reduction and helps in curtailing power leakage. This has not only helped in bringing down the line losses but also protects against pilferage as hooking at high voltages is extremely dangerous and difficult. This system has also benefits consumer by enhancing the performance of the agriculture pump sets, as the 11KV supply line is extended until the load point. To ensure that all future AP connections are released on HVDS with DT metering PSPCL has already adopted a policy mandating HVDS and DT Metering on all new AP connections. A project for FEEDER SEGREGATION and AP CONSUMER METERING IN KANDI AREA under DDUGJY scheme has been initiated at a cost 191 Cr for better accounting of AP energy in Kandi feeders. - PSPCL is using an online system to record AP feeder energy readings, where data is submitted by concerned Sr XEN Grid Maintenance and cannot be subsequently modified. Same data is shared on a monthly basis with PSERC. The data of about 1800 AP feeders is being received under AMR/ REC Rural Feeder Monitoring projects and is being shared with PSERC. - Further if 100% metering is implemented, recording monthly readings using AMR/ Smart meters not only involves connectivity issues but also requires huge infrastructure, additional manpower and software licenses cost. No utility in India has carried out AMR/ Smart metering for such a large number of consumers. So far only utilities have carried out AMR of large consumers numbering from hundreds to few thousand.Technology changes in mobile networks: It has been informed by the vendor implementing AMR project in PSPCL that the modems already purchased by PSPCL has become obsolete as these modems are compatible with 2G networks, 2G SIMs and are not compatible with newer 4G SIM cards available from Mobile Network operators. The vendor has recommended replacing all theses modems already purchased by PSPCL. Manually recording meter readings shall required large manpower, keeping in view large expanses of rural PSPCL network. Assuming approximately 13.78 Lac total AP consumers an investment of approx. 1143.74 Cr. shall be required for AMR/ Smart meters, Data Centre Servers and Software Licenses. Periodic replacement of defective meters or modems will also involve cost. - PSPCL is going to assess the T&D Losses on AP Feeders and 1% AP Feeders to be covered under 100% metering and T&D Losses would be computed by engaging independent agency as per the direction of Hon'ble PSERC. - PSPCL under instructions of Punjab Govt and in collaboration with M/S J-PAL and World Bank, has launched a DBTE scheme Pani Bachao Paise Kamo on 256 no AP feeders. In this scheme farmers are being asked to install meters on their agriculture pumpsets, if they want to receive benefits under this scheme. PSPCL has taken multiple measures to enhance the energy accounting on agriculture networks, such as enhancing the sample size of consumer meters, 100% AP feeder metering, segregation of AP feeders. Policy has already been changed, mandating all new AP connections to be released on HVDS, installing meters on new AP connections. However, in spite of the above, various Kissan Unions are not allowing PSPCL to install meters at their AP connections. |
| 6.2 Metering | - Introduction of prepaid and smart meters PSPCL shall submit a complete action plan with target dates for introduction of new metering technologies such as pre-paid meters/smart meters for different classes of consumers by 1st Sept. 2019. | - LT CT Smart Meter It is submitted that LT CT meters are being used for industrial/commercial/DS category of consumers having sanctioned load equal to or more than 25 KW but less than 100 KW. AMR for approximately 100 such meters has been carried out in Ludhiana city and these meters are also transmitting data to data centre via external modem similar to HT meters as such online reading and online billing for these meters is being carried out. The remaining quantity of LT CT meters which is not transmitting data using AMR is approximately 27,000 Nos. Accordingly, Tender Enquiry no MQP-154 for procurement of 34,000 LT CT Smart meters has been floated which was scheduled to be opened on 13.12.2019, but none of the firm participated, The Corrigendum incorporating the changes as decided by PSPCL in accordance with the 'PREFERENCE TO MAKE IN PUNJAB: ORDERS 2019' as well as representations of the firms will be floated soon. It is expected that PO for these meters shall be placed by 25.04.2020 and supply of LT CT smart meters shall commence from 25.05.2020 in ME labs and shall be completed by 25.07.2020 and entire lot is expected to be commissioned and integrated in PSPCL system by April, 2021. Thus, all consumers with connected load equal to or more than 25KW shall be on AMR thereafter and online billing/reading shall be achieved. It is also mentioned that Purchase Order No 6069/M-137/MQP-125A/PO(M) dated 20.09.2019 has been placed on M/s Secure Meters Limited for procurement of 2,500 No. LT CT compact meters of rating 40-200 Amp, having inbuilt Modem and CT sets. Out of these 2500 no meters, 1600 no meters have been received at ME Lab Ludhiana and are under testing. Further, 900 No. meters are under inspection and are likely to be available in ME labs by 31.12.2019. These meters are suitable for GPRS technology and are less prone to low voltage problems caused due to carbonization. These meters shall also be utilized for AMR. These LT CT compact meters shall be used for MS consumers and are likely to be installed in Ludhiana city. B. Three phase Whole Current Smart Meter: Tender Enquiry No MQP-145 has been floated on 4.7.2019 for procurement of 96,000 No. Three phase Whole Current Smart Meters. Out of these, approx 52,000 meters are to be installed on AP consumers being fed from 250 No feeders identified under DBTE scheme. Rest of the meters will be installed on industrial and commercial connections having sanctioned load greater than 20KW and up to 25KW. Due date of opening of Tender Enquiry was 19.11.19, but only one firm submitted tender documents along with samples. The case for opening of Tender is under process. It is also intimated that above mentioned tender enquiry stipulates smart meter either on 4G or NBIOT based on 4G technology with fall back on 3G/2G. The broad timeline proposed for procurement of these meters is as under: S No; Activity; Tentative Date. Due date of opening; 03.01.2020. Sample Testing of smart meters at ME lab and opening of price bid; 14.02.2020. Finalization of Purchase case and submission of agenda to competent authority; 28.02.2020. Placement of LOA/LOI/PO after receipt of decision of Competent authority.; 20.03.2020. Receipt of Smart meters in ME labs.; 21.04.2020 (Total Material shall be received progressively thereafter in six equal monthly instalments). As tabulated above, the supply of three phase whole current smart meters shall commence in ME labs during April, 2020 and thereafter @16,000 meters per month and supply shall be completed by October, 2020. The implementation period (i.e. commissioning of Head End System, installation of meter along with SIM and integration of meter data with MDM of PSPCL etc) is 6 months after receipt of material in Labs. As such, all these smart meters are likely to be commissioned and integrated in the system between October, 2020 and March, 2021. These smart meters shall be used as pre-paid/post-paid meters. C. RF Meters (three phase and single phase): RF meters can be used to eliminate manual intervention in taking readings of meters and to capture/communicate real time data. Accordingly, a pilot project was got executed free of cost at Patiala during 4/2019 to 7/2019 wherein single phase and three phase meters along with DCUs were used to form mesh network to collect the data. The working of this pilot project was studied by the committee which has submitted its report. Case has been approved by competent authority and approximately 1.20 lac RF meters (90,000 no. single phase and 30,000 no. three phase meters) shall be installed/commissioned in Agar Nagar Special Division, Ludhiana city. These meters shall be installed in cluster. These RF meters are capable to transmit data online (by using DCUs) and are similar to smart meters except that disconnection feature is not available in RF meters. The broad timeline proposed for procurement of these meters is as under: S No; Activity; Tentative Date. Floating of N.I.T.; 31.12.2019. Pre-bid Meeting after floating N.I.T.; 14.01.2020. Due date of opening after incorporating representations received from firms during prebid meeting as well as related to 'Preference to Make in Punjab: Orders 2019'; 13.02.2020. Sample Testing of smart meters at ME lab and opening of price bid; 13.04.2020. Finalization of Purchase case and submission of agenda to competent authority; 29.04.2020. Placement of LOA/LOI/PO after receipt of decision of Competent authority.; 05.05.2020. Receipt of RF meters in ME labs.; 08.07.2020 (Total Material shall be received progressively thereafter in six equal monthly instalments). As tabulated above, the supply of these whole current single phase and three phase RF meters shall commence in ME labs during July, 2020 and supplies shall be completed by January, 2021. The implementation period (i.e. commissioning of Head End System, installation of meter along with DCUs and integration of meter data with MDM of PSPCL, billing etc) is 6 months after receipt of material in Labs. As such, all these RF meters are likely to be commissioned and integrated in the system between January, 2021 to June, 2021. D. Single phase Prepaid meters: TE no MQP-146/PO(M) has been floated for procurement of 10,000 no Prepaid Single Phase meters with extended date of opening as 20.12.2019. However, none of the firm has submitted its tender on due date of opening. Tender will be refloated since the due date of opening has already been extended twice. Also, Commercial Clauses related to 'Preference to Make in Punjab: Orders 2019' will be incorporated. Regarding prepaid HT & LT CT meters, It is intimated that prepaid metering can be done only on whole current meters. It is not possible for CT connected and CT/PT connected meters. However, Electricity Act-2003 has provision for installation of pre-paid meter for consumers and in that case no security is required to be deposited/maintained. Electricity Supply Code-2006 and 2014 also have similar provisions. Prepaid metering is available in whole current meters only (single and three phase) and not in LT CT meters or HT meters. This fact has also been verified by representatives of M/s. L&T limited and M/s. Secure Meters (copies of e-mail attached along with). For industrial consumers as far as SP connections are concerned, pre-paid metering is thus possible. For MS connections having sanctioned load up to 25kw, pre-paid three phase whole current meters can be used but it is not possible to use LT CT pre-paid or HT pre-paid meters . |
| .6.2 Metering | - AMR of HT/MS consumers PSPCL is directed to complete AMR of HT/MS consumers during FY 2019-20. | AMR of HT Consumers: AMR billing report of SAP and Non-SAP HT/LS Consumers for quarter ending December, 2019. Month; Count of Consumer Meters- AMR reading given for Billing Purpose. SAP; Non-SAP (excluding IPDS); Total. 21st of month; 30/31st of month; 21st of month. October, 2019; 5859; 762; 1328; 7949. November, 2019; 5891; 759; 1338; 7988. December, 2019; 5979; 793; 1357; 8129. There are 1302 MS consumers on HT line in SAP Area. Out of these, 921 MS/HT Consumers are covered under AMR. For AMR of H.T consumers in 97 towns covered under IPDS, the WO for supply, installation and commissioning of modems has been issued. |
| 6.2 Metering | iv) Accreditation of existing meter testing labs from NABL PSPCL is directed to get accreditation of its existing testing labs from NABL as per provisions of Supply Code. | It is submitted that the requisite training regarding understanding and implementing IS/ISO/IEC 17025-2017 including Management System and Documentation and internal Auditing shall be imparted to 15 no. officers/officials from Metering Organisation in the month of Jan 2020 and approval for the same has been given by the Competent Authority. After that process regarding NABL accreditation for ME Lab Ludhiana and ME Lab Patiala shall be started. |
| 6.2 Metering | - (v)PSPCL shall ensure on site testing of all HT/EHT metering equipments including CTs/PTs. In case PSPCL is unable to develop its own testing capabilities, a third party may be engaged to test check atleast 10% of the EHT connections in next 6 months. A report be submitted to the Commission by Dec. 2019. | PSPCL is in the process of procuring on site testing Mobile Van with NABL accreditation for testing of HT/EHT meter equipments (i.e. upto 66 KV class including CTs /PTs). This mobile testing van shall comprise of 1 no. CT/PT testing equipment and 1 no. fully automatic two position meter testing equipment. Tender enquiry MQP-141/2018-19/PR for the same was floated with due date of opening as 24.10.19. Pre bid meeting was held on 26.09.2019 and only two no. firms participated in that meeting. Subsequently on the request of other firms who could not participate in pre-bid meeting dated 26.09.2019, another pre bid meeting held on 16.10.2019 in which total 6 no. firms participated including previous 2 no. firms. All the firms vide letter dated 18.10.19 were requested to submit their suggestions/observations on the tender specification. No bid of the any firm was received up to due date of opening of tender i.e. 24.10.2019. The firms have submitted contradictory comments on the specification. Another bre-bid meeting to discuss the contradictory observations/suggestions given by the firms shall be scheduled during Jan 2020. After compiling the observations/suggestions of the firms, corrigendum for the tender enquiry shall be issued. However, to engage third party for testing 10% EHT (19 no. 66KV) connections, open tender shall be floated separately. The case for the same is under process. The tender shall be floated in the month of Feb 2020. . |
| 6.3A(i) Status of Central Schemes | - R-APDRP - PSPCL shall ensure successful completion of the SCADA project within the stipulated time. | SCADA/DMS – Status of audit by TPIEA The SCADA/DMS audit by TPIEA in three control centres at Jalandhar, Amritsar and Ludhiana and one DR centre at Patiala is underway and the town wise progress of the phase-1 activity is as under: Amritsar – 80% Jalandhar – 80% Ludhiana – 80% Patiala (DR) – 80% It is expected that the Phase-2 verification will start at Amritsar by 6th February 2020 and shall be complete by 20th February 2020. |
| 6.3A(i) Status of Central Schemes | (ii)PSPCL shall submit status of conversion of loan to grant under the R-APDRP scheme. | The work of 46 no. towns has been completed. However financial closing of towns is under progress. The financial closure documents of 38 nos. of completed towns have been submitted to Nodal agency PFC to claim final tranche of loan/grant. Out of 38 nos. towns, the final tranche of 10 % loan of 18 towns has been received. Further, it is stated that no loan amount has been converted to grant as the procedure for conversion of loan to grant is under consideration of MoP/GoI as conveyed by PFC. turnkey contractors in the month of Sept,2017 with a completion period of 24 months i.e. upto Sept,2019. The completion date has been extended upto March, 2020 by PFC.. |
| 6.3 Status of Central Schemes | - IPDS and DDUJJY PSPCL shall implement the schemes within the time period allotted by GoI and submit quarterly report to the Commission. | a) IPDS Scheme: Work order for executing the IPDS scheme on full Work orders for executing the IPDS scheme on full turnkey basis in 20 No. circles of Punjab State were issued to the turnkey contractors in the month of Sept,2017 with a completion period of 24 months i.e. upto Sept,2019. The completion date has been extended upto March, 2020 by PFC. The work of 13 No. circles stands completed and the target has been set to complete the work of balance 7 No. circles by March, 2020. b) DDUGJY Scheme: Execution of awarded work in 5 nos. packages for scope of work covered in 20 no. districts under DDUGJY is under progress. The package wise status of progress achieved in % age as on 31.12.2019 on the basis of cost of erection completed is as under: Contractor; Package No.; % progress achieved. M/s H R; I; 43.65 %. M/s Star; II; 89.6 %. M/s PP; III; 66 %. M/s Nucon; IV; 59.69 %. Ms Star; V; 96.10 %. The scope of work in all the 20 no. SansadAdarsh Gram Yojana (SAGY) Villages adopted by concerned MPs stands completed. Under this project total works amounting to Rs. 176.49 Cr. Approx. have been completed (overall progress of 70.05% of awarded works). However in the matter of monthly targets for completion of projects, it is submitted that work got delayed due to imposition of model code of conduct during Parliamentary elections 2019, no shut downs due to high demand of electricity in summer/ paddy season, and non- availability of Right Of Way in fields due paddy crop cultivation. PSPCL is intended to complete the project in all the 20 no. districts by March 2020. |
| 6.3A Status of Central Schemes | (C) PSPCL is directed to submit the status of implementation of MIS in Non APDRP Towns in the State. | (C)The office of Chief Engineer/RE & APDRP has been updating the progress of DDUGJY scheme regularly on MIS Portal. |
| 6.4(i) AP consumption | - AMR of AP feeders The Commission directs PSPCL to ensure availability of monthly AMR data along with feeder wise sanctioned load of AP consumers of all AP feeders without any further delay. | S. No.; Status; Count (In Nos.); Data received (In Nos.); Remarks. 1; AP feeders covered under 11kV Rural Feeder Monitoring Scheme (RFMS) by RECTPCL, New Delhi; 3650; 2868*; For the balance meters, issues like meter compatibility problem, optical cable disconnection, network failure etc. are being addressed on priority.. 2; AP feeders covered under AMR Project; 760; 610; Hardware declared faulty at 14 no. sub-stations. Since, no spare units available now, these 150 no. feeders being shifted to 11kV RFMS of RECTPCL.. 3; AP feeders covered under MDAS (R-APDRP) project; 250; 116; Hardware such as UPS/ batteries at 19 no. sub-station needs replacement/ repair and 51 no. meters are incompatible. The work already undertaken and likely to be completed by 15.02.2020.. 4; Additional nodes to be brought under 11kV RFMS; 1199; --; M/s RECTPCL instructed to install modems at these sites ensuring completion by Feb’20 end.. Total 11kV AP Feeder meters in Punjab; 5859; 3594. NOTE: *Out of 3650 no. feeders, 894 no. are DLMS compliant and 2756 no. meters are non-DLMS. RECTPCL although has been successful in acquiring data on remote from non-DLMS meters but all the parameters are not available due to protocol implementation issue at the modem/ server end. For this, a Non-Disclosure Agreement has since been signed and subsequently, protocol details from meter OEM i.e. M/s L&T has been handed over to RECTPCL. Now, the Protocol/ API’s has been successfully implemented by the firm on pilot basis which is presently under validation. After validation, AMR data from 2868 no. feeders under 11kV RFMS will be made available in addition to in-house AMR and MDAS from March'20 onwards.. Earlier the AMR data of 3200 nos. feeders were available during 2015-16 but due to introduction of 11kV Rural Feeder Monitoring Scheme by RECTPCL, New Delhi, the majority of rural/AP feeders were shifted under their scope. As on date, modems on 3650 no. AP feeders have been installed under 11kV RFMS by implementing agency, out of which 2756 nos. feeders have non-DLMS compliant energy meters. Currently, the data from 2756 nos. non-DLMS meters under is not being captured by implementing agency due to mismatch in modem/meter Protocol/ API. As such, the Non-Disclosure Agreement between M/s L&T, M/s Lampex (11kV RFMS implementing Agency), RECTPCL and PSPCL has been signed. The meter communication Protocol details have been handed over by L&T to RECTPCL. Now, RECTPCL has agreed to read AMR data of all DLMS and non-DLMS meters by 15.02.2020. - the AMR data of 3 phase, 3 wire purely AP Feeders upto the month of December 2019 has been sent to Hon'ble Commission for further submission to Hon'ble PSERC. Moreover, the online access of AMR system has already been provided to PSERC( with effect from 13.09.2017). Updated Status of AMR data is as under:- S.no; Status; Count (In nos); Data received; Remarks; Timeline and agency to make it functional. 1.; AP feeders covered under 11KV Rural Feeder Monitoring Scheme (RFMS) by RECTPCL New Delhi.; 3650; 2868; For the balance 782 no. meters issues likes meter compatibility problem, optical cable disconnection, network failure etc, are being addressed on priority and team failed visits have been planned.; 31-03-2020 (RECTPCL). 2.; AP feeders covered under AMR project.; 760; 610; Hardware declared faulty at 14 no. sub-stations. Since, no spare units available now, these 150 no. feeders have been shifted to 11KV RFMS of RECTPCL.; 31-03-2020 (RECTPCL). 3.; AP feeders covered under MDAS (R-APDRP) project.; 250; 118; Hardware such as UPS/Batteries at 19 no substations needs replacement/repair and 51 no. meters are incompatible. The work has already been undertaken.; 31-03-2020 (PSPCL-IT). 4.; Additional nodes to be brought under 11KV RFMS.; 1199; ------; M/s RECTPCL instructed to install modems at these 1199 no. sites ensuring completion by Feb, 2020 end. However, as per latest communication from RECTPCL, the firm is yet to take up work as the approval from ministry is awaited at their end.; With in one month from the date of taking up of the work by RECTPCL.. Total 11KV AP feeder meters in Punjab.; 5859; 3594. Out of 3650 no. feeders, 894 no. have DLMS complaint energy meters for which monthly pumped energy reports are being generated and 2756 no. meters are non-DLMS. RECTPCL although has been successfully in acquiring data on remote from non-DLMS meters but all the parameters are not available due to protocol implementation issue at the modem/server end. For this, a non-disclosure agreement has been signed and subsequently, a protocol details from meters OEM i.e. M/s L&T has been handed over RECTPCL. Now, the protocol/API's for billing parameters has been successfully implemented by the firm w.e.f 05-02-2020 which has been validated by PSPCL. Now, AMR data from2858 feeders under 11KV RFMS will be made available in addition to in-house AMR and MDAS data ensuring 100%AMR data availability from March 2020 onwards. Regarding submission of monthly AMR data along with feeder wise sanctioned of AP consumers of all AP feeder, it is submitted that the data regarding sanctioned load is manually punched and uploaded on the Distribution Return Portal of PSPCL website and the same is submitted to Hon'ble PSERC w.e.f. September, 2019 onwards on the prescribed format . |
| 6.4 AP consumption | - Kandi area feeders The Commission directs PSPCL to submit the physical progress of segregation of kandi area feeders / providing of meters on quarterly basis. PSPCL is further directed to submit the data of segregated feeders/100% metered feeders along with monthly pumped energy data of AP feeders. | (ii) Kandi Area Feeders Rs.191.19 Cr. has been sanctioned by MoP/GoI for feeder segregation / AP consumer metering in five districts of Kandi Area in the State of Punjab under DDUGJY. The work of feeder segregation / AP consumer metering in Kandi Areas of 5 no. districts (Gurdaspur, Hoshiarpur, SBS Nagar, Rupnagar, SAS Nagar) in the State of Punjab under DDUGJY were awarded to various companies on 01.12.2017 (for 4 Packages) and 15.11.2018 (for 1 Package) with completion period of 24 months i.e. up to 30.11.2019 and 14.11.2020 respectively. Due to stiff resistance from AP consumers and Kissan Unions, the progress remained very slow and very less progress was achieved under this project. However, with the intervention of Punjab Govt. and PSPCL management, the pace of work has now been picked up and works are likely to be completed by September’ 2020 for Package no. 2 to 5 and that of Package no. 1 by November’ 2020. Package wise ,status of progress is as under: Contractor; Package No.; No. of feeders in WOs; Progress (No. of feeders). for Load Segregation; for AP Metering; Total; for Load Segregation; for AP Metering. M/s Jay Bee; I; 10; 37; 47; 5 (WIP); 0. M/s Star; II; 12; 22; 34; 12 (WIP); 0. III; 28; 53; 81; 3 (Completed) 21 (WIP); 0. M/s Nucon; IV; 9; 24; 33; 4 (WIP); 0. V; 23; 58; 81; 1 (Completed) 12 (WIP); 0. Total; 82; 194; 276; 04 (Completed) 54 (WIP); 0. The work of 4 no. feeders after load segregation have been physically completed. However these new feeders are yet to be energized whlch shall be done after attending few observations of Chief Electrical Inspector and coordinating with DS organization. As such the data related to pumped energy of segregated feeders shall be sublimed after the energization of the same. |
| 100% (iii)metering | - 100% metering on A.P. consumers fed from urban feeders The Commission directs PSPCL to complete 100% metering of all such AP connection fed from urban feeders. The Commission reiterates its directive that after due validation, consumption of only metered AP consumers fed from urban feeders shall be considered while computing AP consumption. | ((iii) 100% metering on A.P. consumers fed from urban feeders The delay has been on account of resistance from Kissan Unions and there was no intention of PSPCL to non-comply with the directives. At present only 890 AP connections are pending where Kissan Unions are not allowing PSPCL employees to install meters. The detail of balance meters to be installed on AP consumers fed from Urban Feeders is as under: Sr. No.; Name of Circle; Balance Meters to be Installed. 1; Suburban Amritsar; 267. 2; City Amritsar; 168. 3; Tarntatan; 69. 4; Bathinda; 386. TOTAL; 890. Recently Sr. Xen DS Division Patti along with his staff started shifting of AP Motors from 11 KV Garden Colony Urban Feeder and 11 KV Patti City Urban Feeder then Kissan Union and local Leader along with his supporters did Gherao the official of PSPCL and also did manhandling with the employees which results into serious injuries and one no. employee also got hospitalised during this incident. |
| 100% (iv)metering | - (iv) Assessment of T&D losses on AP feeders: The Commission directs PSPCL that till the engagement of an independent agency for the subject cited assignment, monthly readings of AP consumers on 1% sample feeders covered under 100% metering be recorded departmentally and the computation of losses based on the same be provided to the Commission along with the data of monthly pumped energy. | In compliance to WTD decision taken in 232nd meeting held on dated 04-12-2019 at Patiala, a fresh tender enquiry no.- 004/DSM-2019-20 on Dt: 13.11.2019 has been floated. Only one number bid from M/s Feedback Energy Distribution Company Limited, Gurugram has been received on date 03-01-2020 and to make the competition more healthy the last date of submission of tender has been extended up to 11-02-2020 from the previous date of opening i.e. 20-01-2020. Regarding recording of meter readings, departmentally the same shall be provided w.e.f. Jan. 2020 onwards for which requisite instructions are being issued to the concerned DS offices through Director Distribution, PSPCL for compliance of the directive. |
| 6.5 Improving power factor of AP feeders | During public hearings, some consumers raised the issue of poor power factor on the AP feeders due to non-installation of necessary capacitors by the farmers. PSPCL shall submit the power factor of AP feeders along with monthly pumped energy data to the Commission. PSPCL is directed to take necessary steps to ensure installation/operation of adequate capacity of capacitors at AP motors. | The List of Power factor of AP Feeders for November-2019 and December-2019 is attached as Annexure-I-1 & I-2. PSPCL has already issued instructions/directions to the field offices to take necessary steps to ensure installation/operation of adequate capacity of shunt capacitors on 11 KV feeders wide Office Memo No. 797/801 Dated: 16.04.2019 and PSPCL has distributed Pamphlets in Kissan Union meetings and field offices, advertised on website and PSPCL APP to create awareness among farmers to ensure installation/operation of adequate capacity of capacitors at AP motors. |
| 6.6 Receivables | PSPCL is directed to take action against the defaulters as per the provisions of the Supply Code, 2014. | Status of Defaulting Amount ending 03-2019, 12-2019 is as under:- ( In Lacs) Category; Total Defaulting Ending 03/2019; Govt. Defaulting Ending 03/2019; General Defaulting Ending 03/2019; Total Defaulting Ending 12/2019; Govt. Defaulting Ending 12/2019; General Defaulting Ending 12/2019. a; b; c; (b-c); e; f; (e-f). Ind; 181665; 151290; 30375; 215271; 183702; 31569. AP; 361; 0; 361; 313; 1; 313. GSC; 118721; 19517; 99204; 126884; 20780; 106104. Others; 7412; 6095; 1317; 9977; 8496; 1481. Total; 308159; 176902; 131257; 352446; 212979; 139467. PSPCL is striving hard to recover the outstanding dues from defaulting consumers. Out of total outstanding amount of Rs 3524.46 Cr., amount to the tune of Rs. 2129.79 Cr. (Detail attached as Annexure-A) is pending towards Govt. connections. All out efforts are being made by PSPCL for the recovery of this amount by making liaison with Govt. Departments time and again. It is pertinent to mention that PSPCL has recovered/adjusted around Rs1606.10 Cr against defaulting consumers up to 31-12-2019 during this Financial Year but at the same time outstanding amount of Rs.2107.97 Cr. has been added resulting into increase in total outstanding amount of PSPCL. As on 31-12-2019 Net Recoverable Amount of PSPCL excluding Court cases, DSC cases and Government Departments is Rs. 1026.71 Cr. For the recovery of this amount mass drive has been initiated by PSPCL and connections of defaulters except essential services are being disconnected in order to press them for depositing the outstanding dues. Annexure-B. |
| 6.7 Consumer Service | - Interest on Security The Commission reiterates its directive that PSPCL should ensure that no consumer is deprived of the right to get interest on security deposit as per the provisions of the Supply Code. As per regulation 17.2 of the Supply Code, 2014, the distribution licensee shall credit the interest on security to the account of the consumer annually and shall adjust it in the first bill raised after 1st April. PSPCL shall submit a certificate on affidavit by 30th June, 2019 that necessary compliance has been made | Total consumers: 55299 New consumers: 10052 Change of Name: 170 Locked: 1185 Moved Out: 5028 Less than Rs. 1 38864 Interest : From above, it is clear that interest on security of 38864 consumers is insignificant and interest on security to the remaining consumers will be posted as per the due date after March-2020 as per PSPCL Regulations. |
| 6.7 Consumer Service | (ii) PSPCL shall ensure release of all new connections within the time period specified in Supply Code 2014 | ii) All connections are being released within stipulated time period irrespective of technical constraints and disputes. PSPCL only lags behind in case of GSC connections due to shortage of meters and after March-2020 all connections of GSC shall also release within the time periods specified in Supply Code, 2014. |
| 6.7 Consumer Service | (iii )PSPCL is directed to resolve the billing disputes within the time period specified in Supply Code, 2014 | PSPCL endeavors to resolve the billing disputes in a timely manner. However, in order to monitor the timely redressal of billing related complaints, a pilot project on 1912 as a Single Touch Point has been started under 5 nos. PSPCL's DS Sub Divisions. This project will be further rolled out in other DS Sub Divisions in a phased manner after analyzing the performance and usefulness of this project to consumers. The generated report of above project for billing related complaints received and resolved thereof from 1-10-2019 to 31-12-2019 under these 5 no. Sub Divisions is as under. Complaint Type; Total No. of complaints; No. of complaints redressed within SERC time limit; No. of complaints redressed beyond SERC time limit. Incorrect Bill; 54; 52; 2. Bill not Received; 33; 33; 0. Online Payment Problem; 2; 2; 0. Enquiries Regarding Bill; 90; 89; 1. Dispute Regarding Bill; 1; 1; 0. The detail of cases Registered and Decided at Zonal, Circle and Division Level DSCs at the end of 2nd quarter of FY2019-20 under PSPCL is as below :- Name of DSC; Total No. of Cases Registered upto 12.2019; Total Nos. of cases Decided; No. of cases decided within 90 days; No. of cases decided beyond 90 days. ZONAL DSC's; 27; 15; 14; 1. CIRCLE DSC's; 238; 146; 143; 3. DIVISIONAL DSC'c; 533; 306; 306; 3. TOTAL; 798; 467; 460; 7. Note:- As per status of DSCs ending 31-12-2019, only 15 Nos. cases were pending beyond stipulated time period specified by Hon'able PSERC . |
| 6.7 Consumer Service | iv)PSPCL shall extend the facility of on-line registration of all new connection applications during FY 2019-20. | The feature of Online registration of application for load above 100 KVA is already running on single window system provided by M/s Yeah and by In-house IT office. There is also provision of registration of connections online for load below 100KVA (SAP Area) which is being run under IT office. For left out Non SAP consumer below 100 kW separate application has been developed by IT office, which has been made live. A Commercial Circular No. 02 dated 03.01.2020 has been issued for registration of application below 100KVA (Non-SAP). With this, registration of all new/extension load applications has been made online during FY 2019-20. |
| 6.7 Consumer Service | (v)The website of the PSPCL is not user-friendly from the point of view of a consumer. A separate consumer services portal/page may be created where all copies of formats used to avail various services, the charges payable by the applicant/consumer, rights and obligations of consumers with all relevant rules and regulations shall be made available in an easy to understand and viewable format. | . “Online Consumer services “ webpage has been re-designed to make it more user friendly from the point of view of consumers and make them aware about the online services provided by PSPCL. In this webpage, consumers are having the facility of consumer login for new connection, extension of loads, NOC etc., Load calculator, LDHF Calculator, bill payment, download bill receipt, current tariff, documents for consumers. A screenshot of the redesigned –homepage of PSPCL website is attached at Annexure-C |
| 6.7 Consumer Service | (vi) To create awareness amongst consumers, PSPCL shall use electronic media, social media and all other means to reach the consumers. | (vi) 24x7 social media control room established to answer queries of consumers on social media twitter.com/PSPCLPb, facebook.com/PSPCLPb, instagram.com/PSPCLPb, Telegram: t.me/PSPCLPb, Email: 1912@pspcl.in, PSPCL WhatsApp (+91-9646106835) number and PSPCL Mobile APP have been made available for the convenience of consumers. Total no. of Complaints received from 01.10.19 to 31.12.19; PHONE; WHATSAPP; TWITTER; FACEBOOK; TOTAL. 6394; 6019; 461; 42; 12916. |
| 6.7 Consumer Service | (vii) PSPCL shall regularly hold ‘Consumer grievances resolution week’ in every quarter at divisional/circle level where grievances of the consumers shall be resolved immediately by the senior officers. | (vii) PSPCL instructed all DS Zones vide CE/ Commercial office Memo no. 1626-30 Dated: 22.08.2019 (copy enclosed) to held monthly meetings regarding redressal of consumer grievances with the esteemed consumers. The status of monthly meetings conducted by all DS Zones is as below. Sr. No.; Zone; No. of Meetings conducted upto 31.12.2019; No. of Consumer Grievances addressed Till 31.12.2019; No. of Grievances resolved; No. of Grievances pending; Reason for Pendency. 1; BORDER; 74; 155; 153; 2; New T/Fs are being installed, 70% work completed. 2; CENTRAL; 61; 194; 194; 0. 3; NORTH; 43; 79; 79; 0. 4; SOUTH; 103; 499; 499; 0. 5; WEST; 32; 135; 135; 0. TOTAL; 313; 1062; 1060; 2. |
| 6.7 Consumer Service | (viii)A ‘Frequently asked Question’ link shall be created which provides all information to the consumers regarding frequently raised queries regarding PSPCL procedures and its rules/regulations.. | IT-related FAQ already available on homepage of PSPCL. Website since June 2018. Link to access FAQs on PSPCL website is: https:/www.pspcl.in/wp.content/uploads/2018/07/FAQs-updated.pdf. |
| 6.7 Consumer Service | (ix)PSPCL shall submit billing cycle wise key exception reports of both SAP and Non-SAP areas quarterly to the Commission | The Key Exception reports of billing Cycle-5 (Bi-Monthly) and Cycle-10 (Monthly) under SAP & Non SAP Areas is attached as Annexure J. |
| 6.8 Employee Cost | PSPCL shall submit category wise recruitment plan of employees for FY 2019-20 and for next MYT control period. PSPCL shall also submit a comprehensive cadre management plan for next 10 years. | Comprehensive Cadre Management Plan – It is submitted thatthe work of staffing study of manpower requirement based on work-load norms, of erstwhile PSEB was entrusted to Price-Waterhouse Cooper (PWC) in the year 2007 as desired by PSERC. Post unbundling of erstwhile PSEB into PSPCL and PSTCL, the consultant submitted its revised & final report in March 2011 wherein it was recommended that the employee strength of PSPCL be brought down to 48767 no. employees from the then sanctioned strength of 77382 no. employees with further reductions as detailed at Annexure-D. In line with the recommendations of PwC report, PSPCL is already conducting various in-house restructuring & re-engineering initiatives. For optimum utilization of existing manpower and to reduce employee cost the following measures are being taken – - Three committees of officers were duly constituted to suggest modification/ revision in the staffing study report submitted by PWC in the year 2011 for Generation Organization, Distribution Organization and Other Organizations of PSPCL as per prevailing scenario and formulate revised staffing norms category-wise and organization-wise. - The committee for Generation Organization has submitted its recommendations.The proposal regarding rationalising manpower strength for GNDTP, Bathinda & GGSSTP, Roopnagar is as under – Office; Present Sanctioned Strength; No. of Posts to be Abolished/Diverted; Proposed Sanctioned Strength. CE/GNDTP, Bathinda; 2392; 2194; 198. CE/GGSSTP, Roopnagar; 2927; 1164; 1763. Subsequently, plant-wise/ organization-wise agendas for rationalizing manpower as per the recommendations of the committee have been prepared and two nos. agendas, i.e. for GNDTP, Bathinda and GGSSTP, Roopnagar are being placed to the BODs for approval. - The process for formulation and recommendation of revised staffing norms by the committee for Other Organizations is currently on-going. The committee comprising of Dy.CE/Personnel, SE/Employee Development, Dy.Secy./ Personnel, Dy.Chief Auditor & AEE/ODMD held its first meeting on 15.01.2020 wherein it was decided that detailed workload assessment of all employees under each HOD shall be submitted by all departments. The same shall be discussed and deliberated upon in future meetings department-wise and accordingly, revised staffing norms for each department shall be proposed by the committee for consideration by the BOD’s. As on date, the first proposal regarding rationalising manpower strength for Store & Workshop Organization, Ludhiana is as under – Office; Present Sanctioned Strength; No. of Posts to be Abolished/Diverted; Proposed Sanctioned Strength. CE/S&W, Ludhiana; 1046; 351; 695. In addition to the above, the Board of Directors of PSPCL, in their 73rd and 75th meetings held on 02.02.19 and 01.06.19 respectively decided to discontinue the recruitment under categories of Medical Officer, Law Officer Grade-II and JDM. With the discontinuation of the posts of JDM, other cadres like DM, DHD & CHD shall also be abolished with the passage of time. Further redundant/ superfluous categories to be discontinued are also being considered and shall be deliberated upon further. In addition, the existing staff will also superannuate over a period of time and the posts identified as redundant shall not be filled and will be subsequently abolished. In view of the above, it is also submitted that the present posted strength of PSPCL is 34555 no. employees (as on 30.06.2019) is well within the recommendations of PWC as tabulated below – Sr. No.; Parameter; Value (Nos.). 1; PSEB Cadre Strength as on 16.04.10; 83,445. 2; PSPCL Cadre Strength as on 16.04.2010; 78,125. 3; Posts Transferred to PSTCL after unbundling; 5,320. 4; PWC Proposed Total Sanctioned Strength of PSPCL; 48,767. 5; PWC Proposed Total Sanctioned Strength of PSTCL; 4,350. 6; Present Sanctioned Strength of PSPCL as on 30.06.19; 75,757. 7; Present Posted Strength of PSPCL as on 30.06.19; 34,555. 8; Present Sanctioned Strength of PSTCL; 5,129. 9; Present Posted Strength of PSTCL as on 08.01.20; 2,774. 10; PSPCL Officers/Officials working in PSTCL as on 08.01.20; 1,746. In addition to the above, since 30.06.19, 225 nos. employees have been recruited directly and 137 nos. employees have been employed on compassionate grounds. It is also intimated that the recommendations given by PWC were as per the scenario prevailing in the year 2011, and since unbundling of PSEB in 2010, there is a tremendous increase in workload due to more Consumer Base, more no. of Grid Sub-Stations, more length of lines etc. as tabulated below – Sr. No.; Description; 31.03.2010; 31.03.2019; Difference; %-age Difference. 1; Maximum Demand (MW); 7,407; 12,638; 5,231; 70.62%. 2; Consumers (Nos.); 69,18,145; 94,78,248; 25,60,103; 37.01%. 3; Load (MW); 25,933.96; 36,416.13; 10,482.17; 40.42%. 4; Energy Sold (MU); 33,741.54; 47,446.08; 13,704.54; 40.62%. 5; No. of Transformers (11KV) (Nos.); 4,03,619; 10,66,770; 6,63,151; 164.30%. 6; Length of Transmission Lines (Ckt. Kms) (33/66KV); 7,829; 10,185; 2,356; 30.09%. 7; No. of Grids (Nos.); 608; 957; 349; 57.40%. 8; 11KV Lines (Km); 1,61,159; 2,42,012; 80,853; 50.17%. 9; LT Lines (Km) *; 1,67,021; 1,47,083; -19,938; -11.94%. As such, careful deliberation and re-consideration of the recommendations given by PWC is required before carrying out re-structuring of PSPCL, and as has been illustrated on the previous pages and comprehensive efforts are underway in order to accomplish the same. |
| 6.9 Performance parameters | - DISTRIBUTION - Damage to DTs PSPCL should supply rating wise information regarding DTs installed, DTs damaged and number of overloaded DTs during FY 2018-19. The damage rate of DTs (excluding warranty of new & repaired DTs) upto Dec. 2018 is 3.41% as compared to 3.60% during the same period of last year. PSPCL shall bring down the damage rate of DTs to below 3% (excluding warranty of new & repaired DTs) during FY 2019-20. | (A) Rating wise DTs installed, DTs damaged and DTs Overloaded for FY-2018-19. 6.3 KVA; 10 KVA; 16 KVA; 25 KVA; 63 KVA; 100 KVA; Above 100 KVA; TOTAL. INSTALLED; 115343; 325074; 182107; 201809; 116727; 103309; 22399; 1066768. DAMAGE (Without Warranty & Theft); 3710; 9242; 5770; 9767; 6862; 6731; 415; 42497. OVERLOADED; 2075; 1396; 3688; 202; 210; 170; 41; 7782. To reduce damage rate of DTs during first quarter of FY 2019-20, 6147 no., during second quarter of FY 2019-20, 5932 no. and during third quarter of FY 2019-20, 9718 no. DTs have been Augmented for deloading. PSPCL is hopeful to bring down the damage rate of DTs during FY 2019-20. Damage rate of DTs excluding warranty, repair, theft and storm upto 12.2019 is 3.50%. |
| 6.9 Performance parameters | - (II) Standards of Performance PSPCL is directed to ensure implementation of the Standards of Performance specified by the Commission and submit quarterly information to the Commission. | Standards of performance parameters which includes information regarding billing mistakes, faulty meters, line breakdowns,outages, equipment failure, voltage fluctuations, release of new connections, shifting of meter/lines, consumer complaints, reliability indices etc. a meeting was held with Hon'able Commission on dated 18,09,2019 with Director/Distribution, PSPCL, wherein new instructions were passed regarding SOP's. Further these instructions were passed on to all distribution zones for strict compliance |
| 6.9 Performance parameters | - (III) it has been observed from the MIR data of damaged transformers (Format-29) that the damage rate of distribution transformers got repaired from the Firms during FY 2017-18 was 15.2%. PSPCL is directed to inform the Commission regarding the reasons for such a high rate of damage of repaired transformers and also the remedial measures being taken to reduce the damage rate. | On comparison of the data of format MR-14 and MR-29 of the MIR for the period from 2010-11 to 2019-20 upto september-2019) ,(copy of the comparison attached-Annexure-E) it was found that 235536 T/Fs were got repaired from various firms during this period. Whereas as per MR-29 ending 09/2019, 111793 T/Fs were shown as installed by all the Chief Engineer/Operations Zones which seems to be incorrect. The T/Fs repaired by various firms under this organization (Chief Engineer/Store & Workshop, Ludhiana) ending 09,2019 were 235536 and damaged T/Fs during this period were 102147. The difference of repaired & damaged T/Fs which was 133389 had not been added in installed T/Fs by the concerned Operation Zones. As per annexure attached, 35116 T/Fs were shown as installed upto 03/2011.had the above difference of 133389 Nos. T/Fs been added to the already installed T/Fs( i.e. 35116) then Total installed T/Fs would have been 168505( 35116+133389) instead of 35116. During the year 2019-20 ( upto September 2019) 11139 T/Fs were damaged out of 168505 total No. of installed T/Fs hence damaged rate is 6.6% It is further added that a letter vide memo no. 3877/81 dated 15.07.2019 and reminders have been already written to all CE/Operations of all zones to reconcile the figure as detailed in above para. After reconciliation from all operation zones current figure of damaged rate can be initiated. . |
| 6.9 Performance parameters | - Sub-Transmission System - Overloading of grid sub-stations PSPCL is directed to ensure deloading of the nine number grid sub-stations with loading more than 90% before start of paddy season of 2019. | There were 9 No. 66KV Grids with loading more than 90% out of these 9 No. Grids, work of 4 No. Grids had been completed and 1 No.grid has been deloaded by shifting the load to near by grids and deloading of balance 4 No. Grids has been planned in TWL 2018-19.and subsequently in TWL 2019-20 These 4 No. grids will be de-loaded by 31.03.2020. The details of the planning list is attached herewith. (Annexure-F ) |
|  | - Maintenance of sub-transmission system PSPCL is directed to ensure adequate number of line staff at the load centres to reduce the response time to attend to breakdowns. | (B) Sub-Transmission System (ii) The status of line staff for maintenance at 66 KV Sub-Transmission System under PSPCL is as below: a) Additional Posts have already been created under P&M Circle Jalandhar vide office order no. 542/Cadre-1 Dy. Secy/Personnal, Dated: 28.08.2018 (Annexure-M). The vacant post of lineman's are filled during promotion from ALM to Lineman and vacant posts of ALM's are to be filled from new recruitment of ALM's for carrying out maintenance of 66 KV Lines. b) 2 nos. AE/TL S/D Ropar and Malerkotla have been created under P&M Circle Patiala vide office order no. 631/Cadre-1 Dy. Secy/ Personnal, Dated: 17.12.2019 and 632 /Cadre-1 Dy. Secy/ Personnal dated 17.12.2019 (Annexure-M). The vacant post of lineman's are filled during promotion from ALM to Lineman and vacant posts of ALM's are to be filled from new recruitment of ALM's for carrying out maintenance of 66 KV Lines. c) The vacant post of 9 no. lineman's all filled during promotion from ALM to Lineman and 31 no. vacant posts of ALM's are to be filled from new recruitment of ALM's for carrying out maintenance of 66 KV Lines under P&M Circle Bathinda.. d) Additional Posts have already been created under P&M Circle Amritsar vide office order no. 542/Cadre-1 Dy. Secy/Personnal, Dated: 28.08.2018 (Annexure-M). The vacant post of 7 no. lineman's are field during promotion from ALM to Lineman and 18 no. vacant posts of ALM's are to be filled from new recruitment of ALM's for carrying out maintenance of 66 KV Lines. e) A new AEE/TL S/D West Ludhiana has already been created under P&M Circle Jalandhar vide office order no. 542/Cadre-1 Dy. Secy/Personnal, Dated: 28.08.2018 (Annexure-M).However, the working labor shall be outsourced from contractors/ service providers. To operationalize the AEE/TL S/D West the tender inquiry no.2 was floated in month 07/2019 but no bid has been received, so retendering was done, vide tender enquiry no:03 in month 10/2019 even no bid has been received against tender enquiry no:03, Now the case is under process to modify the proposal as per the work order on the pattern of PSTCL. The vacant post of 7 no. lineman's are filled during promotion from ALM to Lineman and 32 no. vacant posts of ALM's are to be filled from new recruitment of ALM's for carrying out maintenance of 66 KV Lines The process of new recruitment of ALM's is under process. |
| 6.9 Performance parameters | - Preventive maintenance of 11/66 kV Feeders PSPCL shall formulate a comprehensive feeder – wise maintenance schedule to ensure un-interrupted power supply to the consumers. PSPCL shall submit feeder wise monthly trippings/breakdowns and total time period of interruptions. PSPCL shall also submit details of electrical accidents (both fatal and non-fatal) which occurred on the feeders along with reasons for the mishap | (C) For Preventive maintenance of 11/66 kV Feeders, instructions were issued by the o/o. Director/Distribution vide Memo No. 2505/2509 Dated: 30.09.2019 to All DS Zones. During 3rd Quarter of FY 2019-20, Maintenance of 4248 nos. 11 KV Feeders have been done by DS Zones and maintenance of 258 nos. 66 KV Lines have been done by P&M Organisation. The information regarding monthly trippings/breakdowns and total time period of interruptions is attached as Annexure-K-1 to K-3. Details of electrical accidents (both fatal and non-fatal) occurred on the feeders along with reasons for the mishap is enclosed as Annexure-L. |
| Accounting of Defective Transformers after repair 6.10 | The Commission notes that the repaired transformers are being issued to Accounting units of PSPCL in the field, on the value based on weighted average method, which is not appropriate. The same transformer when issued to other Accounting Unit in the field after repair has to be valued on actual value basis and not on weighted average method. Since the Fixed Assets Cards/Registers are already being maintained by PSPCL with complete nomenclature, value of the transformer and depreciation thereof so PSPCL is directed to re-examine the accounting method of issuing the transformers after repair and devise a proper accounting procedure. PSPCL shall account for any loss due to damaged transformrs | The receipt/issue of damaged and thereafter repaired transformers is being done as per respective method prescribed in Memo No. 11893 dt 19.9.1995 of Chief Accounts Officer/Commercial Accounting Cell PSEB Patiala. So currently the accounting done by the office of AO/Evaluation PSPCL Patiala is as per the policies of the PSPCL is as per policies of the PSPCL.. Annexure-G |
| 6.11 Fixed Asset Register/ Segregation of Accounts | - PSPCL is directed to maintain the updated Fixed Assets Registers and make them available online within a year. | It is submitted that in compliance of directives of PSERC, an M.S. Office (Excel) utility has been designed to for preparation of fixed assets registers and calculation of depreciation, which is being used by all field accounting uttits through this utility, uniform assets and depreciation record has been maintained by all the accounting units of PSPCL. Further, the process of implementation of ERP system has also been initiated by PSPCL and this work has been awarded to M/s Tech Mahindra Ltd. As such online preparation of fixed assets register will be taken up at the time of implementation of ERP. As such Hon'ble commission is now requested to drop this directive. As PSPCL has started the implementation of ERP Software package in Oct., 2019 which shall be having three major modules i.e. HR, Finance & Accounts and Material Management. Concerned Finance office needs to co-ordinate for maintaining Fixed Assets Register in ERP with ERP team. |
| 6.11 Fixed Asset Register/ Segregation of Accounts | (ii)The Commission reiterates its directive to segregate the accounts for distribution & generation (project wise) businesses for determination of tariff as per Regulation 5 of MYT Regulation | ANNEXURE-H |
| 6.11 Fixed Asset Register/ Segregation of Accounts | (iii) PSPCL is also directed to further segregate the accounts of its distribution business into wheeling business and retail supply as per Regulation 6 of MYT Regulation.. | Segregation the accounts of distribution business into wheeling business and retail supply business. The segregation of costs/expenses and revenues of the distribution business into wheeling business and retail supply business is not available in the present accounting system. The accounts of Wheeling and retail supply are integrated and are being maintained by same accounting units i.e. Distribution divisions. Further, as desired bv PSERC to formulate system to maintain accounts in such a way that the information with regard to segregation the accounts of distribution business into wheeling business and retail supply business is concerned, the matter is under active consideration of the management to revive the P&M divisions, shortly, to maintain accounts of transmission system separately. lt is also added that the process of implementation of ERP System has also been initiated, the possibilities of segregation will be explored in the developing stage. |
| DSM 6.12 | PSPCL is directed to execute at least one pilot project each for Ag. DSM and efficient lighting to showcase the benefits to the stakeholders. | - Regarding implementation of Agriculture Demand Side Management (Ag-DSM) in the state of Punjab: PSPCL has selected one number feeder named 11KV Wazir Bhullar under DS Division Beas. The office of Dy.CE/DS Circle, Tarantaran has sent the details of 158 no. consumers having different capacity of pump sets along with the consent of the AP consumers for replacement of existing pump sets with BEE 5 star pump sets and the scheme for project is under finalization. - Replacement of ICLs/Tube Lights with LEDs in the buildings of PSPCL departmentally: The Committee of WTD's PSPCL in its 211th meeting held on 23.08.2018 at Mohali has been decided "THAT approval be and is hereby accorded to the proposal as given in Para no. 11.0 for procurement by CE/ MM of 4137 no. of 9 Watt LED lamps along with 42582 no. of 20 Watt LED Tube lights, at rates mentioned in Para 5 of the agenda, in 2 phases ( i.e. 21291 no. of 20 W LED Tube lights & 4137 no. of 9 Watt LED lamps in 1st phase & remaining 21291 no. of 20 W LED Tube Lights in 2nd phase)". Accordingly, office of CE/ MM, PSPCL has awarded P.O.-CUM-CONTRACT NO.- HD-506/Q-190/PO-C Dated: 11.10.2018 to M/s EESL for "Supply and delivery of new energy efficient 9 Watt LED lamps and 20 W LED Tube lights (UJALA appliances) to replace ICL's Fluorescent Tube lights in the buildings of PSPCL". From this project there would be savings of 2.72 MUs per annum. As per latest status, M/s EESL has delivered 4137 no. of 9 Watt LED lamps along with 42582 no. of 20 Watt LED Tube lights to the PSPCL Stores and now various departments of PSPCL are replacing their existing bulbs and tube lights with LED bulbs and LED tube lights. - Distribution of 9 W LED Bulbs among the consumers that falls under the category of BPL, SC & BC category: A proposal was prepared to distribute 2 no. of 9 Watt LED Lamp among the of 1.01 Lac of BPL, 15.48 Lac of SC & 1.28 Lac of BC consumers of PSPCL (consumers having their load up to 1 KW) in the state of Punjab without any charge to consumers. The total project cost of Rs. 21.72 Cr (for two phases). After obtaining the administrative approval of worthy CMD-PSPCL, the detailed proposal has been submitted before the Secretary/ PSERC, Chandigarh vide CE/ ARR & TR, PSPCL, Patiala Memo No.-2300/CC/DTR-104/Vol.49 Dated: 18.07.2018 to consider this proposal as DSM measure. The Secretary/ PSERC, Chandigarh vide its Memo No.-2179/PSERC/DTJ-69/Vol./Vol.II Dated: 05.12.2018 has approved the implementation of the scheme for phase-1 on the following terms & conditions: - Two numbers LEDs of 9 Watt each may be given to subsidized categories of DS consumers against replacement of two lighting appliances out of which at least one should be ICL of minimum wattage of 60 Watt. The 2nd lighting appliance may be a ICL or CFL. - Rs.15/- Per LED shall be recovered from the consumes. - A proper record of the consumers covered under the scheme shall be maintained by PSPCL. All ICLs collected from the consumers shall be stored at designated centres of PSPCL and at the end of the Phase-I, a 3rd party verification will be carried out. All these ICLs and CFLs collected from consumers shall be destroyed in the presence of 3rd party agency as per the environment norms. - PSPCL shall tie-up with EESL for procurement of LEDs at the lowest rate. - It shall be ensured that funds against DSM schemes approved in the Tariff Order for FY: 2018-19 are utilized for the implementation of the scheme. - After completion of the phase-I, PSPCL shall submit a complete report to the Commission and approval for distribution of LEDs in phase-II will be considered by the Commission after scrutiny of the results of phase-I. A meeting was held on 03.06.2019 under the chairmanship Chairperson/ PSERC and PSPCL, wherein it was decided as under: "PSPCL brought out the difficulties of 2 no. LEDs to subsidized category of consumers in accordance with the conditions imposed in the approval letter of the Commission. It was submitted that the scheme is for free distribution of 2 no. LEDs to subsidized category of consumers to save electricity. While appreciating the difficulties which may be faced by PSPCL in collecting the ICLs/CFLs, its proper storage, accounting and final disposal under the supervision of the 3rd party, the Commission expressed its apprehension that distribution of free LEDs may be misused and a nominal cost of Rs.15/ per LED must be recovered from these consumers. PSPCL agreed that Rs. 15/-LED can be collected from the consumers. PSPCL was instructed to submit the revised proposal for implementation of schemes under Phase 1 approval of the Commission. It was assured by PSPCL that after completion of Phase 1, the consumption pattern of beneficiaries along with total energy saving achieved shall be submitted to the Commission before submitting the proposal for further distribution of LEDs under phase 2." In compliance to above, a revised proposal was submitted Hon'ble PSERC and Hon'ble PSERC, Chandigarh vide their office memo no.- 1340/PSERC/DTJ-69(Vol.-II) Dt: 12.09.2019 has approved PSPCL proposal for phase-I subject to the following condition: - "PSPCL shall tie up with EESL for procurement of LEDs at the lowest rate. It shall be ensured that no over head charges such as distribution charges and publicity expenses etc. are included in the price of LEDs offered by EESL to PSPCL." M/s EESL vide their E-mail Dt: 09.10.2019 has provided bifurcation of the price of 9W Led bulb (i.e. Rs.60/-) and as per the detail M/s EESL fulfilled the condition of Hon'ble PSERC. As per latest status: PSPCL has allocated Rs. 10 crore for the procurement of 17.75 lakh 9 Watt LED Lamps to be distributed among the subsidized categories of PSPCL i.e. SC, BC and BPL. - Replacement of conventional incandescent lamps /CFLs/Tube lights and Fans with efficient 20 Watt LED Tube Lights & 50 Watt BEE star rated Energy Efficient Fans in the Government Hospitals: The Purpose of this proposal is to provide energy efficiency in the Public places like Govt. Hospitals where the consumption of electricity is for 24 hours and it is being used for needy patients over there and to utilize the DSM Funds approved by Hon’ble PSERC, On the above mentioned matter a meeting was held on dated 13.06.2019 under the chairmanship of Chairperson/PSERC with PSPCL officials and it was decided as under: "The Commission directed PSPCL to ensure utilization of funds approved in the Tariff Order for FY2019-20. PSPCL was asked to submit proposal for replacement of inefficient electrical appliances in Government hospitals/dispensaries etc." In compliance to the above directives of Hon’ble PSERC, and to provide energy saving benefits to General Public of Punjab, a proposal has been formulated to replace conventional incandescent lamps/CFLs/Tube lights and Fans with efficient 20 Watt LED Tube Lights & 50 Watt BEE star rated Energy Efficient Fans in the Government Hospitals. Therefore, while considering this fact, the campus of Government Rajindra Hospital at Patiala, JBMM Civil Hospital Amritsar, Civil Hospital Bathinda & Civil Hospital Ludhiana is proposed as a Pilot Project to replace conventional appliance with energy efficient appliances. Total Project Cost of Rs. 86,14,704/-(say Rs. 86.14 Lac) is required to replace conventional ICLS, CFLs, Tube lights and Fans. In compliance to the directives of Hon’ble PSERC and after obtaining the approval of worthy CMD-PSPCL, a petition-cum-application in form of detailed project report of this proposal is submitted before Hon'ble PSERC vide this office Memo no.- 711 Dated: 04.09.2019 through CE/ ARR & TR, PSPCL, Patiala for obtaining their approval to consider this proposal as a DSM measure against DSM funds. Hon’ble PSERC had called a meeting with concerned officers of DSM office for discussion on the subject cited proposal. In this regard, a meeting was held on dated 29.10.2019 under the chairmanship of Chairperson/PSERC with PSPCL and In compliance to the Minutes of the meeting, CE/ Electrical, PWD (B&R, Punjab), Chandigarh and Executive Engineer (Electrical)Punjab Health System Corporation, Mohali have been approached to issue necessary instructions to concerned officers/officials for joint verification of basic data of inefficient appliances of each of the hospital/college submitted by the concerned hospital/college authorities to PSPCL and to provide concurrence of execution of DSM Scheme with details of material to be provided by M/s EESL along with furnishing comments on the disposal of the dismantled material after joint verification. In this regard following is the present status: - Joint verifications of Government Rajindra Hospital Patiala, with the representative of CE/ Electrical ,PWD (B&R, Punjab) and JBMM Civil Hospital Amritsar, Civil Hospital Bathinda & Civil Hospital Ludhiana with the representative of Executive Engineer (Electrical)Punjab Health System Corporation has been carried out. - The offices of CE/Electrical, PWD (B&R,Punjab) Chandigarh (for Government Rajindra Hospital Patiala), and Executive Engineer (Electrical)Punjab Health System Corporation, Mohali (for other hospitals under this scheme) have been requested to provide concurrence of execution of DSM Schemes with the material to provided by M/s EESL. - Regarding methodology for disposal of material, matter has been taken up separately with the above named offices. |
| 6.13 Surplus power | PSPCL is directed to continue with its efforts in selling surplus power through the exchange / traders in order to reduce the fixed cost liability on consumers of the State. PSPCL should submit quarterly report of power sold, per unit sale price and profit earned through sale of power. PSPCL is also directed to include in the ARR the details of power surrendered/proposed to be surrendered during the year along with the financial implication regarding the fixed cost of this power. | - For sale of surplus power PSPCL has created a dedicated cell consisting of a Dy. CE, an Addl. SE and an AEE to manage sale of surplus power. - PSPCL has appointed M/s NHPC Ltd for sale of surplus power on behalf of PSPCL. - PSPCL is considering tenders for sale of power to other Utilities/Discoms and participating in every tender except for the issues like paddy season, coal related conditions, transmission corridor congestion etc. - PSPCL has floated Tender enquiry for Sale of Surplus Power (500 MW RTC & 1000 MW night hours) in which no one participated so tender enquiry was dropped finally. - With above efforts PSPCL has sold 14.8416 Mus of Energy at an average rate of Rs. 4.97 per KWH at Punjab periphery in Day Ahead Market and 3.1595 Mus of Energy at an average rate of Rs. 5.21 per KWH at Punjab periphery in Term Ahead Market in Exchange during the period Oct’19 to Dec’19 by daily bidding. - The tentative benefit calculated from sale of power is as under:- Tentative Sale benefit Q3 2019-20 (Provisional). Sale; Benefit. Month; Units (Mus); Avg. Rate (Rs./KWh); Amount (Rs. Crore); Tentative Benefit with Variable Cost (Rs. Crore); Tentative Benefit along with Normative Fixed Cost (Rs. Crore). 1; 2; 3; 4; 5; 6. Oct-19; 14.40; 5.13; 7.39; 2.99; 1.16. Nov-19; 3.19; 4.46; 1.42; 0.42; 0.02. Dec-19; 0.41; 4.4; 0.18; 0.05; 0.00. Total; 18.00; 4.99; 8.99; 3.46; 1.18. |
| 6.14 Load flow studies | PSPCL should submit all proposals for sub-transmission system works supported by load flow studies | The requisite software has been received from PSTCL and in this regard the required technical data ihas been obtained from concerned DS/P&M organization of PSPCL and PSTCL. The work of data feeding in PSS/E software is being initiated and under process. The process of load flow studies shall be commenced by 28.02.2020. |
| 6.15 Harmonics Measurement | As per Regulation 24 of the Supply Code, 2014, the distribution licensee is required to monitor the harmonic currents and voltages at its HT/EHT Sub-stations and of HT/EHT consumers, which are prone to generation of harmonics. It has further been provided that the consumers contributing harmonics distortion in excess of specified standards shall be served with a three months notice to rectify the violation, failing which penalty can be imposed as prescribed by the licensee with the approval of the Commission. Power Intensive category of Industrial consumers are prone to generation of harmonics affecting quality of supply and also resulting in long term damage to the electrical equipments. The Commission observes that the distribution licensee is neither measuring the harmonics injected by the PIU category consumers in to the system nor has any penalty been suggested for violation. PSPCL is directed to submit a complete plan regarding installation of necessary power quality meters for measurement of harmonics levels along with time frame for recording the harmonics. PSPCL may also recommend penalty to be recovered from the PIU consumers contributing harmonics in excess of the specified standards. PSPCL shall submit the proposal by 1st August, 2019. | Meetings of the Committee constituted vide EIC/Commercial Office order no. 227/CC/DTR-104 dt. 21.08.2019 to consider the process of monitoring/measurement of voltage/ current harmonics/ Total harmonics distortion (THD) was concluded on 30.09.2019 and committee had submitted its report/ Minutes of Meeting (MoM) on 11.10.2019, which were circulated to all the concerned offices including the O/o CE/ARR & TR vide this office Memo no. 213 dated 11.10.2019. The above proposal has already been forwarded to the PSERC on dated 15.11.2019 by the O/o CE/ARR & TR. vide memo no. 2530 for your consideration. Similarly comments desired on draft regulations on Power Quality were also submitted to the Commission through the O/o CE/ARR & TR vide this office Memo no. 237 dated 08.11.2019, where a formula was also proposed regarding imposition of penalty for excess values of THD. Directions/decision on proposal is awaited before further action is taken towards compliance of the directive. |
| 6.16 Supply of Sales/revenue data | - PSPCL is directed to supply category wise and slab wise number of consumers, connected load/demand, consumption (in kWh as well as kVAh), power factor and revenue data to the Commission along with ARR for next MYT. The revenue data shall contain separate figures of SoP, rebate and surcharge | The slab wise data, as finalized by PSERC, has been made available in system from Jan 2019. The data in desired slab wise format prior to Jan 2019 is not available in the system as logic for slab wise was developed in system w.e.f Jan 2019. However, while testing the report, some structural issues were there in slab wise report which were rectified after consultation with all concerned offices and the correct report was made available in system from April 2019. However data for the year 2018-19 has also been provided in slab wise format from 01.01.2019 to 31.03.2019. Also the data for the FY 2018-19 has been supplied on prorata basis, based upon the data of FY 2019-20 H1. |
| 6.16 Supply of Sales/revenue data | - (ii) During processing of ARR for FY 2019-20, it has been noticed that kVAh consumption has erroneously been shown as kWh consumption thus affecting the Energy Balance in the Tariff Order. It is apprehended that same error might have occurred in the consumption data supplied to the Commission since introduction of kVAh tariff w.e.f. FY 2014-15. PSPCL is directed to supply the correct consumption data in kWh for the previous years within 3 months from the date of issue of this Tariff Order. | The KVAh billing for LS, MS and other categories was started from FY 2014-15 onward in different timelines. The data of 40 no. towns was also in transit due to migration from NON SAP to SAP system during FY 2014-15 and 2015-16. As such, the data may contain inflated bills and dial over cases during that period. The reversal activity regarding inflated/ dial over cases is being monitored regularly from FY 2019-20. As such the data for FY 2019-20, is being supplied as per the requirement of PSERC. |
| 6.17 Review of Rebates/ surcharges | i) PSPCL is directed to examine in detail the effect of introducing ToD tariff on the recovery of revenue and flattening of load curve. PSPCL shall submit detailed report by 1st Nov. 2019 along with a fresh proposal for next MYT. | The load curves have been studied by the O/o CE/PPR and inference is as under: ToD tariff during peak season of Summer/Paddy/Khariff: It has been observed that with regular implementation of ToD from financial year 2017-18 onwards has shifted from peak period of 06.00PM to 10.00 PM of financial year 2013-14 to 2016-17, to other period usually 3.00PM to 4.00PM. It can be inferred that ToD tariff has helped in checking peak demand during peak hours. To flatten the load curve, further night tariff has also been introduced. So far 74 no. industries have opted for it with cumulative load of 226 MVA upto 31.01.2020. ToD tariff during lean season of Winter/Rabi: During above period load curves do not suggest any perceptible change in profile during the night period of lean season from 10.00 PM to 6.00AM next day. Thus the ToD tariff introduced during the lean season has not enhanced utilization of power during night hours since the demand falls steeply during the winter months in these hours. |
| 6.17 Review of Rebates/ surcharges | (ii) rise in consumption of various categories of consumers and benefits accrued to PSPCL with the introduction of Threshold limit rebate. PSPCL shall submit detailed report by 1st Nov. 2019 | Regarding this part of directive, information regarding industrial consumers was collected and accordingly following observation has been made: Number of Threshold units and consumers availing Threshold rebates has shown upward trend. Consumption of Threshold units by LS category consumers has resulted in additional sale of Rs. 118.97 Cr. of PSPCL for the period of 2016-17 to 2018-19. |