## 2017-18
AO /TL Patiala for FY 2017-18 (Annexure-A)
| NAME OF WORK | AMOUNT | interst A&R | Total amt Capitalised | DATE OF START | DATE OF COMPLETION
A | REC Works
1 | 66KV Line phool Jethu ke T-off Gill Kalan - 7940 | 173537 | 3700 | 177237 | 2018-04-01 | 2018-11-01
2 | 66KV Line Ghubaya-Fattanwala upto Jallabad T off for Chak janisar-10290 | 815273 | 17384 | 832657 | 2014-05-01 | 2015-03-01
3 | 66KV Line Ladhuke to Chimney wala( 1 ckt)-10290 | 656166 | 13991 | 670157 | 2014-05-01 | 2015-02-01
4 | 66KV Line Dabwali Road BTI to IGC BTI-10290 | 83012 | 1770 | 84782 | 2014-05-01 | 2015-02-01
5 | 66 kv line Lubbianwali-Makand/ MUKAND Singh Wala 9295(1) | 2523374 | 53805 | 2577179 | 2016-03-01 | 2017-05-01
6 | 66 kv line Chaksherwala-Lakhewali -10290 | 2374236 | 50625 | 2424861 | 2014-10-01 | 2015-06-01
7 | 66 kv bareta - kishangarh 9295 | 5285 | 113 | 5398 | 2013-10-01 | 2016-06-01
8 | 66 kv line 220 kv passiana to 66 kv gajju majra 3719 | 93023 | 1983 | 95006 | 2015-11-01 | 2019-01-01
9 | T-off of 66 KV Nathana- Kalyan Sukha Line t-off ganga 9295 sr.2 | 220333 | 4698 | 225031 |  | WIP
10 | lehra mohabbat to phool -TRANF TO NREC,NOW 12115 | 7446366 | 158775 | 7605141 | 2016-03-01 | 2019-02-01
11 | Replacement of 66 KV HRP Line from 220 KV S/Stn BaJakhana to 66 KV S/Stn Bargari with SC/DC Tower line 10290 | 131143 | 2796 | 133939 | 2016-06-01 | 2019-03-18
12 | Kharunj to Chak Janisar line 10290 | 16409 | 350 | 16759 | 2015-10-01 | 2016-06-01
13 | 66KV Line DC Ghattianwali-Chimnewala 10290 | 1144151 | 24396 | 1168547 | 2015-05-01 | 2016-09-01
14 | 66KV Line DC Sandhwa to Kotkapura/OVERHEAD ELECTRIC CROSSING KOATKPURA AND WANDER JATAN RLY 10290 | 501299 | 10689 | 511988 | 2015-06-01 | work in progress
15 | 66KV Line Banghi Nihal- Sekhu sc on dc towers 10290 d/c o/h line b/w RMN-SGA railway station of sirsa BTI | 730173 | 15569 | 745742 | 2016-07-01 | 2017-10-01
16 | 66KV Line 2nd CKT Arniwala- Ghattanwali 2nd ckt with dc tower 10290 | 808573 | 17241 | 825814 | 2014-05-01 | 2018-05-01
17 | 66KV Line Kot Dharmu- Hirewala sc on dc 10290 | 7463 | 159 | 7622 |  | WIP
18 | 66KV Line Lakhewali to Khrunj dc on dc to replace aug exsiting sc on sc/OVERHEAD ELECTRIC CROSSING LAKHEWALI AND RORANWALA ON KKP FKA SECTION(lakhewali khrunj line) 10290 | 646616 | 13788 | 660404 | 2014-05-01 | 2017-05-01
19 | Replacement of 66 KV Rail Pole Line from 220 KV G/S/S Patran to 66 KV G/S/S Dirba with DC/DC Ringmain Type Towers 10291 | 571460 | 12185 | 583645 | 2016-02-01 | 2020-05-01
20 | 66 KV T-off for Baltana T-off from existing 66 kv Mubarakpur-Dhakoli line SC on DC 10291 | 511868 | 10914 | 522782 | 2016-04-01 | WIP (Stay on Baltana S/S)
21 | Mour Rampura line 3719 SAGGING | 363703 | 7755 | 371458 | 2016-07-01 | work in progress
22 | 66KV Line Karmuwala-7940/ferozshah to khosa dan singh wala toff karmuwala | 88281 | 1882 | 90163 | 2014-03-01 | 2015-10-01
23 | 66 KV Jhunir-Boha T-off for 66 KV Daanewala | 12402 | 264 | 12666 | 2017-06-01 | 2017-12-01
24 | 66KV Line Malkotra Check Shere wala dc on dc-10290 | 2148968 | 45821 | 2194789 | 2015-05-01 | work in progress
25 | STR. AND SAGGING OF OF 66 KV LINE FROM FEROZ SHAH TO MALLANWALA 10290 | 990661 | 21123 | 1011784 | 2015-05-01 | 2019-05-01
26 | BHAGAPURANA TO SAMALSAR LINE STR. & SAGGING | 381101 | 8126 | 389227 | 2014-02-01 | 2016-06-01
27 | GHUBAYA JALABAD T-OFF CHAK JANISAR/OVERHEAD ELECTRIC CROSSING BAHANIWALA AND JALABAD RLY. STATION FZR FKA SECTION AND RORANWALA ON KKP FKA SECTION/VEREKO TO JALABAD DC AND 66KV OLD VEROKE TO JALABAD DISMANTLEMENT(Ghubaya fattanwala t point chak janisar)-10290 | 609814 | 13003 | 622817 | 2015-09-01 | 2017-03-01
28 | GHUBAYA TO MUKAND SINGH WALA - 9295 | 0 | 0 |  | 2015-02-01 | 2017-05-01
29 | 66KV Line Malout road-Dabwali road | 0 | 0 |  | 2018-03-01 | work in progress
30 | 66 KV Derabassi-Mubarkpur Line | 0 | 0 |  |  | WIP
31 | 66KV MES S/S to 66KV shakti Viihar (66kv LINE 220kv to 66KV Shakti vihar) DC on DC 2nd ckt | 125380 | 2673 | 128053 |  | wip
32 | UBEWAL TO MANGEWAL I/C SAGGING | 1491099 | 31794 | 1522893 | 2016-05-01 | 2016-11-01
33 | BAJA KHANA TO BAGRARI SC ON DC-10290 | 2841 | 61 | 2902 | 2016-06-01 | 2019-03-18
34 | MANGEWAL TO BALWAN sc on dc tower under forest div & distt sangrur | 234798 | 5006 | 239804 | 2016-04-01 | 2018-06-01
35 | 220 kv S/s Mansa-132 kv S/S Maur line LILO for 66 kv S/S Mansa Maur iwr no 985-new scheme | 10328 | 220 | 10548 | 2016-04-01 | 2017-02-01
36 | 66KV Line Bhucho-Nathana | 165734 | 3534 | 169268 | 2016-06-01 | 2016-12-01
37 | 66KV Line Mastewala toZira | 11200 | 239 | 11439 | 2011-10-01 | 2020-08-01
38 | kot sukhian to sandhawa | 4298600 | 91657 | 4390257 | 2014-02-01 | 2018-05-01
39 | o/h crossing b/w gainni zail singh & faridkot railway station on bti-ferozpur section-10290 | 1071436 | 22846 | 1094282 | 2017-08-01 | 2017-08-01
40 | 2nd ckt ferozshah to lohgarh thakran | 15372 | 328 | 15700 |  | WIP
41 | MASTEWALA TO ZIRA-10290 | 37305 | 795 | 38100 | 2011-10-01 | 2020-08-01
42 | 66 kv t-off nandgarh upto sangat line stubbing | 72388 | 1543 | 73931 |  | WIP
| Total REC for 17-18 | 31591171 | 673601 | 32264772 |  | WIP
B | Non-REC Works
1 | 66KV Line Malktora-Arniwala Malkotra | 9873609 | 210530 | 10084139 | 2015-05-01 | work in progress
2 | 66 KV D/C line from 220 KV S/s Lalru to 66 KV S/s Alamgir | 4799511 | 102338 | 4901849 |  | WIP
3 | 66 KV Lehragagga- Khandebad S/C on D/C Line | 52483 | 1119 | 53602 | 2016-04-01 | 2018-06-01
4 | 66 KV Sandour-Kuthala D/C on D/C Line | 1459 | 31 | 1490 | 2016-02-18 | 2018-02-18
5 | 66 KV from 220 KV S/S Focal Point Nabha- 66 KV S/s Samundgarh Line | 26203 | 559 | 26762 | 2016-05-01 | 2019-05-01
6 | 66 KV Cheema- Kanakwal Line | 25623 | 546 | 26169 | 2014-06-01 | 2015-10-01
7 | 66 KV Mehla Chowk- Nagra Line | 3807151 | 81178 | 3888329 | 2016-03-18 | 2018-02-18
8 | 66 KV Derabassi-Mubarkpur Line | 10523 | 224 | 10747 |  | WIP
9 | 66 KV D/C on D/C Bhawanigarh-Sangrur Line | 274723 | 5858 | 280581 | 2013-03-01 | 2014-10-01
10 | 66 KV power colony T-off Sohian Road Sangrur bhawanigarh sr 210 | 4029 | 86 | 4115 | 2016-02-18 | 2016-09-18
11 | 66KV Line Sadiq to Golewala | 87363 | 1863 | 89226 | 2015-04-01 | 2016-06-01
12 | 66KV LINE Kakrala- Badshahpur | 826683 | 17627 | 844310 |  | WIP
13 | 66KV Line Ferozepur to Mallan wala - 10290 | 114659 | 2445 | 117104 | 2014-09-01 | 2019-05-01
14 | 66KV Line Jhoktehal singh to Momdot | 291077 | 6207 | 297284 | 2013-05-01 | 2016-10-01
15 | sc/dc tower 66 kv mandhir line | 13480 | 287 | 13767 | 2016-03-01 | 2020-06-01
16 | 66 kv patran to khanori / ghanouri DC ON DC | 623057 | 13285 | 636342 | 2015-06-01 | 2015-10-01
17 | 66 kv bahadurgarh to ghanor | 24309 | 518 | 24827 | 2018-01-01 | 2020-01-01
18 | 66 kv line mangewal to balwan | 21454 | 457 | 21911 | 2016-04-01 | 2018-06-01
19 | abohar to khui khera t-off for churiwala dhanna | 516403 | 11011 | 527414 | 2015-05-01 | 2018-09-01
20 | ghubeya to dhandi qadim kadim JODHA BHAINI | 240397 | 5126 | 245523 | 2015-05-01 | 2017-02-01
21 | HRP line with s/c on d/c Rajpura Sarai Banjar | 1399656 | 29844 | 1429500 |  | wip
22 | Bhateri to ghanour line for chapper | 543828 | 11596 | 555424 |  | WIP
23 | BANUR TO MUBARAKPUR LINE | 1566829 | 33409 | 1600238 |  | wip
24 | 66 KV LINE FROM SUNAM SOLID TAP POINT FOR SHERON DC ON DC | 19981 | 426 | 20407 | 2016-05-01 | 2016-11-01
25 | survey and stocking of 66 kv line from dyalpura bhai ka-jalabad/dayalpura mirza toff jalal | 3181028 | 67828 | 3248856 | 2016-05-01 | 2016-07-01
26 | stringing and sagging of 2nd circuit of banur bhabat line | 14538 | 310 | 14848 |  | WIP
27 | 66KV Line Jalal- Dyalpura | 521 | 11 | 532 | 2016-09-01 | 2019-12-01
28 | STUBBING OF TOWER 66KV Line Thermal plant Lehra Mohabat- Phool S/C on D/C ring main | 37646 | 803 | 38449 | 2016-03-01 | 2019-03-01
29 | JOGA RAM THIRATH G/S/S TO NANGLA JARKIAN G/S/S (SURVEY AND RECO.) | 195004 | 4158 | 199162 | 2018-05-01 | 2018-07-01
30 | MALKOTRA 220 KV G/S/S TO ARNIWALA G/S/S (SURVEY AND RECO.) | 4311986 | 91943 | 4403929 | 2014-10-01 | 2015-04-01
31 | NANGLA JARKIAN 66 KV GSS TO KANEWAL 66 KV GSS jv no2/Revised Survey of 66 kv ss Nagla-Jaurkian to 66Kv SS Kahnewal | 17456273 | 372212 | 17828485 | 2018-05-01 | 2018-07-01
32 | badal to lambi line 2nd ckt survey of revised ROUTE PLAN | 1745841 | 37226 | 1783067 | 2018-05-01 | 2018-07-01
33 | 66KV SC on DC Line from 220KV S/S Banur to 66KV S/S Mubarakpur | 133522 | 2847 | 136369 |  | wip
34 | MALKOTRA TO ARNIWALA STR. & SAGGING | 4366103 | 93096 | 4459199 | 2017-10-01 | 2018-05-01
35 | DYALPURA BHAI KA TO JALABAD STR. AND SAGGING | 1450643 | 30931 | 1481574 | 2016-09-01 | 2018-10-01
36 | 66KV line 220KV S/S RAJLA to 66KV S/S BALBERA 2ND CKT 66 KV LINE | 96279 | 2053 | 98332 |  | wip
37 | 66KV Nabha-1 S/S to Gurditpura upto T-off 66KV line, exchange with SC on DC | 24190 | 516 | 24706 |  | 2017-03-01
38 | MALKOTRA TO ARNIWALA STUFFING ERR STR. & SAGGING | 1395302 | 29751 | 1425053 | 2017-10-01 | 2018-05-01
39 | 66KV line Guru Hargobind Thermal Plant Lehra Mohabbat to 66KV G/S/S Phool SC on DC | 19513 | 416 | 19929 | 2016-03-01 | 2019-03-01
40 | 66 kv sc on dc line for new ss hasanpur to join 66 kv line from dharamgarh to m/s oliver India pvt ltd | 1793492 | 38242 | 1831734 | 2017-03-01 | 2018-03-01
41 | MALKOTRA TO ARNIWALA multi circuit line iwr 979, your office memo no 2611 dt 30/916 | 129569 | 2763 | 132332 | 2017-10-01 | 2018-07-01
42 | providing 2nd ckt banga to manook line,your office memo no 3378 dt 8/9/16,banga-mandvi 2nd ckt | 803903 | 17141 | 821044 | 2013-11-18 | 2015-09-18
43 | 66KV Line Malkotara-madhir S/c on D/C | 217303 | 4633 | 221936 | 2016-03-01 | 2020-06-01
44 | dabwali road to barnala road dc on dc iwr 198/ revised dabwali road bti mes line survey & staking/Revised Railway crossing case for 66 kv Dabwali road Bathinda to MES Bathinda TP NO.168/10-168/11 | 259294 | 5529 | 264823 |  | WIP
45 | JHUNIR SARDULGARH IWR 895/Jhunir sardulgarh lilo at kahnewal | 4183003 | 89192 | 4272195 | 2014-12-01 | 2017-03-01
46 | 66 kv sc on dc line from dhuri mckt tl-30 to 66 kv ss Rangian | 4553849 | 97100 | 4650949 | 2017-01-01 | 2018-11-01
47 | 66 kv sc on dc line for kalodi t-off from 66 kv BBMB Sangrur to Bhawanigarh | 1751434 | 37345 | 1788779 | 2017-01-01 | 2018-01-01
48 | 66 kv sardulgarh to sangh T-OFF for sc on dc line for 66kv ss a s/s ahalupur (kauriwala) | 5924827 | 126332 | 6051159 | 2014-08-01 | 2018-03-01
49 | 66 KV Double CKT o/h crossing railway track between mast no. 5/8 & 5/9 b/w bti & behman diwana ryl station on BTI-SNG ryl section.( way leave & supervision charges)//66 kv dc on dc malout bti dabwali road iwr 917/u/g cable line b/w BTTI-Gahribhagi railway station of SSA-BTI sector | 1681716 | 35858 | 1717574 | 2015-05-01 | 2015-05-01
50 | Lalru to Handesar 2nd ckt stringing & Sagging smb no 28 pg 39 | 4523381 | 96450 | 4619831 | 2017-10-01 | WIP
51 | 66KV line G/S/S Phool to 66KV G/S/S Jethuke 2nd ckt | 410501 | 8753 | 419254 | 2018-01-01 | 2018-10-01
52 | Abohar-Khui khera T off churiwala dhanna | 1369330 | 29198 | 1398528 | 2017-10-01 | 2019-01-01
53 | 220 kv gss sunam to 66 kv gss sheron sc on dc 2ndckt line | 28538 | 608 | 29146 | 2017-05-01 | 2018-03-01
54 | 66KV Line M/Ckt Line 132KV S/S Badal to Lambi | 7828643 | 166927 | 7995570 | 2016-10-01 | 2018-05-01
55 | 66KV Line Mastewala to Gulari | 597803 | 12747 | 610550 | 2016-05-01 | 2017-08-01
56 | 66KV U/G 240 sqmm XLPE cable T-off for Mahes Gate T-off from existing 66KV Nabha-Ablowal line | 3759694 | 80166 | 3839860 |  | WIP
57 | bhadargarh to ghanour sc on dc line | 3144532 | 67049 | 3211581 |  | WIP
58 | 2ND CKT line jhunir to boha/Revised survey of Exit. Tl no 92 to 100 of 66 kv boha jhunir line of 1 ckt used for mansa jhunir | 1231243 | 26253 | 1257496 | 2016-06-01 | 2016-08-01
59 | Stubbing,Err,Stringing & sagg. Of 66 Kv line from Mastewala to Gurali | 342449 | 7302 | 349751 | 2016-05-01 | 2017-08-01
60 | Fathemajri to Bamna 2nd Ckt | 192744 | 4110 | 196854 | 2016-07-01 | 2017-02-01
61 | 66KV G/S/S Dhan Singh Khana to 66 KV G/S/S Ghasso khana SC on DC for tower | 4272728 | 91105 | 4363833 | 2016-05-01 | work in progress
62 | Survey of 66 kv lineJhunir to Raipur toff 66 kv gss moosa | 3698275 | 78857 | 3777132 | 2017-08-01 | 2020-06-01
63 | 2nd circuit of Ferozpur to chugtewala 66 kv toff atari line | 479832 | 10231 | 490063 | 2017-10-01 | work in progress
64 | 66 KV DC Ring Main line from GNDTP bathinda to malout road | 378180 | 8064 | 386244 | 2016-03-01 | 2016-10-01
65 | Survey of t off ferozshah to mallanwala line for 66 kv gss sudh singh wala | 9884 | 211 | 10095 | 2019-03-01 | 2020-04-01
66 | survey of 66 kv line btwn khosa dan singh to kassoana | 108359 | 2310 | 110669 | 2017-06-01 | 2017-09-01
67 | Survey of matti to gurthari | 2064259 | 44015 | 2108274 |  | WIP
68 | Const of 66 kv towr line from 220 v malkotra to madhir sc on dc line under forest division shri mukatsaar Sahib. | 42873 | 914 | 43787 | 2016-03-01 | 2020-06-01
69 | 2nd ckt on existing towers jhunir to sardulgarh | 139218 | 2968 | 142186 |  | WIP
70 | lakhewali bhagsar toff line dismantlement | 6690 | 143 | 6833 |  | WIP
71 | MALKOTRA TO MADHIR SC ON DC | 7137 | 152 | 7289 | 2016-03-01 | 2020-06-01
72 | Shifting of Gantry at 220kv S/S Chhajli | 104280 | 2224 | 106504 |  | WIP
73 | 66 Kv line jog ram tirath to nangla | 98513 | 2101 | 100614 | 2017-06-01 | work in progress
74 | Humbra to adda dakkha | 43100 | 919 | 44019 | 2014-05-01 | work in progress
75 | Const. of 66kv mallanwala kamala midha line | 114345 | 2438 | 116783 | 2013-05-01 | 2015-06-01
76 | SODEWALA TO CHUGTEWALA(66 kv zira gate to chugatewala) | 10461 | 223 | 10684 | 2012-10-01 | 2014-05-01
77 | Survey of 66 kv link line 66kv gss rumuwala to gss charik | 37781 | 806 | 38587 |  | WIP
78 | preliminary survey and 66 kv line BOTTIANWALA MAKHU TO DAN SINGH WALA | 167821 | 3578 | 171399 | 2016-06-01 | 2016-09-01
79 | preliminary survey and 66 kv ss bhaloor to 66 kv ss kot sukhian | 42392 | 904 | 43296 | 2016-06-01 | 2016-09-01
80 | SURVEY 66 KV RPL JOGA RALLA TO PAKHOKALAN/66 KV rail pole line Joga ralla to pakho kalan SC on DC | 4249610 | 90613 | 4340223 | 2018-02-01 | 2019-03-01
81 | survey of 66 kv line talwandi sabo to maur line | 60402 | 1288 | 61690 | 2017-06-01 | 2017-08-01
82 | Survey of 66 kv u/g cable gss abohar to khui khera | 12655 | 270 | 12925 | 2019-06-01 | 2019-09-01
83 | Survey of 66 kv u/g cable gss malout to 66 kv new gss malout/132KV S/S Malout to 66 KV New Malout Under APDRP line ckt. U/G.(TL-654) | 14468214 | 308499 | 14776713 | 2017-06-01 | 2017-08-01
84 | 66kv link line 66kv gss dugru to 66kv daulatpura sc on dc | 398868 | 8505 | 407373 | 2017-01-01 | work in progress
85 | Survey of 66kv link line 66kv gss fathegarh kortana to 66kv gss bhinder kalan | 58497 | 1247 | 59744 | 2016-05-01 | 2016-08-01
86 | SURVEY OF BANWALA TO HANWANTA to gss khui khera | 76623 | 1634 | 78257 | 2018-06-01 | 2018-10-01
87 | Survey of jhunir to boha line toff gss tahlian | 41777 | 891 | 42668 | 2018-01-01 | 2018-05-01
88 | Survey of replacement 66 kv rpl 66 kv gss jhok tehal singh to 66kv gss guru har sahai | 112598 | 2401 | 114999 | 2017-06-01 | 2017-09-01
89 | Survey of replacement 66kv rpl 132kv badni kalan to bilaspur | 1228711 | 26199 | 1254910 | 2018-02-01 | 2019-09-01
90 | Survey of replacement 66kv rpl 220kv dharamkot to mastian to fathegarh panjor | 130308 | 2779 | 133087 | 2017-07-01 | 2017-10-01
91 | Survey of replacement of 66 kv sc on dc line mansa (bikhi ) to dhalewan and lilo of 66 kv ss bikhi | 69153 | 1475 | 70628 |  | WIP
92 | survey of replacement of rpl abohar to khui sarvar | 143310 | 3056 | 146366 | 2017-12-01 | 2018-04-01
93 | jalal-dayalpur bhaika 66 kv line construction new line | 5446205 | 116127 | 5562332 | 2017-06-01 | 2019-05-01
94 | Talwandi sabo to rama survey | 385212 | 8214 | 393426 | 2017-01-01 | 2017-04-01
95 | Mansa to Kot Dharmu sc on dc tower survey | 8199553 | 174835 | 8374388 | 2017-06-01 | 2017-10-01
96 | Daulatpura to Khora kotta/khosa kotla sc on dc | 6811413 | 145237 | 6956650 | 2018-05-01 | work in progress
97 | kot karor to dagru survey | 3426067 | 73052 | 3499119 | 2017-06-01 | 2017-10-01
98 | Mukatsar to Fattanwala survey | 93043 | 1984 | 95027 | 2017-06-01 | 2017-10-01
99 | Stubbing of 66 kv rp line Mansa-Raipur | 807286 | 17213 | 824499 |  | WIP
100 | t off hasanpur from 66kv ss dharamgarh to oliver industry | 34258 | 730 | 34988 | 2017-03-01 | 2018-03-01
101 | 66 kv t off line jiwan Aral to be link with new tower line./66 Kv line ghubaya guru har sahai jeewa arian | 323761 | 6903 | 330664 | 2008-04-01 | 2010-09-01
102 | 66 KV Line from Mudki to Kotakror | 375642 | 8010 | 383652 | 2014-05-01 | 2015-09-01
103 | 66 kv Line (fall in tower) Ferozpur to Chugtewala | 291775 | 6221 | 297996 | 2017-12-01 | 2018-12-01
104 | lilo route plan sangrur patran dirba route plan | 9774 | 208 | 9982 | Work discarded
105 | maatewala to makhu restoration of supply new line | 194341 | 4144 | 198485 | 2017-06-01 | 2017-06-01
106 | sukhanwala to baja marar erection | 28672 | 611 | 29283 | 2017-06-01 | 2017-09-01
107 | malout to new malout sc on dc line survey and staking | 7377 | 157 | 7534 | 2017-06-01 | 2017-09-01
108 | u/g cable 132 kv gss abohar to 66 kv gss khui khera survey | 13831 | 295 | 14126 | 2017-05-01 | 2017-08-01
109 | Dismantlement hr pole line bbmb 220 kv sangrur to bhawanigarh | 766557 | 16345 | 782902 | 2017-11-01 | 2018-05-01
110 | nagla jorkian to kahnewal | 622076 | 13264 | 635340 | 2018-06-01 | work in progress
111 | RPL Samana toff bhamana | 64850 | 1383 | 66233 | 2016-07-01 | 2017-02-01
112 | Survey & repl. Sadiq to Jhok tehal singh wala mckt ring main line | 124354 | 2652 | 127006 | 2017-06-01 | 2017-08-01
113 | 66 kv t-off nandgarh upto sangat line for strining and saging | 1353071 | 28851 | 1381922 | 2017-06-01 | 2018-05-01
114 | 66 KV Rail pole line from 220 KV S/S Jhunir to 66 KV S/S Mansa T off | 642334 | 13696 | 656030 | 2017-10-01 | 2020-02-01
115 | jhunir to boha Shifting of gantry | 187300 | 3994 | 191294 | 2017-10-01 | 2017-11-01
116 | Dharamgarh to Hasanpur 2nd ckt line inspection fee | 504 | 11 | 515 | 2017-03-01 | 2018-03-01
117 | gndtp to mct ral | 54467 | 1161 | 55628 |  | WIP
118 | Saidpura to lalru lilo 66 kv haripur kurah ring main line proposed route plan | 9832 | 210 | 10042 |  | WIP
119 | Burj Dhilwan on jogga forest case | 97634 | 2082 | 99716 |  | WIP
120 | 66 KV S/S Fatehgarh kotrana to 66Kv Bhandari kalan | 177790 | 3791 | 181581 | 2017-04-01 | work in progress
121 | Rail pole line Badni to bilaspur Replacement 66 KV SC on DC tower | 26015 | 555 | 26570 | 2018-02-01 | 2019-09-01
122 | kharar to banur mckt | 5636341 | 120181 | 5756522 | 2016-04-01 | 2018-11-01
123 | Gantry shifting at 66 kv old rajpura | 5724 | 122 | 5846 | wip | wip
124 | bhadurgarh to ghanour | 413773 | 8823 | 422596 | 2019-10-01 | 2020-01-01
125 | u/g cable gss malout to 66 kv gss malout survey | 11526 | 246 | 11772 | 2017-10-01 | 2018-02-01
| Total Non-REC year 17-18 | 173839339 | 3706697 | 177546036 |  | WIP
C | Deposit Works
1 | 66kv DC tower line Airport Mohali T-off from 220KV Banur-Ansal (66kv mckt line Khara-Banur line) | 890645 | 0 | 890645 | 2016-06-01 | 2018-10-01
2 | 66 kv gami wala to surya | 197964 | 0 | 197964 |  | WIP
3 | 66 kv line dc from 220 kv s station phase 6 to tdi hamir developer mohali phase 7 | 174971 | 0 | 174971 |  | 2016-06-01
4 | route plan 66 kv HRP dhanoula to badrukha | 78090 | 0 | 78090 |  | WIP
5 | 66 kv DC Rajpura-Banur line at liberty chownk Rajpura on NH-64 | 2927895 | 0 | 2927895 | 2015-10-01 | 2017-06-01
6 | 66 KV SC Rajpura-Naushera line due to ovrhead road bridge on NH-64 | 577642 | 0 | 577642 | 2016-11-01 | 2017-04-01
7 | 66 KV SC on DC line from 66 KV S/S Focal point Rajpura to 66KV S/S M/s Asian fine cement | 9951845 | 0 | 9951845 | 2019-12-01 | 2020-01-01
8 | Shifting of Dabwali Road Barnala RP line new bustand patel nagar | 79954 | 0 | 79954 |  | WIP
9 | 66 KV BARNALA PAKHOKE RAIL LINE | 3657398 | 0 | 3657398 |  | WIP
10 | Raising of Badni Bilaspur for roarke kalan | 745817 | 0 | 745817 | 2016-11-01 | 2017-12-01
11 | 66 KV HANDAYA TO DHANULA LINE/66 KV D/C Line from 220 KV S/S Handiaya to Mehalkalan & Malwa) | 2666248 | 0 | 2666248 | 2016-10-01 | 2017-12-01
12 | 66 KV HANDAYA TO THIKRIWALA LINE PAKHOKE M/CKT LINE | 379678 | 0 | 379678 |  | WIP
13 | 66 KV BARNALA PAKHOKERAIL LINE AT JODHPUR CHEEMA/Raising of SC/DC line LILO from 66 KV Barnala-Pakhoke line at Jodhpur-Cheema on NH-71 | 931695 | 0 | 931695 | 2016-10-01 | 2017-05-01
14 | 66 KV HANDAYA TO BARNALA H RAIL LINE | 1627705 | 0 | 1627705 |  | WIP
15 | 66KV BADNI DODARA LINE/ raising of 66 kv line 12 no. line badni to daoda on nh-71 deposit work of 66 kv line from nh-71 ( barnala to jalandhar NH Road) | 894838 | 0 | 894838 | 2016-10-01 | 2017-12-01
16 | 66kv SC on DC line from 66KV Barnala -Pakhoke on NH-71 | 879843 | 0 | 879843 | 2016-10-01 | 2017-05-01
17 | 66KV Moga-Badni H-Rail pole line on NH-71 | 967120 | 0 | 967120 | 2016-10-01 | 2018-05-01
18 | 66KV Line Pacca Kaleke-Gross Spin deposit work | 99675 | 0 | 99675 |  | WIP
19 | 66KV SC on DC 66kv S/S Dharamgarh o M/s Oliver Engineers Sandharsi /66 kv line HASANPUR TOFF FROM 66 KV DHARAMGARH to OLIVER INDIA PVT LTD. | 136943 | 0 | 136943 | 2017-03-01 | 2018-03-01
20 | MANNKHERA TO SANGHA LINE MS MIHIT SOLAR PLAN SURVEY | 52506 | 0 | 52506 |  | WIP
21 | 66kv DC Baran-Bahadurgarh DC on DC line on NH-64-work closed in 1/18 exp finalise 4862638 iwr 190 | 179402 | 0 | 179402 | 2015-10-01 | 2016-02-01
22 | SURVEY AND STAKING FOR RAISING BIO MASS GULABWALA LUBANIAWALI/lubaniwali to gulabewali sc line for jasseana magatker road | 167862 | 0 | 167862 |  | WIP
23 | Fallen tower on 66KV line Badrukhan-Khillrian line | 467231 | 0 | 467231 | 2018-01-01 | 2018-01-01
24 | Revised route plan for raising 66 kv dc line from 66 kv ss tapa to 66 kv ss joga due to construction of overhead bridge at nh-64 dw | 205975 | 0 | 205975 | 2017-10-01 | 2018-01-01
25 | Proposed route plan for raising / Shifting of 220 kv ss Handiyan to Dhola due to const of overhead bridge at nh 64 dw | 236946 | 0 | 236946 | 2016-03-01 | 2016-08-01
26 | Proposed route plan for raising / Shifting of 66 kv sc line from dhanoula sanghera of ms trident ltd barnala due to construction of overhead bridge at nh64 dw | 123050 | 0 | 123050 | 2016-03-01 | 2016-08-01
27 | survey of shifting of 66 kv line mastewala sekhuwala for nh-15 smb no 23 pg 45 | 1058376 | 0 | 1058376 |  | WIP
28 | survey of revised route plan of 66 kv line mastewala zira for nh-15 smb no 23 pg 45 | 203583 | 0 | 203583 |  | WIP
29 | Raising of Dala to Ramuwal from nh-64,your office memo no 3378 dt 8/9/16 | 1134187 | 0 | 1134187 | 2016-11-01 | 2017-12-01
30 | Raising of Badhni Bilaspur for roarke kalan from nh-71,your office memo no 3378 dt 8/9/16 | 929025 | 0 | 929025 | 2016-11-01 | 2017-12-01
31 | Himmatpura to gehlan from nh 64 | 929118 | 0 | 929118 | 2016-11-01 | 2017-12-01
32 | Deposit Work of Raising/Shifting of 66 KV SC on DC Line Himatpura- Tallewal on NH-71 | 993829 | 0 | 993829 | 2016-11-01 | 2017-12-01
33 | fallen tower sunam-nagra dc on dc,your office memo no 3378 dt 8/9/16 | 118702 | 0 | 118702 | 2016-06-01 | 2016-06-01
34 | moga to kishanpura for nh-71 | 1064561 | 0 | 1064561 | 2016-11-01 | 2017-12-01
35 | 66 kv line dhurito katron old line from railway track ,your office memo no 3378 dt 8/9/16 | 4620563 | 0 | 4620563 | 2017-12-01 | 2018-05-01
36 | Shifting of 66 kv line from 220 kv bbmb sangrur to patran ckt-1 from railway track | 4380422 | 0 | 4380422 | 2017-12-01 | 2018-03-01
37 | KHARAR BANUR U/G CABLE RAILWAY CASE/Revised route plan for 66 kv mckt kharar ansal line b/w tl 86-80 ryl. Crossing from u/g to o/h line | 1890707 | 0 | 1890707 | 2017-03-01 | 2018-11-01
38 | Kharar-Banur line on mckt towers inside lark City Landran iwr 48/3 | 4121443 | 0 | 4121443 |  | WIP
39 | 66KV SC on DC line from 66KV S/S Bamna to T-off point Gajewas-NON RC | 1598726 | 0 | 1598726 | 2016-07-01 | 2017-02-01
40 | Kot karor To Dagru nh 15 | 5271561 | 0 | 5271561 | 2014-06-01 | 2015-08-01
41 | Dona Mattar Crossing Tower satluj river | 2108127 | 0 | 2108127 |  | WIP
42 | 66KV SC line on H-Pole Moga-Dala on jal-Bar road on NH-71 | 1719183 | 0 | 1719183 | 2014-06-01 | 2015-08-01
43 | 66KV SC on DC line Himatpura-Bilaspur on NH-71 | 1150047 | 0 | 1150047 | 2017-01-01 | 2017-12-01
44 | Shifting of 66KV Patran-Kakrala line | 229361 | 0 | 229361 |  | WIP
45 | 66KV SC on DC line from 66kv s/s Handesra to 66KV S/S M/s Pragati Paper Industry Ltd. Village Handesra, Derabassi | 3450124 | 0 | 3450124 | 2016-11-01 | 2017-06-01
46 | 66 kvrpl ablowal to patiala line for premises of S. GHUMAN SINGH S/O KIRPAL SINGH OF VILL SIDHUWAL | 1667930 | 0 | 1667930 | 2017-05-01 | 2018-01-01
47 | Proposed route plan for 2nd ckt t off line from 220kv sector 80mohali 220kv phase 8 mohali 66 kv ss sec 88 near purba apatments | 650854 | 0 | 650854 | 2017-05-01 | 2018-10-01
48 | LARK PROJECT | 774467 | 0 | 774467 |  | WIP
| Total Deposit works year 17-18 | 69363834 | 0 | 69363834
|  | Amount | Interest | Total
| REC | 31591171 | 673601 | 32264772
| NREC | 173839339 | 3706697 | 177546036
| DEPOSIT works | 69363834 | 0 | 69363834
| Total for FY 2017-18 | 274794344 | 4380298 | 279174642

## 2018-19
AO /TL Patiala for FY 2018-19
| Name of work | total exp on work | int A&R | g.total | DATE OF START | DATE OF COMPLETION
A | REC Works
1 | 66 KV MANGWAL TO SUNAM/Stringing of 2nd ckt. With 0.2 sq'' conductor on DC Towers from Ubhewal to T-off point for Sangrur-Bhawanigarh ckt.I (10291) | 763665 | 288285 | 1051950 | 2016-05-01 | 2016-11-01
2 | 66KV LINE BANGA TO MANDVI ON 2ND CKT | 2347418 | 886154 | 3233572 | 2017-05-01 | 2019-04-01
3 | 66 kv line tibbi khurd to pujuke | 1816586 | 685764 | 2502350 |  | W.I.P
4 | 66 kv lalru to handesran | 1822990 | 688181 | 2511171 | 2017-10-01 | WIP
5 | 66kv line ferozshah to khosa dal singh t-off karamuwala | 1679253 | 633920 | 2313173 | 2014-04-01 | 2015-06-01
6 | 66 kv jalabad to fathanwala | 445414 | 168145 | 613559 | 2016-06-01 | 2017-04-01
7 | 66 kv sardulgarh sangha t-off ahlupur line | 19356 | 7307 | 26663 |  | W.I.P
8 | 66 kv jalal to dayalpur bhaika | 4383254 | 1654685 | 6037939 | 2017-07-01 | 2019-05-01
9 | 66 kv t-off gill kalan 2nd ckt | 4245014 | 1602498 | 5847512 | 2018-04-01 | 2018-11-01
10 | 66KV Line Malkotra Check Shere wala dc on dc-10290 | 1633206 | 616537 | 2249743 | 2015-01-01 | work in progress
11 | UBHAWAL TO MANGEWAL 66KV LINE | 1864366 | 703801 | 2568167 | 2016-05-01 | 2016-11-01
12 | survey of 66 kv handiaya -Barnala | 58502 | 22084 | 80586 |  | WIP
13 | JOGA RAM THIRATH G/S/S TO NANGLA JARKIAN G/S/S (SURVEY AND RECO.) | 581644 | 219571 | 801215 | 2017-12-01 | 2018-04-01
14 | OVERHEAD ELECTRIC CROSSING BAHANIWALA AND JALABAD RLY. STATION FZR FKA SECTION AND RORANWALA ON KKP FKA SECTION/VEREKO TO JALABAD DC AND 66KV OLD VEROKE TO JALABAD DISMANTLEMENT(Ghubaya fattanwala t point chak janisar)-10290 | 114804 | 43338 | 158142 | 2018-07-01 | 2018-07-01
15 | Revised estimate for providing 2nd ckt of 66 kv ubhewal to mangewl sc on dc,your office memo no 3378 dt 8/9/16 | 118412 | 44701 | 163113 | 2016-05-01 | 2016-11-01
16 | ADDITIONAL WORK FOR STRING 2CKT T-OFF 66KV PHOOL GILL KALAIN GSS PHOOL | 124293 | 46921 | 171214 |  | W.I.P
17 | 66KV Line phool Jethu ke T-off Gill Kalan - 7940 | 174526 | 65884 | 240410 | 2018-04-01 | 2018-11-01
18 | 66KV Line DC Sandhwa to Kotkapura/OVERHEAD ELECTRIC CROSSING KOATKPURA AND WANDER JATAN RLY 10290 | 204709 | 77278 | 281987 | 2018-07-01 | work in progress
19 | 2nd ckt ferozshah to lohgarh thakran 10290 | 251441 | 94919 | 346360 | 2014-02-01 | 2015-05-01
20 | 66KV Line Banghi Nihal- Sekhu sc on dc towers 10290 d/c o/h line b/w RMN-SGA railway station of sirsa BTI | 252634 | 95369 | 348003 | 2018-01-01 | 2018-06-01
21 | 66 kv line 220 kv passiana to 66 kv gajju majra 3719 | 259573 | 97989 | 357562 | 2015-11-01 | 2019-01-01
22 | MANGEWAL TO BHALWAN sc on dc tower under forest div & distt sangrur | 304539 | 114964 | 419503 | 2016-04-01 | 2018-06-01
23 | Baghapurana to Samalsar IWR No. 1041 | 346323 | 130737 | 477060 | 2015-06-01 | 2016-10-01
24 | Replacement of 66 KV Rail Pole Line from 220 KV G/S/S Patran to 66 KV G/S/S Dirba with DC/DC Ringmain Type Towers 10291 | 505958 | 191000 | 696958 | 2016-02-01 | 2020-05-01
25 | 66 kv line Chaksherewala-Lakhewali -10290 | 613588 | 231631 | 845219 | 2017-03-01 | 2018-08-01
26 | STR. AND SAGGING OF OF 66 KV LINE FROM FEROZ SHAH TO MALLANWALA 10290 | 675715 | 255083 | 930798 | 2017-03-01 | 2018-05-01
27 | Kharunj to Chak Janisar line 10290 | 708432 | 267434 | 975866 | 2018-05-01 | 2018-12-01
28 | 66KV RINGMAIN TOWER LINE GHTP TO PHOOL | 810288 | 305885 | 1116173 | 2016-03-01 | 2019-03-18
29 | 66KV Line 2nd CKT Arniwala- Ghattanwali 2nd ckt with dc tower 10290 | 819374 | 309315 | 1128689 | 2017-02-01 | 2018-05-01
30 | Restoration of supply ghubaya jalalabad | 857538 | 323722 | 1181260 | 2014-07-01 | 2014-07-01
31 | BAGHA PURANA TO SAMALSAR LINE STR. & SAGGING | 918173 | 346612 | 1264785 | 2015-06-01 | 2016-10-01
32 | kot sukhian to sandhawa | 949478 | 358429 | 1307907 | 2010-05-01 | 2012-10-01
33 | 66KV Line DC Ghattianwali-Chimnewala 10290 | 1032308 | 389698 | 1422006 | 2018-10-01 | 2019-05-01
34 | 66KV Line Ghubaya-Fattanwala upto Jallabad T off for Chak janisar-10290 | 1249390 | 471646 | 1721036 | 2016-01-01 | 2017-03-01
35 | Replacement of 66 KV HRP Line from 220 KV S/Stn BaJakhana to 66 KV S/Stn Bargari with SC/DC Tower line 10290 | 1950714 | 736397 | 2687111 | 2016-06-01 | 2019-03-18
36 | 66KV S/S JAGARAM TIRATH T 66 KV NANGAL JORDIAN SC ON DC STRINGING | 3627817 | 1369506 | 4997323 | 2017-06-01 | work in progress
37 | lehra mohabbat to phool -TRANF TO NREC,NOW 12115 | 4686579 | 1769190 | 6455769 | 2016-03-01 | 2019-03-18
38 | 66KV line from 220KV S/S Bhateri to 66KV S/S Ghanour 2nd ckt | 6125664 | 2312447 | 8438111 |  | WIP
| Total REC works | 49342938 | 18627027 | 67969965 |  | W.I.P
B | Non-REC Works
1 | 66KV Line Baja Khana-Jeeda | 9031 | 3409 | 12440 | 2017-06-01 | 2018-05-01
2 | 66KV Line Jalabad-Fattan Wala | 29589 | 11170 | 40759 | 2017-06-01 | 2018-06-01
3 | 66KV Line Baghapurana-Smalsar | 123134 | 46483 | 169617 | 2015-06-01 | 2016-10-01
4 | 66KV Line Lohgarh-Chugtewala(2nd CKT) | 221676 | 83683 | 305359 | 2015-08-01 | 2016-12-01
5 | 66 KV D/C line from 220 KV S/s Lalru to 66 KV S/s Alamgir | 4463297 | 1684901 | 6148198 |  | WIP
6 | 66 KV Abohar-Amarpura Line | 150729 | 56901 | 207630 | 2012-02-01 | 2013-01-01
7 | 66 KV S/C on D/C Line from 220 KV S/S Passiana to 66 KV S/S Gajjumajra | 1277795 | 482369 | 1760164 | 2015-11-01 | 2019-01-01
8 | 66 KV Paras Ram Nagar-Dabwali Road | 64091 | 24195 | 88286 | 2017-05-01 | 2018-06-01
9 | 66 KV Sandour-Kuthala D/C on D/C Line | 165964 | 62652 | 228616 | 2016-02-18 | 2018-02-18
10 | 66 KV from 220 KV S/S Focal Point Nabha- 66 KV S/s Samundgarh Line | 5366484 | 2025855 | 7392339 |  | 2019-05-01
11 | 66 KV Mehla Chowk- Nagra Line | 929495 | 350886 | 1280381 | 2016-03-18 | 2018-02-18
12 | 66 KV Longowal - Sheron D/C on D/C lIne | 651900 | 246093 | 897993 |  | W.I.P
13 | 66 KV Banga-Moonak Line 2nd Ckt | 442739 | 167134 | 609873 | 2013-11-18 | 2015-09-18
14 | 66KV Line baja Khana to Bhagta | 2427326 | 916319 | 3343645 | 2015-05-01 | 2016-04-01
15 | 66 kv line Khurunj-Chak Janesar | 6860 | 2590 | 9450 | 2017-05-01 | 2018-09-01
16 | 66 kv line Gahttian Wala- Chimniwal | 98795 | 37295 | 136090 | 2017-04-01 | 2019-10-01
17 | 66 kv line t-off bajeke | 2259837 | 853091 | 3112928 | 2017-02-01 | 2019-10-01
18 | 66KV Line baja Khana to Bagrarhi | 3360882 | 1268738 | 4629620 | 2016-06-18 | 2019-03-18
19 | 66KV Line Malktora ChakShere wala -10290 | 270751 | 102209 | 372960 | 2017-02-01 | work in progress
20 | 66KV Line Jhoktehal singh to Momdot | 3128538 | 1181027 | 4309565 | 2017-05-01 | 2018-09-01
21 | 66 kv sandhwa faridkot | 9507657 | 3589154 | 13096811 | 2018-05-01 | 2018-10-01
22 | 66 kv line deep singh wala | 197413 | 74524 | 271937 | 2017-05-01 | 2018-10-01
23 | sc/dc tower 66 kv mandhir line | 431512 | 162896 | 594408 | 2016-03-18 | 2020-06-01
24 | 66KV Line Malkotra Gillzewala | 23249 | 8777 | 32026 | 2015-07-01 | 2016-05-01
25 | 66KV Line Bangi Nihal Singh to Sekhu | 34785 | 13132 | 47917 | 2015-06-01 | 2016-10-01
26 | survey & staking of 66 kv mastewala to makhu tower line | 4245 | 1602 | 5847 | 2017-02-01 | 2017-05-01
27 | abohar to khui khera t-off for churiwala dhanna | 699714 | 264143 | 963857 | 2018-05-01 | 2019-10-01
28 | 66KV Line LUBANIAWALI to gulabeWala | 11483 | 4335 | 15818 | 2017-01-01 | 2017-12-01
29 | malout sangat line | 42923 | 16203 | 59126 | 2017-04-01 | 2018-09-01
30 | GHUBEYA TO JALALABAD T-OFF CHAK JANISAR LINE | 23950 | 9041 | 32991 | 2017-02-01 | 2018-09-01
31 | OVERHEAD ELECTRIC CROSSING AT 343/G GIANI ZAIL SINGH FARIDKOT-10290 | 3224796 | 1217365 | 4442161 | 2018-10-01 | 2018-10-01
32 | GNDTP MALOUT ROAD RING MAIN | 19431 | 7335 | 26766 | 2017-10-01 | 2017-11-01
33 | ghubeya to dhandi qadim kadim JODHA BHAINI | 130782 | 49370 | 180152 | 2016-06-01 | 2017-10-01
34 | VAJID KE NANDGARH LINE M/S PARSHOTAM | 105646 | 39881 | 145527 | 2018-06-01 | 2019-05-01
35 | stringing and sagging of 2nd circuit of 66 kv line from 220 s/s Mohali to ICI paint factory | 2511309 | 948022 | 3459331 | 2018-04-01 | 2019-05-01
36 | 66 KV LINE FROM SUNAM SOLID TAP POINT FOR SHERON DC ON DC | 5093 | 1922 | 7015 | 2016-05-01 | 2016-11-01
37 | survey and stocking of 66 kv line from dyalpura bhai ka-jalabad/dayalpura mirza toff jalal | 59755 | 22557 | 82312 | 2016-06-01 | 2016-09-01
38 | MALKOTRA 220 KV G/S/S TO ARNIWALA G/S/S (SURVEY AND RECO.) | 417433 | 157581 | 575014 | 2016-05-01 | 2016-08-01
39 | NANGLA JORKIAN 66 KV GSS TO KANEWAL 66 KV GSS jv no2/Revised Survey of 66 kv ss Nagla-Jaurkian to 66Kv SS Kahnewal | 2710910 | 1023372 | 3734282 | 2017-06-01 | 2017-09-01
40 | 66KV line 220KV S/S RAJLA to 66KV S/S BALBERA 2ND CKT 66 KV LINE | 80203 | 30277 | 110480 |  | WIP
41 | MALKOTRA TO ARNIWALA STUFFING ERR STR. & SAGGING | 111278 | 42008 | 153286 | 2017-05-01 | work in progress
42 | survey of 66 kv mastewala to gulari line | 74186 | 28006 | 102192 | 2017-05-01 | 2018-10-01
43 | 66 kv sc on dc line for new ss hasanpur to join 66 kv line from dharamgarh to m/s oliver India pvt ltd | 243710 | 92001 | 335711 | 2017-03-01 | 2018-03-01
44 | MALKOTRA TO ARNIWALA multi circuit line iwr 979, your office memo no 2611 dt 30/916 | 2855605 | 1077995 | 3933600 | 2016-06-01 | work in progress
45 | providing 2nd ckt banga to manook line,your office memo no 3378 dt 8/9/16,diff from banga-mandvi 2nd ckt | 566529 | 213866 | 780395 | 2014-06-01 | 2016-01-01
46 | dabwali road to barnala road dc on dc iwr 198/ revised dabwali road bti mes line survey & staking/Revised Railway crossing case for 66 kv Dabwali road Bathinda to MES Bathinda TP NO.168/10-168/11 | 23529 | 8882 | 32411 | 2016-05-01 | 2016-08-01
47 | 66 kv fattehwala t-off pakka kalan | 78656 | 29693 | 108349 | 2017-06-01 | 2019-08-01
48 | 66 kv sc on dc line from dhuri mckt tl-30 to 66 kv ss Rangian | 11766522 | 4441878 | 16208400 | 2017-01-01 | 2018-11-01
49 | 66 KV Double CKT o/h crossing railway track between mast no. 5/8 & 5/9 b/w bti & behman diwana ryl station on BTI-SNG ryl section.( way leave & supervision charges)//66 kv dc on dc malout bti dabwali road iwr 917/u/g cable line b/w BTTI-Gahribhagi railway station of SSA-BTI sector | 32279 | 12186 | 44465 | 2018-10-01 | 2018-10-01
50 | Lalru to Handesar 2nd ckt stringing & Sagging smb no 28 pg 39 | 557281 | 210374 | 767655 | 2017-10-01 | WIP
51 | 66 KV SC on DC line for new 66 kv ss Chapper t-off of existing 66 kv line from 220 kv ss Bhateri to 66 KV ss Ghanour //66KV line from 220KV S/S Bhateri to 66KV S/S Ghanour 2nd ckt | 1037946 | 391826 | 1429772 | 2016-12-01 | 2017-06-01
52 | 66KV Line Malout road-Dabwali road same as 344 | 351849 | 132824 | 484673 | 2018-06-01 | work in progress
53 | 66KV line G/S/S Phool to 66KV G/S/S Jethuke 2nd ckt,gillkalan to jethuke | 2514546 | 949244 | 3463790 | 2018-04-01 | 2018-11-01
54 | Abohar-Khui khera T off churiwala dhanna | 441077 | 166507 | 607584 | 2017-06-01 | 2018-10-01
55 | 66KV Line M/Ckt Line 132KV S/S Badal to Lambi | 329167 | 124261 | 453428 | 2017-05-01 | 2018-10-01
56 | 66KV Jhunir-Sardhulgarh Line Lilo for 66 KV GSS Kahnewal | 14820 | 5594 | 20414 | 2017-02-01 | 2018-05-01
57 | 66KV G/S/S Dhan Singh Khana to 66 KV G/S/S Ghasso khana SC on DC for tower | 4284071 | 1617243 | 5901314 | 2017-05-01 | work in progress
58 | Survey of 66 kv lineJhunir to Raipur toff 66 kv gss moosa | 1278373 | 482588 | 1760961 | 2018-05-01 | 2020-02-01
59 | ferozshah to mallanwala line for 66 kv gss sudh singh wala | 2523624 | 952671 | 3476295 | 2018-02-01 | 2019-01-01
60 | matti to gurthari | 1617674 | 610674 | 2228348 |  | WIP
61 | lakhewali bhagsar toff line dismantlement | 164424 | 62070 | 226494 | 2017-05-01 | 2017-10-01
62 | Shifting of Gantry at 220kv S/S Chhajli | 237479 | 89648 | 327127 |  | W.I.P
63 | 66 Kv line joga ram tirath to nangla | 326521 | 123262 | 449783 | 2018-05-01 | work in progress
64 | Humbra to adda dakkha | 2423151 | 914743 | 3337894 | 2018-06-01 | 2019-05-01
65 | Const. of 66kv mallanwala kamala midha line | 142500 | 53794 | 196294 | 2017-05-01 | 2018-09-01
66 | 66 kv line BOTTIANWALA MAKHU TO DAL SINGH WALA | 23505695 | 8873432 | 32379127 | 2018-02-01 | work in progress
67 | 66 kv ss bhaloor to 66 kv ss kot sukhian | 745293 | 281349 | 1026642 | 02-20018 | work in progress
68 | 66 KV RPL JOGA RALLA TO PAKHOKALAN/66 KV rail pole line Joga ralla to pakho kalan SC on DC | 10103273 | 3814000 | 13917273 | 2018-02-01 | 2019-03-01
69 | 66 kv u/g cable gss abohar to khui khera,33/66 KV Line from 132 KV S/S Abhor to 66 KV S/S Khue Khera line 132 KV Abhor | 28675245 | 10824944 | 39500189 | 2018-06-01 | 2018-08-01
70 | 66 kv u/g cable gss malout to 66 kv new gss malout/132KV S/S Malout to 66 KV New Malout Under APDRP line ckt. U/G.(TL-654) | 8284600 | 3127448 | 11412048 | 2018-07-01 | 2018-08-01
71 | 66kv link line 66kv gss dagru to 66kv daulatpura sc on dc | 7493955 | 2828978 | 10322933 | 2018-05-01 | work in progress
72 | 66kv link line 66kv gss fathegarh kortana to 66kv gss bhinder kalan | 8961385 | 3382935 | 12344320 | 2017-05-01 | work in progress
73 | Jhunir to boha line toff gss tahlian | 11560746 | 4364198 | 15924944 | 2018-05-01 | work in progress
74 | replacement 66kv rpl 132kv badni kalan to bilaspur | 14806598 | 5589511 | 20396109 | 2018-02-01 | 2019-09-01
75 | replacement 66kv rpl 220kv dharamkot to mastian to fatehegarh panjtoor | 11120206 | 4197893 | 15318099 | 2018-05-01 | 2018-10-01
76 | jalal-dayalpur bhaika 66 kv line construction new line | 949900 | 358589 | 1308489 | 2017-05-01 | 2018-06-01
77 | Talwandi sabo to rama | 16911651 | 6384171 | 23295822 | 2016-05-01 | 2017-08-01
78 | Mansa to Kot Dharmu sc on dc tower survey | 9748355 | 3680017 | 13428372 | 2017-02-01 | 2017-05-01
79 | Daulatpura to khosa kotla sc on dc | 8677443 | 3275747 | 11953190 | 2018-05-01 | work in progress
80 | kot karor to dagru survey | 498517 | 188191 | 686708 | 2018-05-01 | work in progress
81 | Mukatsar to Fattanwala | 1479138 | 558377 | 2037515 | 2018-05-01 | 2019-06-01
82 | Stubbing of 66 kv rp line Mansa-Raipur | 989129 | 373397 | 1362526 | 2018-05-01 | 2019-10-01
83 | 66 KV Line from Mudki to Kotakror | 130549 | 49283 | 179832 | 2017-05-01 | 2018-10-01
84 | 66 kv Line (fall in tower) Ferozpur to Chugtewala | 8287 | 3129 | 11416 | 2018-06-01 | 2018-06-01
85 | u/g cable 132 kv gss abohar to 66 kv gss khui khera | 10630238 | 4012930 | 14643168 | 2018-05-01 | 2018-06-01
86 | Sadiq to Jhok tehal singh wala mckt ring main line | 22263 | 8404 | 30667 | 2018-10-01 | work in progress
87 | 66 KV Rail pole line from 220 KV S/S Jhunir to 66 KV S/S Mansa T off | 20497224 | 7737730 | 28234954 | 2018-05-01 | 2019-10-01
88 | Saidpura to lalru lilo 66 kv haripur kurah ring main line proposed route plan | 566455 | 213838 | 780293 | 2019-03-01 | 2019-11-01
89 | 66 KV S/S Fatehgarh kotrana to 66Kv Bhandari kalan | 8347057 | 3151025 | 11498082 | 2018-01-01 | work in progress
90 | Rail pole line Badni to bilaspur Replacement 66 KV SC on DC tower | 8031156 | 3031773 | 11062929 | 2018-02-01 | 2019-09-01
91 | 66 KV Rail pole line from 220 KV S/S Talwandi sabho to 132 KV S/S Mour S | 38444760 | 14512950 | 52957710 | 2017-05-01 | 2018-10-01
92 | Chuhriwala to Dhanna 66 kv | 116765 | 44079 | 160844 | 2018-05-01 | 2019-10-01
93 | Lubhayawali to mukand singh wala 66 kv | 171646 | 64797 | 236443 | 2018-05-01 | 2018-10-01
94 | Rail pole line Malkatora to Chaksherewala replacement of 66 | 188210 | 71049 | 259259 | 2017-05-01 | work in progress
95 | Jhunir to sardulgarh t off to kahnewal 66 kv | 246390 | 93013 | 339403 | 2017-02-01 | 2018-10-01
96 | Nandgarh to sangat 66 kv line | 739925 | 279323 | 1019248 | 2017-05-01 | 2018-06-01
97 | BaHAMNA to Gajewas 66 kv | 174062 | 65708 | 239770 | 2016-07-01 | 2017-02-01
98 | H RPS Eng SANGRUR TO Bhawanigarh | 24084 | 9092 | 33176 |  | W.I.P
99 | ghantyan wali Chhimnewal66 kv | 100200 | 37826 | 138026 | 2016-05-01 | 2017-10-01
100 | Singwa to Kotakpura line 220 kv | 149405 | 56400 | 205805 | 2017-05-01 | work in progress
101 | malerkotla to nihal singh wala | 47226 | 17828 | 65054 |  | W.I.P
102 | 66 kv over head elec. Crossing between BTI MBY railway station Bti hmm | 783307 | 295700 | 1079007 | 2018-06-01 | 2018-06-01
103 | mansa to dharmu | 160856 | 60723 | 221579 | 2018-05-01 | 2019-01-01
104 | mansa to dharmu rpl line repl. | 6115444 | 2308589 | 8424033 | 2018-05-01 | 2019-01-01
105 | malkotra to arniwala | 7658944 | 2891262 | 10550206 | 2017-06-01 | work in progress
106 | 66 kv railpole line from 66 kv g/s/s abohar to amarpur g/s/s hanumaangarh | 726160 | 274126 | 1000286 | 2018-05-01 | 2019-01-01
107 | 66 kv thattha sahib to bhago ke | 937156 | 353778 | 1290934 | 2017-05-01 | 2018-10-01
108 | 66 kv panje ke uttar | 465430 | 175701 | 641131 | 2017-06-01 | 2018-10-01
109 | Dc on Dc 66 kv line from existing Banur-Bhabatt line for 66 kv Ramgarh Bhuda | 738200 | 278671 | 1016871 |  | W.I.P
110 | 66kv Line t-off noore ke | 2901 | 1095 | 3996 | 2017-01-01 | 2018-02-01
111 | 66 KV Rail pole line tower line form 66 KV Chok Tehal singh to 66 KV Mamdod | 4561 | 1722 | 6283 | 2017-05-01 | 2018-02-01
112 | fallen tower 66 kv t-off rana | 71853 | 27125 | 98978 | 2018-02-01 | 2018-02-01
113 | Fallan Tower 66 KV Line Badal to Killianwali | 129263 | 48797 | 178060 | 2018-02-01 | 2018-02-01
114 | 66 KV LINE ARNIWALA-KANDHWALA HAZARKHAN T-OFF FOR MIDDA | 191784 | 72399 | 264183 | 2017-03-01 | 2017-10-01
115 | 66 kv line Jhoke tehil Singh to Mamdot T Off for Rahoke uttar | 81722 | 30850 | 112572 | 2017-12-01 | 2018-05-01
116 | fabrication of rail pole structure for 66 kv s/station abohar city | 67843 | 25611 | 93454 | 2018-06-01 | 2018-06-01
117 | Ajitwal 220 kv to Deodhar 66 kv restroration of 66 kv line | 131900 | 49792 | 181692 | 2018-06-01 | 2018-06-01
118 | Badal220kv to KILLANWALI 66 KV survey of raising/shifting | 22263 | 8404 | 30667 | 2017-04-01 | 2017-06-01
119 | Fraction of fallan tower at rail pole Moga to Kisanpura | 81426 | 30739 | 112165 | 2018-05-01 | 2019-06-01
120 | Fraction of fallan tower at rail pole Smadh Patto to Hira Singh | 89874 | 33927 | 123801 | 2018-05-01 | 2019-06-01
121 | Ganga to Jeeda 66 kv with 0.2 sq sc on dc tower | 564624 | 213146 | 777770 | 2017-02-01 | 2017-12-01
122 | Ramuwala to Chrik 66 kv line | 6842840 | 2583182 | 9426022 |  | WIP
123 | Sunam to Lehragaga from 66 kv to 220kv | 28035 | 10583 | 38618 |  | W.I.P
124 | Pasiana-sanour | 2904301 | 1096377 | 4000678 | 2019-07-01 | 2019-08-01
125 | 66 kv Tower line from MES to Shakati Vihar 2nd ckt | 13396 | 5057 | 18453 |  | WIP
126 | U/G of 33 to 66 kv Amarpura to sito guno line | 350 | 132 | 482 | 2017-05-01 | 2017-08-01
127 | 66 kv line Mallan to 66 kv s/station Kotalli | 152628 | 57617 | 210245 | 2017-06-01 | 2018-05-01
128 | 66 kv line Sadiq to Gurharsai TOff for 66 kv s/station hamad | 67364 | 25430 | 92794 | 2017-05-01 | 2018-10-01
129 | Lehragaga 66kv shifting of Gantries | 229833 | 86762 | 316595 |  | W.I.P
130 | Lalru 66kv line from 220kv to 66kv Haripur | 796334 | 300617 | 1096951 | 2019-03-01 | 2019-11-01
131 | 66 KV LINE ABLOWAL TO THAPAR CAMPUS | 4206522 | 1587968 | 5794490 | 2019-01-01 | 2019-07-01
132 | 220 KV RAJPURA FOCAL POINT RAJPURA | 22129 | 8354 | 30483 |  | WIP
133 | 66 KV KOT DHARMU LINE XLPE U/G CABLE | 69316 | 26167 | 95483 | 2018-06-01 | 2018-06-01
134 | REVISED ESTIMATE FOR 66KV LINE FROM 220KV S/S SANDHWAN TO 66KV S/S FARIDKOT SC ON DC TOWER STRING | 2106135 | 795069 | 2901204 | 2018-05-01 | 2018-12-01
135 | 66 KV SC ON DC TOWER FROM GIS BATHINDA TO 66 KV AIIMS BATHINDA | 1302611 | 491737 | 1794348 | 2019-01-01 | 2019-05-01
136 | 66KV S/S MEHTA TO 66 KV AIIMS BATHINDA LINE STUBBING | 3879273 | 1464431 | 5343704 | 2019-01-01 | 2019-05-01
137 | 220 KV LINE FROM TALWANDI BHAIKA TO DHARMKOT | 33331 | 12582 | 45913 | 2017-02-01 | 2018-10-01
138 | 66 kv rajpura to saran bajra at NH-1 | 882747 | 333238 | 1215985 |  | WIP
139 | 66 kv ferozpur to sande hasham 1 no. fallen tower | 276776 | 104484 | 381260 | 2018-06-01 | 2018-06-01
140 | survey of 66 kv killi nihal singh to 66kv Bhalaiana | 181238 | 68418 | 249656 | 2018-01-01 | 2018-04-01
141 | Lilo 220 KV mour 66KV joga ralla 66KV chowke | 1087256 | 410441 | 1497697 | 2019-05-01 | 2020-02-01
142 | 66KV t-off attari 2nd circuit | 161762 | 61065 | 222827 | 2018-05-01 | 2018-12-01
143 | 66kv line mour to jodhpur pakhar | 57387 | 21664 | 79051 | 2018-02-01 | 2018-10-01
144 | 66kv line mahmad khan to lohgarh | 297288 | 112227 | 409515 | 2018-01-01 | 2018-10-01
| Total Non- REC Works | 377459393 | 142491440 | 519950833
C | Deposit Works
1 | 66kv DC tower line Airport Mohali T-off from 220KV Banur-Ansal (66kv mckt line Khara-Banur line) |  |  | 77315 | 2016-06-01 | 2018-10-01
2 | tc spinners lalru |  |  | 3631808 |  | WIP
3 | 66 KV SC on DC line from 66 KV S/S Focal point Rajpura to 66KV S/S M/s Asian fine cement |  |  | 92652 | 2019-12-01 | 2020-01-01
4 | Shifting of 66KV SC on DC line from 220KV S/S Banur to 66KV S/S Mubarakpur within the plot of Mr. ANIL Kumar Chabra Chandigarh-THIS LINE IS DIFFERENT FROM BANUR-MUBARAKPUR LINE |  |  | 1877263 |  | W.I.P
5 | SURVEY OF NEW CHANDIGARH GAMADA |  |  | 322726 |  | W.I.P
6 | 66 KV BARNALA PAKHOKE RAIL LINE |  |  | 548861 |  | W.I.P
7 | Raising of Badni Bilaspur for roarke kalan/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV S/C on S/C Towers Badni- Blaspur Line) |  |  | 371191 | 2016-11-01 | 2017-12-01
8 | 66 KV HANDAYA TO DHANULA LINE/66 KV D/C Line from 220 KV S/S Handiaya to Mehalkalan & Malwa)/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV D/C Line from 220 KV S/S Handiaya to Mehalkalan & Malwa) |  |  | 422989 | 2016-10-01 | 2017-12-01
9 | 66 KV MK 220 KV HANDIYA TO ARTIINT SPINING TULLIWALA/66KV mckt line from 220KV S/S Handiaya to Arihant Spinning mill &Thuliwaal on NH-71/66 KV DC Handiaya to Dhanaula CKT-1&2 feed on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV Multi Circuit Line from 220 KV Handiaya (S/S) to Arihant Spinning Mill & Thulliwal) (66 KV M/Ckt line from 220 KV Handiaya to Dhanaula - I & II, Thulliwal,Malwa Spinning Mill). |  |  | 988525 | 2016-10-01 | 2017-11-01
10 | 66 KV HANDAYA TO THIKRIWALA LINE PAKHOKE M/CKT LINE/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) 66 KV Handiaya- Thikriwala- Pakhoke Multi Circuit Line) |  |  | 415684 | 2016-10-01 | 2017-11-01
11 | 66 KV BARNALA PAKHOKERAIL LINE AT JODHPUR CHEEMA/Raising of SC/DC line LILO from 66 KV Barnala-Pakhoke line at Jodhpur-Cheema on NH-71 |  |  | 341230 | 2016-10-01 | 2017-05-01
12 | 66 KV HANDAYA TO BARNALA H RAIL LINE/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV Handiaya to Barnala H. Pole Line) |  |  | 331344 | 2016-10-01 | 2017-11-01
13 | 66KV BADNI DODARA LINE/ raising of 66 kv line 12 no. line badni to daoda on nh-71 deposit work of 66 kv line from nh-71 ( barnala to jalandhar NH Road)/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV Badni –Dodar Line) |  |  | 284696 | 2016-10-01 | 2017-12-01
14 | 66kv SC on DC line from 66KV Barnala -Pakhoke on NH-71 |  |  | 294682 | 2016-10-01 | 2017-05-01
15 | 66KV Moga-Badni H-Rail pole line on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (33/66 KV Moga- Badni Line on H. Rail Pole) |  |  | 490282 | 2016-12-01 | 2018-05-01
16 | 66KV Line Pacca Kaleke-Gross Spin deposit work |  |  | 9644 |  | W.I.P
17 | PROPSED ROUTEPLAN FOR LAYING OF U/G CABLE(66KV)AIRPORT LINE TO AIRPORT GANTRY |  |  | 44162 | 2016-06-01 | 2018-10-01
18 | REVISED ROUTE PLAN FOR T.NO 19 TO 22 66KV LINE M/S TC SPINNERS 220KV SS LALRU |  |  | 20454 |  | W.I.P
19 | 66KV HRP line from 220KV BBMB SANGRUR TO PATRAN LINE NEAR VILLAGE DUGGAL ON NH-71/Shifting of 66 KV Rail Pole line from 220 KV BBMB Sangrur to Patran Ckt-2 near village Duggal on NH-71. (Deposit Work) |  |  | 1466349 | 2016-08-01 | 2018-06-01
20 | 66KV Line Pakka kalan -M/s GrospinZ fab. Ltd. |  |  | 570201 |  | W.I.P
21 | Shifting of 66kv 4-railpole kharar to mohali line from 200 ft road/rail pole dismentalment kharar-mohali |  |  | 22017 |  | W.I.P
22 | Deposit Estimate for RAISING OF HRP LINE IN FRONT OF M/S TAJ CITY SUNAM /raising of 66 kv RPL sunam to patran from taj city sunam |  |  | 8766 | 2016-04-01 | 2016-08-01
23 | RAISING OF HRP BBMB SANGRUR TO PATRAN CKT-II BYPASS SANGRUR NH-64 |  |  | 92369 | 2015-11-01 | 2016-03-01
24 | RAISING OF HRP BBMB SANGRUR TO PATRAN CKT-II NH-64 |  |  | 156475 | 2015-11-01 | 2016-03-01
25 | RAISING OF HRP BBMB SANGRUR TO SUNAM BYPASS SANGRUR NH-64 |  |  | 3188241 | 2015-12-01 | 2017-05-01
26 | RAISING OF SANGRUR TO BHAWANIGARH CKT2 DC ON DC (TL-64-75) NH 64 BYPASS SANGRUR |  |  | 43807 | 2015-10-01 | 2016-03-01
27 | RAISING OF SANGRUR TO BHAWANIGARH CKT-I DC ON DC (TL-26-29) NH 64 BYPASS SANGRUR |  |  | 341652 | 2015-10-01 | 2016-03-01
28 | Raising of 66 kv line from 220 kv bbmb sangrur to bhawanigarh ckt-1 from railway track,your office memo no 3378 dt 8/9/16/Raising of existing 66 KV H.R.P. Line from 220 KV BBMB Sangrur to Bhawanigarh Ckt-2 Line in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Section Sangrur-Sunam-Jakhal at Railway KMS 79/2-3 3rd Xing |  |  | 2030 | Work Discarded
29 | raising of 66 kv sc on dc patiala bhadurgarh line bwten tl 178-180 nh 64 |  |  | 76893 |  | W.I.P
30 | SURVEY AND SHIFTING OF BUCHO NATHAN LINE FROM MSD UNIV, BUCHO |  |  | 15938 | 2017-02-01 | 2017-05-01
31 | Raisng of existing 66KV HRP line from 220KV BBMB Sangrur to Patran ckt-1 on NH-64 |  |  | 2367904 | 2016-05-01 | 2017-05-01
32 | SHIFTING OF PATEL NAGAR LINE NEAR BUS STAND BTI |  |  | 2123004 | 2017-05-01 | 2017-10-01
33 | 66KV SC on DC Sunam-Nagra line on NH-71 |  |  | 46277 | 2016-02-01 | 2016-08-01
34 | Proposed route Plan for sc on dc line for photon suryadoya (p) ltd solar plant at village jodhpur pakhar to 66 kv ss jodhpur pakhar SMB 1040 PG |  |  | 52713 | 2017-03-01 | 2017-09-01
35 | 66KV Mckt line from 220KV S/S Majra to 66KV S/S Mullanpur Garibdas fro connection to various 66KV S/S as planned by GMADA i.e. 1. 66KV S/S Medicity 2. 66KV S/S Omaxe city 3. 66KV S/S Eco city in new chandiagrh area |  |  | 172002 |  | W.I.P
36 | Fallen tower on 66KV line Badrukhan-Khillrian line |  |  | 876779 | 2018-01-01 | 2018-01-01
37 | Revised route plan for raising 66 kv dc line from 66 kv ss tapa to 66 kv ss joga due to construction of overhead bridge at nh-64 dw |  |  | 1098008 | 2017-10-01 | 2018-01-01
38 | Proposed route plan for raising / Shifting of 220 kv ss Handiyan to Dhola due to const of overhead bridge at nh 64 dw |  |  | 236946 | 2016-03-01 | 2016-08-01
39 | Proposed route plan for raising / Shifting of 66 kv sc line from dhanoula sanghera of ms trident ltd barnala due to construction of overhead bridge at nh64 dw |  |  | 123050 | 2016-03-01 | 2016-08-01
40 | Survey of 66 kv line from azure power pluto pvt ltd. Village korianwali to gss banwala hamwanta SMB 22 PG 10 |  |  | 21943 | 2017-01-01 | 2017-04-01
41 | Survey of 66 kv line from azure power pluto pvt ltd. Bahadargarh jandian togss tharajwala SMB 22 PG 11 |  |  | 33350 | 2017-01-01 | 2017-04-01
42 | Survey of 66 kv line from azure power pluto pvt ltd. Bahadargarh jandian to gss peori SMB 22 PG 10 |  |  | 20010 | 2017-01-01 | 2017-04-01
43 | survey of shifting of 66 kv line mastewala sekhuwala for nh-15 smb no 23 pg 45 |  |  | 172751 | 2017-03-01 | 2017-06-01
44 | survey of revised route plan of 66 kv line mastewala zira for nh-15 smb no 23 pg 45 |  |  | 203583 | 2017-04-01 | 2017-06-01
45 | Survey of 66 kv line from azure power pluto pvt ltd. Vill Kandu khera to gss bhitiwala SMB 22 PG 11 |  |  | 16008 | 2018-01-01 | 2018-04-01
46 | 66 KV RAJPURA TO SARAI BANJARA at crossing nh-1 of ASR-LDH-Delhi section your office memo no 659 dt 9/16 |  |  | 21211 |  | wip
47 | 66 kv line from 220kv ss RAJPURA TO SARAI BANJARA near railway station at railway km 298/4-6 your office memo no 659 dt 9/16 |  |  | 402591 |  | wip
48 | RAISING/ Shifting of HRP SANGRUR TO PATRAN CKT II NH71 |  |  | 143767 | 2017-01-01 | 2017-05-01
49 | 67 KV SC line from 220 KV Rajpura to 66KV S/S Naushehra at nh-1 of asr-ldh-delhi section your office memo no 659 dt 29/916 |  |  | 21211 |  | W.I.P
50 | 66Kv bottianwala to bhek gujar |  |  | 38954 | 2017-06-01 | 2018-05-01
51 | 66kv bottianwala to sukhewala |  |  | 21900 | 2017-05-01 | 2018-06-01
52 | Shifting/dismantlement of banur lalru sc line near banur nh-64 (est not passed) your office memo no 659 dt 29/916 |  |  | 21211 | 2020-07-01 | WIP
53 | Raising of Dala to Ramuwal from nh-64,your office memo no 3378 dt 8/9/16/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV SC Line Dala-Ramuwala) |  |  | 1578266 | 2019-01-01 | 2019-02-01
54 | Fathegarh to kartora from nh-71,your office memo no 3378 dt 8/9/16/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703)66 KV SC on DC LineT-off for Fatehgarh-Karotana) |  |  | 31148 |  | W.I.P
55 | raising/shiting of 66 kv line pakhoke to sukhpura sc on dc from nh-71,your office memo no 3378 dt 8/9/16/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala |  |  | 1035571 |  | W.I.P
56 | Himmatpura to gehlan from nh 64/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) 66 KV SC on DC Line Himatpura-Gehlan) |  |  | 1600597 | 2016-11-01 | 2017-12-01
57 | Deposit Work of Raising/Shifting of 66 KV SC on DC Line Himatpura- Tallewal on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703)(66 KV SC on DC Line Himatpura- Tallewal) |  |  | 1196186 | 2016-11-01 | 2017-12-01
58 | Fallen tower barnala to dhanoula dc on d,your office memo no 3378 dt 8/9/16c |  |  | 4511 | 2016-06-01 | 2016-06-01
59 | fallen tower sunam-nagra dc on dc,your office memo no 3378 dt 8/9/16 |  |  | 118702 | 2016-06-01 | 2016-06-01
60 | moga to kishanpura for nh-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV SCLine on H-Pole Moga- Kisanpura) |  |  | 1448168 | 2019-01-01 | 2019-02-01
61 | raising/shiting of 66 kv line karial to mohamed khan from nh-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV DC on DC Line from 220 KV Karial to Kot-Mohamdekhan ) |  |  | 63607 | 2019-02-01 | 2019-03-01
62 | raising/shiting of 66 kv line pakhoke to sukhpura sc on dc from nh-71,your office memo no 3378 dt 8/9/16/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) 66 KV SC on SC Line from Pakhoke- Sukhpura) |  |  | 35783 |  | W.I.P
63 | raising/shiting of 66 kv line moga to dala sc on dc from nh-7 |  |  | 2030 | 2019-01-01 | 2019-02-01
64 | ine (Old) in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Himmatana-Dhuri at Railway KMS 59/1-2/Dhuri Katron line raisindg of 66 kv line |  |  | 335386 | 2017-12-01 | 2018-05-01
65 | Shifting of 66 kv line from 220 kv bbmb sangrur to patran ckt-1 from railway track/Raising of existing 66 KV Rail Pole BBMB Sangrur-Patran Line Ckt-1 in connection with electrification work Shifting of 66 kv line from 220 kv bbmb sangrur to patran ckt-1 from railway track/Raising of existing 66 KV Rail Pole BBMB Sangrur-Patran Line Ckt-1 in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Section Sangrur-Sunam-Jakhal at Railway KMS 79/2-3 2nd Xing (Actual name Raising of existing 66 KV Rail Pole BBMB Sangrur-Patran Line Ckt-2) |  |  | 4940609 | 2017-12-01 | 2018-03-01
66 | 66 kv pspcl alamgir to 66 kv ss nishikawa pvt ltd.Lalru,your office memo no:3659 dt 29/9/16 |  |  | 21211 |  | W.I.P
67 | KHARAR BANUR U/G CABLE RAILWAY CASE/Revised route plan for 66 kv mckt kharar ansal line b/w tl 86-80 ryl. Crossing from u/g to o/h line |  |  | 496137 | 2017-03-01 | 2018-11-01
68 | 66 Kv line mastewala Shifting |  |  | 31755 | 2018-05-01 | 2018-12-01
69 | Kharar-Banur line on mckt towers near Pearl City Mohali IWR 50/3 |  |  | 21211 | 2017-03-01 | 2018-11-01
70 | Dc line from 220 kv phase-7 to 66 kv SCL Godrej,passing over industrial plots in phase-7 & 8-B MOHALI on sec diving road IFP phase-7&8 |  |  | 21211 |  | W.I.P
71 | 66KV SC on DC line from 66KV S/S Bamna to T-off point Gajewas-NON RC |  |  | 1598726 | 2016-07-01 | 2017-02-01
72 | Kot karor To Dagru nh 15 |  |  | 6229779 | 2018-06-01 | 2018-08-01
73 | Dona Mattar Crossing Tower satluj river |  |  | 2306622 |  | W.I.P
74 | Shifting of 66KV Rail Pole Line Mansa to Raipur |  |  | 42171 | 2017-05-01 | 2018-09-01
75 | 66KV SC line on H-Pole Moga-Dala on jal-Bar road on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV SC Line on H. pole from Moga to Dala) |  |  | 2785195 | 2019-01-01 | 2019-02-01
76 | 66KV SC on DC line Himatpura-Bilaspur on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703)(66 KV SC on DC Line from Himatpura to Balaspur) |  |  | 272136 | 2017-12-01 | 2018-11-01
77 | LALRU TO ALAMGIR 66 KV LINE FOR M/S TC SPINNERS |  |  | 1246807 |  | WIP
78 | Shifting of 66KV Patran-Kakrala line |  |  | 3702690 |  | W.I.P
79 | 66KV SC on DC line from 66kv s/s Handesra to 66KV S/S M/s Pragati Paper Industry Ltd. Village Handesra, Derabassi |  |  | 5744324 | 2016-11-01 | 2017-06-01
80 | Badni- Blaspur T-off for Roukekalan 66 KVSC Line T-off |  |  | 314708 | 2016-11-01 | 2017-11-01
81 | 66 kvrpl ablowal to patiala line for premises of S. GHUMAN SINGH S/O KIRPAL SINGH OF VILL SIDHUWAL |  |  | 1662767 | 2017-05-01 | 2018-01-01
82 | 66 KV SC ON DC BANUR TO MUBARAKPUR WITHIN THE PREMISES OF M/S CHD ROYALE CITY PROMOTERS PVT LTD |  |  | 20677 |  | WIP
83 | dw raising of 66 kv nabha to samundgarh railway crossing |  |  | 1682 | 2014-10-01 | 2019-05-01
84 | DW RAISING OF 66 KV NH-71 MCKT 220 KV HANDIYA TO BHADOUR |  |  | 9789 | 2016-11-01 | 2017-11-01
85 | kharar to banur |  |  | 8700 | 2017-03-01 | 2018-11-01
86 | t off line from 220 kv sector 80-66 kv ss phase 8-b,t-off sector 88 |  |  | 21211 | 2017-05-01 | 2018-10-01
87 | Proposed route plan for shifting of 66 kv line from 220kv sec 80 to 66 kv gss phase 8b mohali in front of Judicial complex in IFP Ph-8 a mohali(PSIEC DW) |  |  | 16340262 | 2018-04-01 | 2019-09-01
88 | 66 kv dc on dc ring main line 220 kv sunam from 66 kv sunam jakhepal dhuri ryl track/Raising of existing 66 KV from 220 S/S Sunam to 66 KV S/S Sunam in connection with electrification work of Jakhel-Dhuri at Railway KMS 88/8-9 Xing |  |  | 21344 | Work Discarded
89 | 66 kv Route plan from 66 kv line from 220 kv gss mehlan kalan/66 KV Line from 220 KV Mehalkalan till Tower from which 66 KV Lines to Thikriwala Grid and Channanwal Grid are separated and Shifting of Gantries at 220 KV G/S/S Mehalkalan. (P&M Barnala) |  |  | 1608142 | Work Discarded
90 | Const. of damage tl-61 66 kv sc on dc dhanuala Badrukha |  |  | 243192 | 2017-05-01 | 2017-05-01
91 | Dhanoula to Ashpal Kalan Fallen tower |  |  | 296325 | 2019-06-01 | 2019-06-01
92 | 66kv RPL LINE FROM 220 KV GSS FOR BBMB SANGRUR TO DIRBA 2nd ckt at crossing sangrur to sunam road/Raising of 66 KV Rail Pole line from 220 KV G/S/S BBMB Sangrur to Dirba at Crossing of Sangrur-Sunam Road. (P&M Patran) |  |  | 289203 | 2016-06-01 | 2017-07-01
93 | 66 kv rpl from 220 kv sng-patran ckt-2 near vill. Duggal on nh-71 ( for temp) shifting of ladwanjra GSS RAI DHARAI ON SNG.-patran ckt-1/providing 1 no tower for sangrur patran ckt 1&2 sagging |  |  | 1316666 | 2016-06-01 | 2018-06-01
94 | Survey and raising of /Shifting of 66 kv RPL LINE Kotkaror to Dagru from Ludhiana to Talwandi Section of nh-985 from km 156.280 |  |  | 22011 | 2017-10-01 | 2017-11-01
95 | Survey and raising of /Shifting of 66 kv RPL LINE 132kv gss Moga to m/s Nestle Pvt Ltd from Ludhiana to Talwandi Section of nh-95 from km 147 |  |  | 22011 | 2017-10-01 | 2017-12-01
96 | Survey and raising of /Shifting of 66 kv RPL LINE 132 kv gss moga to dalla from ludhiana to talwandi sec of nh-95 from km 143.580 |  |  | 44022 | 2017-10-01 | 2017-12-01
97 | abohar khui sarvar line from plot sh kalu ram survey & staking |  |  | 16008 | 2018-10-01 | 2019-02-01
98 | survey of m/s photon suryaodhaya pvt solar plant vill Kamalu to 66 kv ss kamalu/66 KV Line from Solar Photon Suryodaya Pvt. Ltd. Village Sandhoa to 66 KV G/S/S Kamalu SC/DC Tower Line. |  |  | 34220 | Work isn't started yet.
99 | revised route plan 66 kv handiaya to dhanoula ckt 1 & 2 and 66 kv handiaya to thuliwal line 66 kv malwa spinning mill line |  |  | 4153180 | 2016-12-01 | 2017-11-01
100 | Revised route plan for raising of 66 kv handiya to thikriwal to pakhokhe mckt line |  |  | 3954535 | 2016-12-01 | 2017-11-01
101 | Proposed route plan for 66 kv sc on dc line from 132 kv moga dala hrpl/Regarding Raising of 66 KV Rail Pole Line from 132 KV Moga to Dala on NH-71 |  |  | 2903419 | 2017-12-01 | 2018-11-01
102 | proposed route plan for raising of 33 kv moga to badni kalan line at butter bypass & 2nd crossing hrpl/Regarding Raising of Existing 33 KV Moga-Badni Kalan Line at Butter Bypass Crossing 1&2 on NH-71. |  |  | 4422245 | 2017-12-01 | 2018-11-01
103 | SANGRUR TO PATRAN 2ND CKT NH71 |  |  | 133400
104 | Survey of raising 66kv t/l mukatsar to phullewala |  |  | 22585 | 2018-05-01 | 2018-08-01
105 | survey of ms photon ojas pvt ltd vill toderpur saspali & ramgarh shahpur to 66 kv ss chak alisher |  |  | 85550 | Work isn't started yet.
106 | jalabad guru har sahai toff jeeva |  |  | 13592 | 2018-05-01 | 2018-06-01
107 | Raising of 66 KV H.R.P. Line Sangrur to Sunam Lehra for Electrification work of Northern Railway Xing 79/2-3 4th Xing./Raising of existing 66 KV H.R.P. Line from 220 KV BBMB Sangrur to Sunam-Lehra in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Section Sangrur-Sunam-Jakhal at Railway KMS 79/2-3 4th Xing |  |  | 4531704 | 2017-12-01 | 2018-03-01
108 | 66 KV S/S Handiaya Barnala linedue to ROB at Court Chowk Barnala on NH-71/Regarding Raising of Existing 66 KV S/C Handiaya-Barnala Line due to ROB at Court Chowk Barnala Section-NH-71, |  |  | 4102954 | 2018-01-01 | 2018-06-01
109 | kanoi maghaan paper mill ram nagar sibian sangrur survey |  |  | 73368 |  | W.I.P
110 | Bhadurgarh to Sanour rpl within the premises of gems public school sanour |  |  | 1092138 | 2018-01-01 | 2018-03-01
111 | tower line 66 kv mukatsar to phullewala m/s anand aluminium industries mukatsa sahib survey |  |  | 22585 | 2019-05-01 | 2019-06-01
112 | Vijay Printing Press Pvt ltd. 66 kv Bhathiwal solar plant/M/s Vijay printing Press Pvt. Ltd. Solar PV Power Plant on Canal Top to 66 KV S/S Bhattiwal |  |  | 22744 | 2018-01-01 | 2018-03-01
113 | SANGRUR BBMB TO PATRAN LINE CKT 1/Raising of existing 66 KV Rail Pole line from 220 KV BBMB Sangrur-Patran Ckt-1 in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Section Sangrur-Sunam-Jakhal at Railway KMS 79/2-3 3rd Xing |  |  | 3703425 | 2017-10-01 | 2018-03-01
114 | sec 80 to 80 b mohali revised route survey |  |  | 21764 | 2019-03-01 | 2020-03-01
115 | Kharar mohali line sec 118-119 mohali |  |  | 166305 |  | W.I.P
116 | Pakhoke to sukhpura on nh-71 revised route plan |  |  | 22585 | Work Discarded
117 | Banur to mubarakpur |  |  | 292183 |  | wIP
118 | iiser sec 81 mohali from sec 80/66 KV U/G Cable line from 220 KV S/S Sector-80 to 66 KV S/S IISER Sector-81, Mohali (Permanent Connection) |  |  | 174525 | 2016-05-01 | W.I.P
119 | M/s canal solar energy pvt ltd 66 kv allowal |  |  | 47881 |  | W.I.P
120 | Patran to khanauri / nh-71 |  |  | 126258 | 2015-06-01 | 2015-10-01
121 | sangrur to krbl p tltd from railway crossing/Sangrur to Malerkotla rpl line dw/Raising of existing 66 KV H.R.P. Line from 220 KV BBMB Sangrur to MLK. M/s Oswal K.R.B.L. Line in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Section Sangrur-Sunam-Jakhal at Railway KMS 59/8-9 Xing |  |  | 1415431 | 2017-12-01 | 2018-04-01
122 | RaJpura to Nsushara 66 kv |  |  | 35416 |  | W.I.P
123 | HRP line BBMB SANGRUR TO MALERKOTLA KRBL LINE |  |  | 11400 |  | W.I.P
124 | Sangrur to Patran 220 KV BBMB N.H.71 |  |  | 154466 |  | W.I.P
125 | derabassi to naher spring lalru fallen tower |  |  | 96027 | 2018-05-01 | 2018-05-01
126 | fallen tower 66 kv line lalru to handesar |  |  | 1991799 | 2018-05-01 | 2018-05-01
127 | fallen tower 66 kv dc line from 220 kv s/s derabassi to 66 kv s/s nahar bassi ind. pvt. ltd. |  |  | 399694 |  | W.I.P
128 | Cont. of fallen towers of 66 kv line phase 9 to 66 kv s/s sector 68 Mohali dc on dc line |  |  | 1156179 |  | W.I.P
129 | shifting of 66 kv dc ring main line from 220 kv s/s Phase7 Mohali to 66 kv sec 39 Chandigarh inside the Land of m/s Flaboyant Dev pvt ltd.sec 119 Mohali |  |  | 928037 | 2018-04-01 | Work in Progress
130 | 66 kv ring main line from 220 kvs/s PH7 to 66 kv Chandigarh |  |  | 2948183 |  | W.I.P
131 | Shifting of Ganties at 220 kv s/s Pasiana for 66 kv Ablowal |  |  | 171817 | 2019-10-01 | 2020-01-01
132 | Bhaterhi to Banaur fallan tower |  |  | 1038926 |  | W.I.P
133 | 66 kv sec 80 to ICI paint factory 8B Mohali |  |  | 1581348 | 2018-04-01 | 2019-05-01
134 | Ablowal- passiana 66kv Railway crossing |  |  | 2776770 | 2018-11-01 | 2019-01-01
135 | Dhanoula to Kattu fallen |  |  | 720120 | 2018-06-01 | 2018-06-01
136 | Chugawan-Behniwal fallen tower |  |  | 660079 | 2018-06-01 | 2018-06-01
137 | ADD WORK HANDIYA PAKHOKE-THIKRIWAL M/C ON NH-71 |  |  | 567231 | 2016-12-01 | 2017-11-01
138 | 66KV LINE M/S CANAL SOLAR ENERGY PVT LTD TO 66KV ABLOWAL |  |  | 22448 |  | W.I.P
139 | 66kv ABLOWAL, PATIALA RAIL POLE LINE RVNL DEPOSIT WORK |  |  | 990770 | 2018-11-01 | 2019-01-01
140 | 66KV BARAN BAHADURGARH/DEVIGARH LINE RAIL POLE RVNL DEPOSIT |  |  | 2054026 | 2015-10-01 | 2016-02-01
141 | 66KV OLD RAJPURA-FOCAL POINT R |  |  | 21764 |  | W.I.P
142 | 66KV ABLOWAL PATIALA RAIL POLE LINE |  |  | 1245194 | 2018-11-01 | 2019-01-01
143 | 66 kv sc on dc tower from gis bathinda to 66 kv aiims bathinda line |  |  | 4162002 | 2019-01-01 | 2019-05-01
144 | 66 kv mehta to aiims |  |  | 5360133 | 2019-01-01 | 2019-05-01
145 | survey of 66 kv line peejay promotors phase 4-5 |  |  | 16426 | 2018-10-01 | 2018-12-01
146 | fallen tower 66kv line ghubaiya ladhuka t-off s/stn Rana |  |  | 116284 | 2018-02-01 | 2018-02-01
147 | malout to new malout sc on dc line survey and staking |  |  | 123063 | 2018-01-01 | 2018-04-01
148 | 66 kv fall in tower ferozpur to chugtewala line |  |  | 389179 | 2018-05-01 | 2018-05-01
| Total Of Deposit Works |  |  | 145232035
| REC | 49342938 | 18627027 | 67969965
| Non-REC | 377459393 | 142491440 | 519950833
| Deposit Work | 145232035 | 0 | 145232035
| TOTAL | 572034366 | 161118467 | 733152833

## 2019-20
AO /TL Patiala for FY 2019-20
sr no | description | amt | A&R INTREST | DATE OF START | DATE OF COMPLETION
A | REC Works
1 | 66KV Line phool Jethu ke T-off Gill Kalan - 7940 | 20964 | 5505 | 2018-04-01 | 2018-11-01
2 | 66 kv line 220 kv passiana to 66 kv gajju majra 3719 | 546441 | 143483 | 2015-11-01 | 2019-01-01
3 | providing 2no CKT FOR SUNAM TO SERON LINE SC ON DC | 438218 | 115066 | 2016-12-01 | 2018-03-01
4 | Replacement of 66 KV Rail Pole Line from 220 KV G/S/S Patran to 66 KV G/S/S Dirba with DC/DC Ringmain Type Towers 10291 | 17638947 | 4631586 | 2016-04-01 | 2020-05-01
5 | STR. AND SAGGING OF OF 66 KV LINE FROM FEROZ SHAH TO MALLANWALA 10290 | 114932 | 30179 | 2017-02-01 | 2018-08-01
6 | 66KV Line Mastewala toZira | 35303 | 9270 | 2010-05-01 | 2020-08-01
7 | 66KV line from 220KV S/S Bhateri to 66KV S/S Ghanour 2nd ckt | 389004 | 102144 |  | WIP
8 | JOGA RAM THIRATH G/S/S TO NANGLA JARKIAN G/S/S (SURVEY AND RECO.) | 169425 | 44487 | 2016-06-01 | 2016-12-01
9 | 66KV S/S JAGARAM TIRATH T 66 KV NANGAL JORDIAN SC ON DC STRINGING | 230503 | 60525 | 2017-03-01 | w.i.p
10 | 66KV LINE BANGA TO MANDVI ON 2ND CKT | 3787 | 994 | 2017-05-01 | 2019-04-01
11 | 66 kv handiaya -Barnala | 791113 | 207728 |  | WIP
12 | 66 KV S/C Line D/C Towers from Nagla Jorekian | 282041 | 74058 | 2017-04-01 | 2018-08-01
13 | 66 KV Line from 66 KV GSS Nangla Jurkian to 66 KV GSS Kahnewala | 111975 | 29402 | 2017-04-01 | 2018-08-01
14 | Shifting of Gantries at 220 KV S/S Bangan for commissioning of 2nd ckt 66 KV Bangan- Mandvi | 162102 | 42564 | 2019-04-01 | 2019-08-01
15 | 66 KV SC line Badal to Killian wali line | 1184239 | 310954 | 2018-08-01 | 2018-09-01
16 | 66 KV Bhateri to Ghanour line | 3836675 | 1007424 |  | WIP
17 | 66 KV Pasiana to Gajju Majra | 565805 | 148568 | 2015-11-01 | 2019-01-01
18 | Shifting of Gantries at 220 KV S/S Grid S/S Sunam ( exp. to be booked to 2nd Ckt. Sunam Sheron) | 514593 | 135120 | 2019-05-01 | 2020-03-01
19 | 220 KV G/S/S Handiaya to 66 KV G/S/S Barnala | 2163447 | 568072 |  | WIP
20 | Re-oreantation of bays for 66 KV line from Jalal-Dayalpura Bhaika & 66 KV line from Jalal to Dayalpur Mirja | 402141 | 105593 | 2018-11-01 | 2018-11-01
21 | 66 KV Line from 220 KV GSS Mastewala to 66 KV GSS Gulari | 133535 | 35063 | 2017-05-01 | 2018-01-01
22 | Malout to arniwala | 3664 | 962 | 2018-05-01 | 2018-11-01
23 | 66 KV line from malout-Arniwala line to avoid the crossing | 3664 | 962 | 2018-04-01 | 2018-10-01
24 | Rail pole line with newly errected DC Malout-Arniwala line | 3664 | 962 | 2018-05-01 | 2018-11-01
25 | 66 KV S/S Ratta Tibba with newly errected DC Malout-Arniwala line | 1833 | 481 | 2018-06-01 | 2019-01-01
26 | 66 KV S/S Midha with newly errected DC Malout-Arniwala line | 1833 | 481 | 2018-05-01 | 2018-12-01
27 | 66 KB Badal Lambi Circuit | 29953 | 7865 | 2018-01-01 | w.i.p
28 | 66 KV Nangal Jordkian stubbing | 1185271 | 311225 | 2017-04-01 | 2018-08-01
29 | Shifting of gantries at 66 KV S/S Phool Jethuke 2nd Ckt | 234711 | 61630 | 2019-11-01 | 2019-11-01
30 | 220 KV S/S Passiana to Gaju Majra | 39604 | 10399 | 2015-11-01 | 2019-01-01
31 | 220 KV S/S Passiana to Gaju Majra | 600656 | 157719 | 2015-11-01 | 2019-01-01
32 | Shifting of 220 KV to 66 KV Sunam to Shero | 16332 | 4288 |  | WIP
33 | 66 KV Patran to Dirba | 20366782 | 5347854 | 2016-02-01 | 2020-05-01
34 | 66 KV Line from 220 KV Handiaya to Barnala | 298152 | 78288 |  | WIP
| Total REC Works | 52521309 | 13790901
B | Non-REC Works
1 | 66 KV Line Bajakhanna to Bargari | 1515 | 398 | 2019-11-01 | 2019-12-01
2 | 66KV Line Railway Xing Mansa-Raipur | 2896 | 760 | 2016-08-01 | 2016-09-01
3 | 66 KV line Lakhewali to Khrnuj | 4179 | 1097 | 2017-10-01 | 2018-10-01
4 | 66 KV Line T-Off Sanauri Adda fromSanur line | 4573 | 1201 |  | W.I.P.
5 | abohar to khui khera t-off for churiwala dhanna | 7272 | 1909 | 2017-09-01 | 2019-06-01
6 | 66 KV G/S/S Jethuke to 66 KV G/S/S jyond SC/DC Line | 8969 | 2355 | 2018-04-01 | 2018-06-01
7 | 66 KV Jhanduke to Gaso Khanna | 9168 | 2407 |  | WIP
8 | Daulatpura to Khora kotta/khosa kotla sc on dc | 9486 | 2491 | 2017-03-01 | w.i.p
9 | 66 KV Firojshah- Mallawala line | 9495 | 2493 | 2017-02-01 | 2018-08-01
10 | 66 KV Fallen Tower Sandhe Hasim | 10034 | 2635 | 2019-06-01 | 2019-06-01
11 | 66kv link line 66kv gss dagru to 66kv daulatpura sc on dc | 10535 | 2766 | 2017-03-01 | w.i.p
12 | 66 kv line Gahttian Wala- Chimniwal | 11138 | 2925 | 2017-02-01 | 2019-06-01
13 | 66 KV Khrunj to Chak Janisar | 13255 | 3480 | 2017-02-01 | 2018-12-01
14 | 66 KV T-Off line Chudiwala dhanna | 13331 | 3500 | 2017-09-01 | 2019-06-01
15 | Rearrangement of 66 KV Line Bhaghapurana to Samalsar | 14039 | 3686 | 2018-06-01 | 2018-07-01
16 | 66KV G/S/S Dhan Singh Khana to 66 KV G/S/S Ghasso khana SC on DC for tower | 14551 | 3821 | 2018-05-01 | w.i.p
17 | 66 KV Jodhpur pakhar link for 220 KV Talwandi Sabo | 14558 | 3823 | 2018-05-01 | 2018-09-01
18 | Revised 66 KV Line Roharjagir T-Off Devigarh | 15039 | 3949 | 2019-07-01 | 2019-09-01
19 | 66 KV Lakhwali Khunj | 15757 | 4137 | 2017-06-01 | 2018-11-01
20 | 66 KV Line PH 9 66 S/S Sec 68, Mohali | 15901 | 4175 | 2018-05-01 | 2018-05-01
21 | 66 KV Line from Mudki to Kotakror | 16429 | 4314 | 2018-02-01 | 2018-07-01
22 | 66 kv sandhwa faridkot | 16707 | 4387 | 2019-05-01 | 2019-10-01
23 | 66KV Line Malkotra Check Shere wala -10290 | 18148 | 4765 | 2017-06-01 | w.i.p
24 | 66 KV Handiaya to Thikriwal for New Kala Mehar | 20964 | 5505 |  | Work isn't started yet
25 | 66 KV Line from 220 KV S/S Saidpur-Lalru | 21098 | 5540 | 2019-03-01 | 2019-11-01
26 | Survey 66 KV PO from 66 KV Airport to New IT City, Sector 82A | 21553 | 5659 | 2020-01-01 | 2020-02-01
27 | 66 KV SC on DC Line Dhanola aspaal Kalan | 22477 | 5902 | 2019-06-01 | 2019-06-01
28 | 66KV Line Humbra to Adda Dakha | 22566 | 5925 |  | W.I.P.
29 | 66 KV Baja Khana Bargari | 25044 | 6576 | 2016-06-01 | 2019-03-01
30 | 66 KV T-Off Patran to Shergarh (Khanauri, T-Off for new 66 KV G/S/S Matoli | 25119 | 6596 |  | Work isn't started yet
31 |  | 26769 | 7029 |  | W.I.P.
32 | Badni- Blaspur T-off for Roukekalan 66 KVSC Line T-off | 27003 | 7090 | 2016-11-01 | 2017-12-01
33 | 66 KV Fallan Tower Rana and sande hasham | 27278 | 7163 |  | W.I.P.
34 | Humbra to adda dakkha | 31323 | 8225 | 2017-09-01 | w.i.p
35 | 66 KV Line from 220 KV Sec 80 to 8 B Mohali | 31423 | 8251 | 2018-04-01 | 2019-05-01
36 | 66 kv t off line jiwan Aral to be link with new tower line./66 Kv line ghubaya guru har sahai jeewa arian | 31693 | 8322 | 2017-06-01 | 2018-05-01
37 | 66 KV Banga Moonak | 33330 | 8752 | 2018-11-01 | 2018-12-01
38 | malout sangat line | 34107 | 8956 | 2014-10-01 | 2020-06-01
39 | 66 kv ferozpur to sande hasham 1 no. fallen tower | 40862 | 10729 | 2018-06-01 | 2018-06-01
40 | 66 KV Ferozeshah to Mallanwala T off Shudh Singh Wala | 45725 | 12006 | 2018-11-01 | 2019-05-01
41 | 66 KV Line Bargari | 46939 | 12325 | 2019-11-01 | 2019-12-01
42 | ferozshah to mallanwala line for 66 kv gss sudh singh wala | 48933 | 12849 | 2018-11-01 | 2019-05-01
43 | 66 KV Firojshah- Mallawala T-Off Sudh Singh Wala | 49448 | 12984 | 2018-11-01 | 2019-05-01
44 | 66 KV Kotkapura-Faridkot | 55410 | 14549 | 2017-02-01 | w.i.p
45 | 66 kv u/g cable gss abohar to khui khera,33/66 KV Line from 132 KV S/S Abhor to 66 KV S/S Khue Khera line 132 KV Abhor | 67903 | 17830 |  | W.I.P.
46 | REVISED ESTIMATE FOR 66KV LINE FROM 220KV S/S SANDHWAN TO 66KV S/S FARIDKOT SC ON DC TOWER STRING | 68219 | 17913 | 2019-05-01 | 2019-10-01
47 | 66 KV line from Mansa to Raipur T-Off S/S Moosa | 68589 | 18010 | 2018-06-01 | 2020-02-01
48 | Survey 66 KV lilo line from 220 KV S/S Bhateri to Devigarh Narru | 69980 | 18375 | 2019-07-01 | 2019-09-01
49 | 66 KV SAC 9997 Survey for M/S Sukhbir Agro LTD | 70970 | 18635 | 2019-03-01 | 2019-06-01
50 | 66 KV Line Dharamgarh to Ghanour | 72556 | 19052 |  | WIP
51 | 66KV Line Malout road-Dabwali road same as 344 | 74043 | 19442 | 2014-05-01 | w.i.p
52 | Bajakhana Bargari | 74659 | 19604 | 2016-06-01 | 2019-03-01
53 | 66 KV line Malkatora to Madhir | 75181 | 19741 | 2016-03-01 | 2020-06-01
54 | 66 KV Sadiq Jhok Tehal Singh T-Off for Sangrahoor line | 79066 | 20761 | not started yet
55 | Dc on Dc 66 kv line from existing Banur-Bhabatt line for 66 kv Ramgarh Bhuda | 85283 | 22393 | 2020-07-01 | w.i.p
56 | M/Ckt line Khard- Banur line | 85490 | 22448 | 2016-04-01 | 2018-11-01
57 | Survey 66 KV GSS Mallan, AIIMS Bathinda | 87365 | 22940 | 2019-01-01 | 2019-04-01
58 | 2nd Ckt. Patel Nagar, Bathinda | 93623 | 24583 | 2018-01-01 | 2018-03-01
59 | Shfting of Gantries at 66 KV S/S Bahadurgarh | 94000 | 24682 | 2019-10-01 | 2020-01-01
60 | 66 KV Line Bhunerheri from Bhateri-Devigarh LIne | 96847 | 25430 | 2019-07-01 | 2019-09-01
61 | 66 KV Abohar-Khuhikhera T-off cHudi wala dhanna line | 97043 | 25481 |  | W.I.P.
62 | 66 KV Line LILO from 220 KV Saidpura to 66 KV Saidpura to 66 KV Haripur Kura | 101532 | 26660 | 2019-03-01 | 2019-11-01
63 | Stringing & sagging of 2nd Ckt from Jhok to Tehal Singh Mandot upto T-Off Rao ke Uttar | 106949 | 28082 |  | W.I.P.
64 | Lilo at 66 KV Haripurkura 66KV GSS Kishanpura | 110014 | 28887 |  | W.I.P.
65 | 66 KV LILO T-Off Bhateri-Devigarh to Bhankhar | 111482 | 29273 |  | WIP
66 | Restoration of supply of 66 KV line Jhandewala line | 115089 | 30220 |  | W.I.P.
67 | Survey 66 KV Jhandu ke to 66 KV Ghaso Khana line | 115936 | 30442 |  | WIP
68 | 66 KV Jhuneer-Boha 2nd CKT | 118518 | 31120 |  | W.I.P.
69 | 66 KV Line Banur to Mubarkpur | 119742 | 31442 |  | WIP
70 | Shifting of 66 KV rail pole line Mansa to Raipur | 120015 | 31513 |  | W.I.P.
71 | 66KV Line Abhor Khui Khere- T off Churiwala Dhana | 124613 | 32721 | 2017-09-01 | 2019-06-01
72 | 66KV Line Mour to Rampura STUBBING | 125543 | 32965 | 2014-05-01 | 2018-11-01
73 | 66 KV SC on DC From Karounda to Banarsi | 126504 | 33217 |  | Work isn't started yet.
74 | 66 KV D/C line from 220 KV S/s Lalru to 66 KV S/s Alamgir | 127190 | 33397 |  | WIP
75 | Bajakhana to 66 KV Bargari line | 132829 | 34878 | 2016-06-01 | 2019-03-01
76 | Fallen Tower 66KV Chak Sherrawala 66 KV Lakhowali66 KV Bhagsar khurunj and Chakjanisarfrom 220 KV Malkatora | 134055 | 35200 | 2019-04-01 | 2019-04-01
77 | LILO OF 66 KV BARAN BHADURGARH LINE AT SANOUR/inspection fee for devigarh to bhadurgarh line d/c lilo for sanour dc on dc | 136026 | 35717 | 2018-07-01 | 2019-04-01
78 | Restoration of supply of 66 KV line Jhoke Harihar | 137713 | 36160 | 2019-04-01 | 2019-04-01
79 | 66 KV Line from 220 KV Patran to Shergar | 153454 | 40294 |  | Work isn't started yet.
80 | NANGLA JARKIAN 66 KV GSS TO KANEWAL 66 KV GSS jv no2/Revised Survey of 66 kv ss Nagla-Jaurkian to 66Kv SS Kahnewal | 155991 | 40960 | 2016-01-01 | 2018-05-01
81 | 66 KV T-Off Line Bhateri to old Rajpura line | 156758 | 41161 |  | WIP
82 | 220 KV S/S Dhanola to Ashpal Kalan | 157216 | 41281 | 2019-06-01 | 2019-06-01
83 | 66 KV Line T-Off Roshanpura from Roharjagir line | 164832 | 43281 | 2019-04-01 | 2020-02-01
84 | 66 KV Devigarh-Rohar jagir line DC/DC | 175769 | 46153 | 2019-04-01 | 2020-03-01
85 | 66 KV SC on DC Line Hero Kalan to Cheema | 176046 | 46226 |  | Work isn't started yet.
86 | 66 KV Line Passiana Sanour | 187911 | 49341 |  | WIP
87 | 66 KV Double CKT o/h crossing railway track between mast no. 5/8 & 5/9 b/w bti & behman diwana ryl station on BTI-SNG ryl section.( way leave & supervision charges)//66 kv dc on dc malout bti dabwali road iwr 917/u/g cable line b/w BTTI-Gahribhagi railway station of SSA-BTI sector | 199143 | 52290 | 2018-05-01 | 2018-05-01
88 | 66 KV Zanduke to Ghasso Khanna | 210051 | 55155 |  | WIP
89 | 66 KV Jhunir-Boha T-off for 66 KV Daanewala | 217573 | 57130 |  | W.I.P.
90 | 66KV Line Bhucho-Nathana -9295 | 228384 | 59968 | 2017-10-01 | 2018-06-01
91 | survey of 66 kv line talwandi sabo to maur line | 228956 | 60119 | 2017-06-01 | 2017-09-01
92 | 66 KV Kapial to Bhattiwala | 230977 | 60649 |  | WIP
93 | 66 KV Line Kapial to Bhattiwal | 232047 | 60930 |  | WIP
94 | Additional work 66 KV S/S Tapa shifting mode from 66 KV G/S/S Pakhoke to 66 KV Tapa for existing joga ralla pakhoke rail pole line | 237802 | 62441 |  | W.I.P.
95 | BADNI TO BILASPUR | 244119 | 64100 | 2018-03-01 | 2019-09-01
96 | 66 KV Malout Road Sangat Pathrab 66 KV Pakka line | 262736 | 68988 | 2019-01-01 | 2019-03-01
97 | Ajitwal 220 kv to Deodhar 66 kv restroration of 66 kv line | 265490 | 69712 |  | W.I.P.
98 | Abohar-Khui khera T off churiwala dhanna | 267151 | 70148 | 2017-09-01 | 2019-06-01
99 | 66KV Line baja Khana to Bagrarhi | 269122 | 70665 | 2016-06-01 | 2019-03-01
100 | survey of replacement of rpl abohar to khui sarvar | 275250 | 72274 | 2018-05-01 | 2018-06-01
101 | 220 kv ss malout ( mlerkotla) to gilzewala sc on dc with 02 squr sr no 112 | 283469 | 74433 | 2015-07-01 | 2016-05-01
102 | 66 KV T-Off Line Bhasmre from Devigarh-Roharjagir | 289962 | 76137 |  | WIP
103 | 66 KV BajaKhana-Jeedaline for construction Ganga | 309801 | 81347 | 2019-01-01 | 2019-05-01
104 | Jhunir to boha line toff gss tahlian | 311927 | 81905 | 2019-05-01 | w.i.p
105 | 66 kv rajpura to saran bajra at NH-1 | 328012 | 86128 |  | WIP
106 | 66 KV Line Liehragagga-Khandebaad | 333347 | 87529 |  | WIP
107 | 66 KV LILO T-Off Bhateri-Devigarh to Bhankhar | 338725 | 88941 |  | WIP
108 | 66 KV DC on DC Line from Devigarh-Roharjagir | 344602 | 90485 | 2019-04-01 | 2020-03-01
109 | 66 KV Malout Road Sangat T-Off Nandgarh | 359417 | 94375 | 2014-05-01 | 2020-06-01
110 | 66KV Line Ghubaya-Fattanwala upto Jallabad T off for Chak janisar | 363000 | 95316 | 2017-05-01 | 2018-10-01
111 | 66 KV Roshanpura Line | 385988 | 101352 | 2019-04-01 | 2020-02-01
112 | 66 KV DC on DC Malout Road Bathinda for connecting overhead Rly Crossing ATI-Bikaner at BTI on multy circuit | 389844 | 102364 | 2019-05-01 | 2019-05-01
113 | 66 KV Malout road Sangat line | 390509 | 102539 | 2019-05-01 | 2019-06-01
114 | 66 KV Ferozepur Sande Hasham line after fallen tower | 416504 | 109364 | 2019-05-01 | 2019-05-01
115 | 66 KV Malkatora Madhir. Fallen Tower | 417920 | 109736 | 2019-02-01 | 2019-02-01
116 | 66 KV Lehragagga to Khandebaad | 423057 | 111085 |  | WIP
117 | 66 KV Line Lohakhera to Longowal | 425744 | 111791 |  | WIP
118 | Fallan Tower 66 KV Line Badal to Killianwali | 432843 | 113655 | 2018-12-01 | 2018-12-01
119 | Mansa to Kot Dharmu sc on dc tower survey | 441634 | 115963 | 2017-05-01 | 2017-06-01
120 | Restoration of supply for 66 KV line T-Off Dina Sahib Dayal- pura Bhaika line | 490806 | 128874 | 2019-05-01 | 2019-05-01
121 | 66 KV Line Malkatora to Madhir | 498670 | 130939 | 2016-03-01 | 2020-06-01
122 | 66 KV Line Passiana Sanour | 510995 | 134176 |  | WIP
123 | 66 KV Link line in the vicinity of ICI Paint Factory between 220 KV S/S Ph-7, 66 KV S/S Phase 8 B and 220 KV S/S Sector 80 Mohali | 530676 | 139343 | 2018-04-01 | 2019-05-01
124 | Pasiana-sanour survey and prepration of rev route plan | 532924 | 139934 | 2019-07-01 | 2019-08-01
125 | 220 KV S/S Sec.80 to 81, Mohali U/G Cable | 535208 | 140533 | 2019-04-01 | 2020-03-01
126 | 66KV Line Anaj Mandi Mansa/66 KV MANSA-KOT DHARMU LINE T-OFF FOR ANAJ MANDI MANSA | 544365 | 142938 | 2018-01-01 | 2018-06-01
127 | 66 KV Fallen Tower Ph-9 to 66 KV Mohali | 551248 | 144745 |  | W.I.P.
128 | 66 KV Bajakhana-Bargari line | 553588 | 145360 | 2019-11-01 | 2019-12-01
129 | Stubbing of 66 kv rp line Mansa-Raipur | 584003 | 153346 | 2018-06-01 | 2020-02-01
130 | Mukatsar to Fattanwala | 584155 | 153386 | 2019-08-01 | w.i.p
131 | 66 KV Line Boha Jhunir T-Off KV S/S Taliya | 600346 | 157637 | 2019-05-01 | w.i.p
132 | 66 KV Ladd Banjara Kalan SC on DC to KV Patran | 601333 | 157896 | 2013-11-01 | 2014-06-01
133 | 66 KV Line Shifting Gantries Badal to Nandgarh | 606543 | 159264 | 2019-06-01 | 2019-06-01
134 | 66 KV Rail pole line from 220 KV S/S Jhunir to 66 KV S/S Mansa T off | 607992 | 159645 | 2018-06-01 | 2020-02-01
135 | SODEWALA TO CHUGTEWALA(66 kv zira gate to chugatewala) | 617405 | 162117 | 2015-01-01 | 2016-05-01
136 | 66 KV Line under ground cable Naushera due to fire | 632478 | 166074 |  | W.I.P.
137 | 66 KV SC Line DC Tower from Pathrala to Killwali line stringing and sagging | 644449 | 169218 | 2019-05-01 | 2019-11-01
138 | sc/dc tower 66 kv mandhir line | 661981 | 173821 | 2016-03-01 | 2020-06-01
139 | Shifting of Gantries at 66 KV S/S Phool Jethuke 2nd Ckt (Exp. to be booked to 66 KV Ringmain Tower line GHTP To Phool | 678968 | 178282 | 2019-11-01 | 2020-02-01
140 | 66 KV Maur Jogaralla Lilo for chaowke | 714188 | 187530 | 2019-01-01 | 2020-01-01
141 | HANDIYA TO TAPPA STR.& SAGGING | 730449 | 191799 |  | WIP
142 | Restoration of supply for 66 KV Ferozepur Sande Hasham line due to Thunder storm | 731536 | 192085 |  | W.I.P.
143 | 66 KV S/S Cheema to Herokala | 738157 | 193823 |  | Work isn't started yet.
144 | 66 KV Line Rauwala to Charik | 740663 | 194481 |  | WIP
145 | 66 KV Line Roshanpur T-Off Devigarh Roharjagir | 765263 | 200941 | 2019-04-01 | 2020-02-01
146 | Fallen Towers of SC Line from Raipur to Nangla | 766524 | 201272 | 2019-06-01 | 2019-06-01
147 | 66 KV from 220 KV S/S Focal Point Nabha- 66 KV S/s Samundgarh Line | 769182 | 201970 | 2016-05-01 | 2019-05-01
148 | Restoration of fallen Tower of SC on DC Sadiq to Golewala | 769677 | 202100 | 2019-06-01 | 2019-06-01
149 | 66 KV GSS Loha Khera to Longowal | 774451 | 203353 |  | WIP
150 | 66 KV LIne Devigarh to Roharjagir | 777273 | 204094 | 2019-04-01 | 2020-03-01
151 | 66 KV Railpole line from GSS Bottianwala | 783026 | 205605 | 2015-02-01 | 2016-04-01
152 | 220 KV LINE FROM TALWANDI BHAIKA TO DHARMKOT | 789668 | 207349 |  | W.I.P.
153 | Survey of replacement 66 kv rpl 66 kv gss jhok tehal singh to 66kv gss guru har sahai | 826210 | 216944 | 2019-05-01 | 2019-07-01
154 | Revised estimate of 66 KV LIne Lalru to Alamgir | 839533 | 220442 |  | WIP
155 | HRP line with s/c on d/c Rajpura Sarai Banjar | 839594 | 220458 | 2015-09-01 | 2017-09-01
156 | 66 KV Jogga Ralla Pakho Kalan | 891139 | 233993 | 2018-02-01 | 2019-03-01
157 | Shifting 66 KV Sangat Mehta from ncms | 919754 | 241506 | 2018-06-01 | 2018-06-01
158 | Revised estimate for stubbing of 66 KV Pathrala-killian wali line | 923813 | 242572 | 2019-07-01 | 2019-11-01
159 | 66 KV line Janduke to Ghaso Khanna | 956615 | 251185 |  | WIP
160 | Estimate for 66 KV SC on DC ckt from Killi Nihal Singh Bhlaiana line tower stubbing and stringing | 961927 | 252580 | 2019-12-01 | w.i.p
161 | 66 KV Line from 220 KV S/S Lalru to Haripurkura | 966794 | 253858 |  | W.I.P.
162 | 66kv link line 66kv gss fathegarh kortana to 66kv gss bhinder kalan | 989651 | 259860 | 2019-06-01 | w.i.p
163 | Restoration of supply for 66 KV Sadiq to Sukhanwala line due to Thunder storm | 1017494 | 267171 | 2019-06-01 | 2019-06-01
164 | Survey of 66 kv Dharamgarh to 66 KV Ghanour SC on DC | 1028404 | 270035 |  | W.I.P.
165 | Erection of fallen towers of 66 KV Fatta kera killianwali line | 1060402 | 278437 | 2019-03-01 | 2019-03-01
166 | Restoration of supply for 66 KV Fattanwala Jhariwala fallen towers | 1100549 | 288979 | 2019-03-01 | 2019-03-01
167 | 66 KV Line Ablowal to Thapar University Patiala | 1104731 | 290077 | 2019-01-01 | 2019-10-01
168 | Restoration of supply for 66 KV line T-Off for Chak Janisar | 1115085 | 292796 | 2019-03-01 | 2019-03-01
169 | Installation and commissiong of damaged 66 KV U/G cable near Railway crossing 66 KV line from Rajpura to 66 KV Naushera | 1134467 | 297885 |  | WIP
170 | 66 KV Rail pole line from 220 KV S/S Talwandi sabho to 132 KV S/S Mour S | 1149802 | 301912 | 2018-04-01 | w.i.p
171 | 66 KV rail pole line 220 KV focal point Nabha-Samundgrah | 1326737 | 348371 | 2016-05-01 | 2019-05-01
172 | Estimate for 66 KV Single Ckt line DC Ckt tower from 132 KV S/S IGC Bathinda to kot Shamir line stub | 1361302 | 357447 | 2019-07-01 | w.i.p
174 | 66 KV Line 220 KV S/S Passiana to Sanur | 1479624 | 388516 |  | WIP
175 | 66 KV Line Bhunarheri lilo from Bhateri-Devigarh | 1549799 | 406942 |  | WIP
176 | Rail pole line Badni to bilaspur Replacement 66 KV SC on DC tower same as | 1597639 | 419504 | 2018-02-01 | 2019-09-01
177 | Revised estimate 220 KV Abohar to 66 KV Amarpura T-Off hunmangarh | 1600096 | 420149 | 2018-11-01 | 2018-12-01
178 | Survey of replacement 66kv rpl 132kv badni kalan to bilaspur | 1614925 | 424043 | 2018-02-01 | 2019-09-01
179 | 66 KV Dhuri to Rangia | 1675666 | 439992 | 2017-01-01 | 2018-11-01
180 | Talwandi sabo to rama | 1768896 | 464472 | 2018-07-01 | w.i.p
181 | 66 KV GhasoKhana to Dhan singh Khana stubing | 1780845 | 467609 | 2018-11-01 | w.i.p
182 | 66 KV Line Kapial to Bhattiwal | 1819193 | 477679 |  | WIP
183 | 66 KV Abohar-Amarpura Line | 1835825 | 482046 | 2018-11-01 | 2018-12-01
184 | MALKOTRA TO MADHIR | 2041890 | 536154 | 2016-03-01 | 2020-06-01
185 | 66 KV LINE ABLOWAL TO THAPAR CAMPUS | 2073954 | 544573 | 2019-01-01 | 2019-07-01
186 | 66KV Line Kotkapura-Sandwa | 2295883 | 602847 | 2018-01-01 | w.i.p
187 | SURVEY OF BANWALA TO HANWANTA to gss khui khera | 2343917 | 615459 | 2019-04-01 | 2019-06-01
188 | Ramuwala to Chrik 66 kv line | 2382436 | 625573 |  | WIP
189 | 220 KV S/S Abohar to 66 KV Khuia sarwar SC on DC | 2410399 | 632916 | 2019-05-01 | w.i.p
190 | Line crossing TL-24 TL-25 220 KV S/S Sec80 to 66 KV 80 D, Mohali | 2764188 | 725813 |  | W.I.P.
191 | 2 CKT 66 KV line Mubarkpur to Dhakoli line | 2800993 | 735477 | 2019-10-01 | 2020-06-01
192 | 66kv line mour to jodhpur pakhar | 3002171 | 788302 | 2019-01-01 | 2019-04-01
193 | Stolen & Damaged Material of 66 KV line from 220 KV Sec80 to 88 Mohali | 3458600 | 908150 | 2019-04-01 | 2020-03-01
194 | 132KV S/S Sh Muktsar Sahib to 66KV Fattanwala | 3509189 | 921433 | 2019-06-01 | w.i.p
195 | 66 KV Line LILO from 220 KV Saidpura to 66 KV Saidpura to 66 KV Haripur Kura | 3900689 | 1024232 | 2019-03-01 | 2019-11-01
196 | 66kV Line Bhasmara T-Off Devigarh | 4040668 | 1060987 |  | WIP
197 | matti to gurthari | 5205515 | 1366850 |  | WIP
198 | 66 KV Talwandi Sabo Bangi Nihal Singh T-off Jiwan Singh | 5478754 | 1438596 | 2019-06-01 | w.i.p
199 | 66 KV Haripur-kura line | 5566228 | 1461565 | 2019-03-01 | 2019-11-01
200 | 66 KV Line Deviarh-Roharjagir | 5725641 | 1503423 | 2019-04-01 | 2020-03-01
201 | 220 KV Dharamkot to 66 KVS/S Masita+Fatehgarh Panjtoor SC on DC line | 5781361 | 1518054 | 2019-01-01 | 2020-01-01
202 | 66kv line mahamad khan to lohgarh | 6038553 | 1585587 | 2019-03-01 | 2019-10-01
203 | 66 KV DC line DC Tower rom wara Krishanpura Mallan line | 6051714 | 1589042 | 2019-06-01 | w.i.p
204 | 66 kv ss bhaloor to 66 kv ss kot sukhian | 6216744 | 1632376 | 2019-01-01 | w.i.p
205 | 66 KV SC on DC Line for Roshanpur T-off 66 KV Devigarh- Roharjagir | 7376781 | 1936975 | 2019-04-01 | 2020-02-01
206 | 66 KV SC On DC Line 66 KV S/S Bhasmarah T-off 66 KV Devigarh rohar | 8326811 | 2186431 |  | WIP
207 | 2nd circuit of 66 KV Line from 220 KV S/S Handiaya to 66 KV Tapa | 8607217 | 2260059 |  | WIP
208 | survey & staking of 66 kv mastewala to makhu tower line | 8723844 | 2290683 | 2017-05-01 | 2017-07-01
209 | Replacement of 66 KV HRP Line from Mallkatora to Madhir with SC/DC Tower line. | 8942508 | 2348099 | 2016-03-01 | 2020-06-01
210 | 66 kv line BOTTIANWALA MAKHU TO DAL SINGH WALA | 9518799 | 2499420 | 2018-02-01 | w.i.p
211 | 66 KV Badni-Bilaspur | 9981903 | 2621021 | 2018-02-01 | 2019-09-01
212 | Revised Deposit Estimate 66 KV line Ablowal to Thapar University, PTA. | 10778217 | 2830115 | 2019-01-01 | 2019-07-01
213 | 220 KV Maur to 66 KV Joga Ralla line | 11032922 | 2896994 | 2019-03-01 | w.i.p
214 | Ganga to Jeeda 66 kv with 0.2 sq sc on dc tower | 12945659 | 3399236 | 2019-01-01 | 2019-05-01
215 | Const. T-Off 66,KV line Passiana sanour for Sanouri adda | 16011026 | 4204131 | 2018-08-01 | 2019-06-01
216 | replacement 66kv rpl 220kv dharamkot to mastian to fathegarh panjor | 20332679 | 5338899 | 2019-02-01 | 2020-01-01
217 | 66 KV Sadiq Jhok Tehal Singh R/main line | 21246191 | 5578768 | 2019-05-01 | w.i.p
218 | Lilo 220 KV mour 66KV joga ralla 66KV chowke | 21433418 | 5627928 | 2019-05-01 | 2020-01-01
219 | 66 KV Lehargaga-Khandebad line T-off for Balran | 22238616 | 5839355 |  | WIP
220 | 66 KV Line DC on DC Devigarh to Roharjagir | 26408196 | 6934192 | 2019-04-01 | 2020-03-01
221 | 220 KV Maur to 66 KV Joga Ralla line | 26451257 | 6945498 | 2019-05-01 | w.i.p
222 | 66 KV DC Line to DC Towers frp, Sadiq Jhok Tehal Singh | 38808619 | 10190260 | 2019-05-01 | w.i.p
| Total Non- REC wporks | 446962540 | 117362195
C | Deposit Works
1 | U/G Cable GSS Moga | 2320 |  | 2019-09-01 | 2019-09-01
2 | 66KV SC line on H-Pole Moga-Dala on jal-Bar road on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV SC Line on H. pole from Moga to Dala) | 6080 |  | 2019-09-01 | 2019-09-01
3 | 66 KV Ablowal- Patiala Line from the premsis of Ghuman Singh wala | 11484 |  | 2017-05-01 | 2018-01-01
4 | 66 kv mehta to aiims | 12893 |  | 2019-01-01 | 2019-04-01
5 | survey of shifting of 66 kv line mastewala sekhuwala for nh-15 smb no 23 pg 45 | 23475 |  |  | W.I.P.
6 | Himmatpura to gehlan from nh 64/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) 66 KV SC on DC Line Himatpura-Gehlan) | 24252 |  | 2016-11-01 | 2017-12-01
7 | Deposit Work of Raising/Shifting of 66 KV SC on DC Line Himatpura- Tallewal on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703)(66 KV SC on DC Line Himatpura- Tallewal) | 24252 |  | 2016-11-01 | 2017-12-01
8 | 66KV SC on DC line Himatpura-Bilaspur on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703)(66 KV SC on DC Line from Himatpura to Balaspur) | 25546 |  | 2017-01-01 | 2017-12-01
9 | 220 KV S/S Banur to airport Mohali | 44637 |  | 2016-06-01 | 2018-10-01
10 | Raising of 66 KV H.R.P. Line Sangrur to Sunam Lehra for Electrification work of Northern Railway Xing 79/2-3 4th Xing./Raising of existing 66 KV H.R.P. Line from 220 KV BBMB Sangrur to Sunam-Lehra in connection with electrification work of Jakhel-Dhuri LDH Section of Ambala Div. Northern Railway between Section Sangrur-Sunam-Jakhal at Railway KMS 79/2-3 4th Xing | 47427 |  | 2017-11-01 | 2018-03-01
11 | 66 KV HANDAYA TO DHANULA LINE/66 KV D/C Line from 220 KV S/S Handiaya to Mehalkalan & Malwa)/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV D/C Line from 220 KV S/S Handiaya to Mehalkalan & Malwa) | 48504 |  | 2016-10-01 | 2017-12-01
12 | 66 KV Shifting Mour-Mansa Line | 56465 |  | 2018-07-01 | 2018-08-01
13 | D.W. 66 KV RP line 220 KV Sangrur to Sunam NH-64 | 65402 |  | 2016-03-01 | 2017-05-01
14 | Raising of 66 KV Line Rajpura Sarai Banjara line at Railway crossing | 65562 |  | 2019-01-01 | 2020-01-01
15 | moga to kishanpura for nh-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV SCLine on H-Pole Moga- Kisanpura) | 75990 |  | 2016-11-01 | 2017-12-01
16 | 66KV Moga-Badni H-Rail pole line on NH-71/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (33/66 KV Moga- Badni Line on H. Rail Pole) | 97978 |  | 2016-10-01 | 2018-05-01
17 | Raising of Badni Bilaspur for roarke kalan/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV S/C on S/C Towers Badni- Blaspur Line) | 99919 |  | 2016-10-01 | 2017-12-01
18 | Revised 66 KV Line Ablowal Pasiana | 103313 |  | 2018-06-01 | 2019-04-01
19 | 66 KV line from 132 KV GSS Bathinda to 66 KV GSS | 109012 |  | 2019-01-01 | 2019-04-01
20 | 66 KV Line SC on DC 220 KV S/S Handaya to IOL Chemical and Pharmeceuticals Ltd. | 133458 |  |  | W.I.P.
21 | 66 KV line Tower 2 Nos. 11 KV Feeder Dona Matar | 153077 |  | 2017-03-01 | 2017-04-01
22 | 66 Rail pole line kot koror to dagru. NH-15 | 156373 |  |  | W.I.P.
23 | 66 kvrpl ablowal to patiala line for premises of S. GHUMAN SINGH S/O KIRPAL SINGH OF VILL SIDHUWAL | 198382 |  | 2017-03-01 | 2018-01-01
24 | 66 KV HANDAYA TO BARNALA H RAIL LINE/Regarding Shifting of Electrical 33/66 KV line Four-lanning of Jalandhar-Barnala Road Section-NH-71, (New NH-703) (66 KV Handiaya to Barnala H. Pole Line) | 217945 |  | 2016-10-01 | 2017-11-01
25 | Deposit Esitmate for 66 KV S/S Malout Road Bathinda line Vardhmaan politax factory stubbing | 274464 |  | 2014-09-01 | 2015-07-01
26 | 66KV BARAN BAHADURGARH/DEVIGARH LINE RAIL POLE RVNL DEPOSIT | 281965 |  | 2015-10-01 | 2016-02-01
27 | Shifting of 66 KV Sangat Mehta Line from plot of Sulekha Garg | 320598 |  | 2017-05-01 | 2017-10-01
28 | 66 KV S/S Shaktivihar PTA to 66 KV M/S Rajindra Hospital, Patiala | 456788 |  |  | WIP
29 | 66 KV GSS Kotakpura to 66 KV Fardikot | 519563 |  | 2017-02-01 | w.i.p
30 | 66 KV S/S Mehta to 66 KV AIiMS BTI Line | 638371 |  | 2019-01-01 | 2019-04-01
31 | Raising of existing line S/S railway crossing Dhuri- Rajomajra Section-79/13-14 XING | 921955 |  | 2019-04-01 | 2019-11-01
32 | 66 KV U/G Cable Tower No. 42 to 43, 220 KV S/S kharar | 933426 |  | 2019-02-01 | 2019-04-01
33 | Deposit work of Shifting of 66 KVRajpura (Deposit Estimate for Shifting of Existing 66 KV SC on DC line from 66 KV S/S Focal point Rajpura to 66 KV S/S M/S Asian fine cement within the Land of M/S Gateway spaces Rajgarh | 1662381 |  |  | W.I.P.
34 | IGC mehta to AIIMS 66 KV line | 1681142 |  | 2019-01-01 | 2019-04-01
35 | 66 KV G/S/S kotkapura to 66 KV Faridkot | 1703512 |  | 2017-02-01 | w.i.p
36 | Shifting of 66 KV line from 220 KV S/S Rajpura to old Rajpura (Deposit Estimate for shifting of existing 66 KV line from 220 KV S/S Fajpura to 66 KV Old Rajpura and focal point Rajpura within the land of M/S Binny. | 1864514 |  | 2019-10-01 | 2019-11-01
38 | 66 KV SC on DC Tower from GIS BTI to 66 KV S/S AIIMS Bathinda | 2118196 |  | 2019-01-01 | 2019-04-01
39 | 66 KV M/S Green Plant Energy Pvt Ltd Manuke Gill Samadh Bhai line | 2814397 |  | 2019-07-01 | 2019-07-01
43 | Rail pole 132 KV G/s/s Moga to 66 KV G/S/S Focal point Moga | 15123877 |  | 2019-09-01 | 2019-09-01
44 | 66 KV SC on dC from IGC BTI to 66 KV S/S AIIMS | 18164541 |  | 2019-01-01 | 2019-04-01
| Total Deposit works | 51283436
|  | Amount | INTREST | TOTAL
| REC | 52521309 | 13790901 | 66312210
| NREC | 446962540 | 117362195 | 564324735
| DEPOSIT WORKS | 51283436 | 0 | 51283436
| TOTAL | 550767285 | 131153096 | 681920381