## Format
S.No. as per tariff | Works Category (kV) | Name of Scheme | Network Addition |  | Total Approved Cost of Scheme (Rs. Crores) | Year of Start | Estimated/ Actual year of project completion | Stage of Scheme
|  |  | Line (km) | Substation |  |  |  | DPR Submitted (Y/N) | Internal Management Approval (Y/N) | Tender Stage (In process/Completed) | Tender/EPC Contract Awarded/Signed (Y/N) | Physical Progress (%) | Financial Progress (Invoiced Amount/ Total contract amount)
Spill over works under progress from FY 2016-17
A |  | Unforeseen Expenditure on works on 2018-19
B
9 | 220 | 220 kV Goindwal Sahib- Botianwala DC line | 64.735 | 0
11 | 220 | 220 kV Nakodar-Rehanajattan DC line | 35 | 0
12 | 220 | 220 kV Mukatsar-Kotkapura DC line | 38 | 0
13 | 220 | 220 kV Makhu-Algon DC line | 50.445 | 0
14 | 220 | 220 kV Makhu-Rashiana DC line | 30 | 0
15 | 220 | 220 kV Abohar- Malout DC line | 29.994 | 0
19 | 220 | 220 kV Nakodar- Ladowal DC line | 40 | 0
20 | 220 | LILO of one ckt of Humbran - Ferozpur Road Ludhiana line at Ladowal | 17 | 0
21 | 220 | 220 kV S/S Ladowal(New) | 0 | 160 MVA, 220/66 kV T/F
23 | 220 | 220 kV S/S Kotla Jangan | 0 | Repl. of 100MVA with 160MVA, 220/66 kV T/F
24 | 220 | 220 kV S/S Maur (U/G from 132 kV) | 0 | 100 MVA, 220/66 kV T/F
29 | 220 | 220 kV S/S Kanjali | 0 | 3rd 100MVA, 220/66 kV T/F
33 | 220 | 220 kV S/S Ablowal | 0 | Addl. 100 MVA, 220/66 kV T/F
36 | 132 | 132 kV S/S Ekalgadda | 0 | Addl. 12.5 MVA, 66/11kV T/F
37 | 132 | 132 kV G.T. Road Amritsar | 0 | 2X50 MVA, 132/66kV T/Fs in place of 1X16/20 MVA & 1X20/25 MVA T/Fs
38 | 132 | 132 kV Power Colony Amritsar | 0 | Addl. 50 MVA, 66/11 kV T/F
SubTotal
New works taken in hand during 2017-18
39 | 220 | Bus Bar Protection scheme for 45 no S/Stns. (90% funding Under Power System Development Fund (PSDF), 10% amount accounted for in FY 2017-18 | 0 | 0
44 | 220 | 220 kV S/Stn Badhni Kalan (U/G from 132 kV) | 0 | 1x100MVA, 220/66 kV T/F
46 | 220 | 220 kV S/Stn Alawalpur (U/G from 132 kV) | 0 | 1x100MVA, 220/66 kV T/F
47 | 220 | LILO of one ckt. of 220 kV S/Stn BBMB, Jalandhar - 220 kV S/Stn Pong DC line (ckt-3) at 220 kV S/Stn Alawalpur | 0 | 0
49 | 220 | 220 kV S/Stn Amloh | 0 | Repl. of 1x100 MVA, 220/66 kV T/F with 1x160 MVA, 220/66 kV T/F
54 | 220 | NIFPES Systems for 31 no. 220 kV, 100 MVA T/Fs | 0 | 31 Nos.
55 | 400 | 400 kV S/S Mukatsar | 0 | 1X500MVA, 400/220 kV T/F
56 | 132 | 132 kV Verpal-Mall Mandi Line | 0 | 0
59 |  | Truck - Trailer | 0 | 200 Ton GCW
60 | 220 | 220 kV S/S Derabassi | 0 | Addl. 100MVA, 220/66 kV T/F
61 | 132 | 132 kV Shanan- Kangra- Pathankot line with new ACSR wolf conductor | 0 | 0
62 | 400 | 400 kV S/Stn. Makhu | 0 | Addl 500MVA 400/220 kV T/F
63 | 400 | Transmission System for 400 kV Rajpura Thermal Plant | 0 | Addl. Civil works at 400 kV S/Stn. Rajpura
64 | 400 | Transmission system for 400 kV Talwandi Sabo Thermal Plant | 0 | For addl. eqpt. at 400 kV S/Stn. Covered in the scheme
65 | 220 | Automation of 5 no. 220 kV Sub Stations | 0 | 220 kV S/Stns Mohali 1 &2, Kharar, Dera Bassi,Lalru
70 | 220 | LILO of 2nd ckt. of 400 kV S/S PGCIL Jalandhar-220 kV S/S Kotla Jangan (Nakodar) line at 220 kV S/S Kartarpur | 0 | 0
72 | 220 | Power System Development Fund (PSDF) scheme for second source of Battery at 220 and 132 kV S/stn.(90% funding Under PSDF, 10% amount accounted for in FY 2017-18 | 0 | 0
74 | 132 | 132 kV S/Stn Malout | 0 | Repl. of 12.5/16 MVA, 132/66 kV T/F with 1x20/25 MVA, 132/66 kV T/F
75 | 220 | 220 kV S/Stn Bangan | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F
77 | 220 | LILO of 220 kV line from 220 kV S/Stn Himmatpura to 220 kV S/Stn Jagraon at 220 kV S/Stn Ajitwal. | 0 | 0
78 | 220 | 220 kV S/Stn Ajitwal | 0 | 2 nos. Bays (in line with Sr. No. 81)
79 | 220 | 220 kV S/Stn Ferozepur Rd. Ludhiana | 0 | Extension in the control room building
84 | 220 | 220 kV S/Stn Bangan | 0 | 1 no. 66 kV line bay for 66 kV Bangan - Mandvi DC on DC line
85 | 220 | 220 kV S/Stn Patran | 0 | 1 no. 66 kV line bay for 66 kV Dirba DC on DC line
86 | 220 | 220 kV S/Stn Jadla (U/G from 132 kV) | 0 | Uplifting of old 132 kV/66 kV yard by level earth filling
88 | 220 | 220 kV S/S Rashiana | 0 | Extension of 66 kV double busbar & Shifting of 2no. 66 kV O/G line bays for 66 kV Tarn Taran ckt 1 & 66 kV Fatahabad ckt.-1
89 | 220 | 220 kV S/S Dhandhari Kalan 1 and 2 | 0 | Provision of 220 kV Double bus bar arrangement
90 | 220 | 220 kV S/S Sahnewal | 0 | Provision of making 66 kV double bus arrangement including dismantlement & erection of new towers
102 | 220 | New Civil Works in respect of 5 no. stores such as sheds, plinths and Boundry walls etc. | 0 | HR, IT, S&D Organization work
103 |  | Installation of CCTV Cameras at 5 No. stores | 0 | HR, IT, S&D Organization work
104 | 220 | Procurement of Hardwares, Server, Furniture, IT Space renovation (Civil Works) & Unforeseen Capital Expenditure | 0 | HR, IT, S&D Organization work
SubTotal
Works to be started from 2017-18
105 | 220 | 220 kV S/Stn Sultanpur | 0 | Erection of 2nd 220 kV Bus bar (Twin zebra conductor)
106 | 220 | Replacement of conductor of 220 kV line from 400 kV S/Stn Ludhiana to 220 kV S/Stn Lalton Kalan (2nd ckt) with HTLS conductor | 2.787 | 0
107 | 220 | 220 kV S/Stn Sadiq | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F
108 | 220 | 220 kV S/Stn Bajakhana | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F
109 | 220 | 220 kV S/Stn Jamsher | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F
110 | 220 | 220 kV S/Stn Ghubaya | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F
111 | 220 | 220 kV S/Stn Talwandi Bhai | 0 | Repl. of (1x16/20+ 1x10/12.5 MVA), 132/11 kV with 2x20 MVA, 66/11 kV T/Fs
112 | 220 | 220 kV S/Stn Chogawan | 0 | Addl. 2nd 160 MVA, 220/66 kV T/F
113 | 220 | 220 kV S/Stn Badal | 0 | Addl. 2nd 100MVA, 220/66 kV T/F
114 | 220 | 220 kV S/Stn Dasuya | 0 | Addl. 2nd 1x100MVA, 220/66 kV
115 | 220 | 220 kV S/Stn Badhni Kalan (U/G from 132 kV) | 0 | Replacement of existing (1x20+1x12.5) MVA, 132/11 kV with 2x20 MVA, 66/11 kV T/Fs.
116 | 220 | 220 kV S/Stn Banga (U/G from 132 kV) | 0 | 1x100 MVA, 220/132 kV T/F as spared from 220 kV S/Stn Mahilpur
117 | 220 | LILO of 220 kV Jadla - Jamsher SC line at 220 kV S/Stn Banga (Proposed) | 2 | 0
119 | 220 | 220 kV Line bays at 220 kV S/Stn Banga (Proposed) | 0 | 2 Nos. (cost of 1no. Line bay already included in s/stn.
120 | 220 | 220 kV S/Stn Sherpur (Focal Point) (U/G from 66 kV grid with 220 kV side GIS and 66 kV side Conventional) | 0 | 1x160 MVA, 220/66 kV T/F
121 | 220 | LILO of both ckts of 220 kV S/Stn Jamalpur - 220 kV S/Stn Dhandari Kalan-I line at 220 kV S/Stn Sherpur (Focal Point) | 13 | 0
122 | 220 | Replacement of conductor of 220 kV line from 400 kV S/Stn Ludhiana to 220 kV S/Stn Lalton Kalan (1st ckt) with HTLS conductor | 1.932 | 0
123 | 220 | 220 kV S/Stn Budhlada (U/G from 66 kV) | 0 | 1x160 MVA, 220/66 kV T/F
124 | 220 | 220 kV S/Stn Mansa - 220 kV S/Stn Budhlada DC Line | 40 | 0
125 | 220 | 220kV S/S Alawalpur | 0 | Repl. of existing 1X20 MVA + 1X12.5 MVA, 132/11 kV T/Fs with 2 no. 20 MVA, 66/11 kV T/Fs
126 | 220 | 220 kV S/S Patran | 0 | Extension in the S/S Control room building complex
128 | 400 | 400 kV S/Stn Doraha (New at Village Dhanansu) | 0 | 2x315 MVA, 400/220 kV T/Fs
129 | 400 | LILO of one ckt. of 400 kVJalandhar-Kurukshetra D/C line f at 400 kV Dhanansu(Quad Moose) | LILO length =5 km(approx) | 0
130 | 400 | (i) 400 kV Bays (ii) 220 kV Bays at 400 kV S/Stn Doraha | 0 | (i) 4 Nos. (ii) 6 Nos.
131 | 220 | 220 kV Banur-Mohali (GMADA) DC line | 4 km Line Length ACSR ZEBRA Conductor | 0
132 | 220 | 220 kV DC line from 400 kV Grid near Doraha to 220 kV Kohara | 12 km (approx.) Line Length / 420 sq mm DC ACSR Zebra | 0
133 | 220 | 220 kV DC line from 400 kV Grid near Doraha to 220 kV Doraha | 10 km (approx.)/ 420 sq mm DC ACSR Zebra | 0
134 | 220 | 220 kV DC line from 400 kV Grid near Doraha to 220 kV Ikolaha | 10 km (approx.)/ 420 sq mm DC ACSR Zebra | 0
135 | 220 | 220 kV Bays (2Nos. at 220 kV Ikolaha, 2 Nos. at Doraha, 2Nos. at Kohara (220 kV bus)and 2 no. ICT bays | 0 | 8 Nos.
136 | 220 | LILO of 220 kV S/Stn Mansa - Sunam (SC) at 400 kV S/Stn Patran (220 kV bus). | 40 km (approx.) Line Length / 1xDC with 420 sq mm ACSR (Zebra) | 0
137-140 |  | 1. Aug/Strengthening of bus bars 2. Extension in Switchyard buildings, Provision for AC etc. 3. Provision for Reactive Compensation 4. Addition of bays/system strengthening required on account of RE generation | 0 | 0
141 | 220 | Replacement of 11 kV VCBs with SCADA Complaint VCBs at various sub stations in the city of Ludhiana, Jalandhar & Amritsar | 0 | Replacement of 11 kV VCBs with SCADA Complaint VCBs at various sub stations in the city of Ludhiana, Jalandhar & Amritsar
142 | 400 | Replacement of Disc Insulators of 400 kV PSTCL lines with Polymer Insulators | 0 | 0
SubTotal
Works planned for 2018-19
143 | 220 | 220 kV DC line from 220 kV S/Stn Gaunsgarh to 220 kV S/Stn Ladhowal. | 18 | 0
144 | 220 | 220 kV S/Stn Alawalpur | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F
145 | 220 | 220 kV S/Stn Maur | 0 | Addl. 100MVA, 220/66 kV T/F
146 | 220 | 220 kV Sahnewal | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F
147 | 220 | 220 kV S/Stn Kharar | 0 | Repl. of (16/20+20) MVA, 132/11 kV with 2x20 MVA, 66/11 kV T/F
148 | 220 | 220 kV S/Stn Lalru | 0 | Repl. of 1x100 MVA, 220/66 kV T/F with 1x160 MVA, 220/66 kV T/F
149 | 220 | 220 kV S/Stn Tibber | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F
150 | 220 | 220 kV S/Stn Udhoke | 0 | Addl. 2nd 160 MVA, 220/66 kV T/F
151 | 220 | 220 kV S/Stn Hoshiarpur | 0 | Addl. 2nd 160 MVA, 220/66 kV T/F
152-155 |  | 1. Aug/Strengthening of bus bars 2. Extension in Switchyard buildings, Provision for AC etc. 3. Provision for Reactive Compensation 4. Addition of bays/system strengthening required on account of RE generation | 0 | 0
156 |  | Partial Discharge Set | 0 | 0
161 | 220 | 220 kV Jamsher | 0 | Augmentation of existing 220 kV twin zebra Double Bus- Bar Conductor with quadruple zebra double bus bar conductor
162 | 220 | 220 kV Kotla Jangan | 0 | Augmentation of existing 220 kV twin zebra Single Bus- Bar Conductor with quadruple zebra Single bus bar conductor
163 | 220 | 132 kV Samadh Bhai | 0 | Construction of a new Switch House Building at a new raised level
164 | 132 | 132 kV Pathankot | 0 | Construction of a new control- room building by replacing old control - room building
165 | 220 | 220 kV Mohali | 0 | 1 no O/G Bay for 66 kV Sub- Station Phase 8-B Mohali ckt II
SubTotal
Works planned for 2019-20
166 | 220 | 220 kV S/Stn Bhawanigarh | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F
167 | 220 | 220 kV S/Stn Jadla | 0 | Addl. 2nd 100MVA, 220/66 kV T/F
168 | 220 | 220 kV S/Stn Botianwala (Thatha Sahib) | 0 | Addl. 3rd 160 MVA, 220/66 kV T/F
169 | 220 | 220 kV S/Stn Majitha | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F
170 | 132 | 132 kV S/Stn Pathankot | 0 | Repl. of 1x12.5/16 MVA, 132/66-33 kV T/F with 1x20/25 MVA, 132/66 kV T/F
171 | 132 | 132 kV IGC, Bathinda | 0 | Repl. of 1x25 MVA, 132/66 kV T/F with 1x50 MVA, 132/66 kV T/F
172-175 |  | 1. Aug/Strengthening of bus bars 2. Extension in Switchyard buildings, Provision for AC etc. 3. Provision for Reactive Compensation 4. Addition of bays/system strengthening required on account of RE generation | 0 | 0
176 | 220 | Replacement of Existing conductor of 220 kV Mohali-I - Mohali-II line | 13 | 0
177 | 220 | 220 kV S/Stn Fazilka (U/G from 66 kV) | 0 | 0
178 | 220 | 400 kV S/Stn Mukatsar - 220 kV S/Stn Fazilka 220 kV DC line | 0 | 0
179 | 220 | 220 kV Bays | 0 | 0
180 | 220 | 220 kV DC line from 400 kV Jalandhar (PGCIL) to 220 kV Kartarpur | Augmentation of existing conductor of both circuits with HTLS conductor of min 1200 A capacity | 0
182 |  | Un-foreseen emergency works | 0 | 0
SubTotal
New works to be started in 2019-20
1a | 132 | 132 kV Faridkot –Kotkapur-2 SC link (Amendment no. 16 / 2018-19) | 30 | 0
1b | 132 | 2no. 132 kV line bays (one at each end) | 0 | 2no. 132 kV line bays (one at each end)
2a | 132 | 132 kV Sihora-132 kV Seh SC line | 31 | 0
2b | 132 | 2no. 132 kV line bays (one at each end) | 0 | 2no. 132 kV line bays (one at each end)
3a | 400 | 400 kV S/Stn Nakodar (2x315 MVA, 400/220 kV) (Amendment no. 43 /2018-19) | 0 | Replacement of 1x315 MVA, 400/220 kV ICT with 1x500 MVA, 400/220 kV ICT
3b | 400 | Cost of dismantlement of 1x315 MVA, 400/220 kV ICT at 400 kV Nakodar | 0 | Cost of dismantlement of 1x315 MVA, 400/220 kV ICT at 400 kV Nakodar
4a | 220 | 220 kV S/S Beas (new) in the premises of Radha Soami Satsang Beas. (Amendment no. 01 /2019-20) | 0 | 2 x 100 MVA, 220/132 kV Auto T/f.
4b | 220 | 220 kV S/S Beas (new) in the premises of Radha Soami Satsang Beas. (Amendment no. 01 /2019-20) | 0 | 2 Nos. ** 2 Nos. 220 kV bays at 400 kV PGCIL Jalandhar fall in the preview of PGCIL.
4c | 220 | 220 kV line bays | 0 | 5 Nos. considering Ekalgadda T-off conversion to LILO
4d | 132 | 132 kV Bays | 33 | 0
4e | 220 | 400 kV PGCIL Jalandhar – 220 kV Beas (New) line. | 14 | 0
4f | 220 | 220 kV Beas (New) – 220 kV Butari line. | 28 | 0
4g | 132 | 132 kV Beas – 132 kV Ekalgada line. | 0 | For making connectivity of 132kV bus of newly created 220kV S/S Beas to existing 132 kV S/s Beas.
4i | 132 | (i) 2 Nos. 132kV towers dismantlement & 3 Nos. towers to be erected. | Stringing of 2nd Ckt from 132kV Ekalgada to T-off point | 0
4k | 132 | (ii) Conversion of 132kV Tarn Taran – Butari T-off at Ekalgada into 132 kV Tarn Taran – Butari LILO at 132kV Ekalgada. | 0 | 0
5 | 220 | 400 kV Rajpura–220 kV Bassi Pathana DC Link. (Amendment no. 13 /2019-20) | 220kV DC Line from 400 kV Rajpura to 220 kV Bassi-Pathana (Line length 2 X 20 km)'. | 0
|  | 4no. 220 kV Bays | 0 | 0
|  | 220 kV Side bus extension arrangement to be made at 400 kV Rajpura for providing sitable space for 2 Nos 220 kV Bays | 0 | 0
6 |  | Solar system on roof top. | 0 | 0
7 |  | OPGW | 0 | 0
8 | 220 | 220 kV Patti | 0 | Replacement of 1x100 MVA, 220/66 kV to 1x160 MVA, 220/66 kV T/F.
9 | 220 | 220 kV Ferozepur road Ludhaiana | 0 | Replacement of 1x100 MVA, 220/66 kV to 1x160 MVA, 220/66 kV T/F.
10 | 220 | 220 kV Dhandari Kalan 2 | 0 | 2x160 MVA, 220/66 kV T/F at new location to be added(with complete newICT bays
11 | 220 |  | 0 | dismantlement of 2x100 MVA T/F for creating space for double bus bar
12 | 220 |  | 0 | interconnecting 66 kV double bus bar of of dhandari kalan 1- dhandari kalan 2
Total Spillover
P&M Works
93 | 400 | To Modernise the hotline work by use of Diagnostic techniques to decrease the outage in transmission system of PSTCL.
94 | 400 | To provide SAS based DRs and ELs at six 220kV S/stns as per requirements of IEGC and SGC and comply with 3rd party protection audit by CPRI.
95 | 400 | To provide DRs and ELs in 220kV S/stns of PSTCL to comply with IEGC, SGC and 3rd party protection audit by CPRI.
96 | 400 | To procure testing Equipment to check healthiness of OPGW channels and Ethernet Switch Network in Substation autmation.
97 | 400 | Tan-Delta Measurement Set (7 No.)
98 | 220 | Tan Delta and Resistive kit for testing of Transformer oil.
99 | 220 | PT/CVT testing kit for ODTL
100 | 400 | Remote Control Operation of 400kV S/Stns Mukhtsar, Nakodar and Makhu
101 | 220 | Insulation Tester for new Substations (25 No.)
102 | 400 | Online partially discharge monitaring kit equipment for 400 kV ICT at 400kV S/s.(14 No.)
103 | 220 | CRM- Contact Resistance measurement meter for maintenance gang
104 | 400 | Upgrading of 2 No. 3 Phase Relay testing kits of 400kV protection Hub and SAP Hub with CMGPS (testing kit synchronising equipment and software) for end to end testing as per recommandation of 3rd party protection audit alongwith advance teasplay software.
105 | 220 | Loader cum Crane for Amritsar Circle
106 | 220 | Mobile oil filteration sets under P&M Circle (4 No., 6KL/H)
107 | 220 | Construction of Security Huts at 220/132kV Sub stations.
108 | 220 | Refixing of UC Fencing at top toe wall to safeguard yard area from fire.
109 | 400 | Providing Plinths for 2 sets(20 No.) of ERS-Emergency Restoration System Towers at 400kV S/S Rajpura,Nakodar and 220kV Muktsar
110 | 220 | Providing RCC Roads in 220kV S/S to facilitate movement of heavy vehicle loaded with equipment.
111 | 220 | Providing PCC in the yard area in 220kV S/s
112 |  | Providing AC and Furniture at kangra Rest House

## Spillover Escalation
S.No. as per tariff | Works Category (kV) | Name of element | Category/Type of Works | Year of Start | Network Addition |  | Escalation |  |  |  | Reason for Escalation
[5 empty] | Line (km) | Substation | Hard Cost | Total | Hard Cost (%) | Total (%)
A |  | Unforeseen Expenditure on works on 2018-19 |  |  |  |  | 10 | 11.68 | 0% | 0%
39 | 220 | Bus Bar Protection scheme for 45 no S/Stns. (90% funding Under Power System Development Fund (PSDF), 10% amount accounted for in FY 2017-18 | Spillover | FY 2017-18 | 0 | 0 | 0 | -0.01 | 0% | -0.4762%
60 | 220 | 220 kV S/S Derabassi | Spillover | FY 2017-18 | 0 | Addl. 100MVA, 220/66 kV T/F | 1.1056 | 1.39 | 12.28% | 13.4%
62 | 400 | 400 kV S/Stn. Makhu | Spillover | FY 2017-18 | 0 | Addl 500MVA 400/220 kV T/F | 12.6 | 13.92 | 74.12% | 71.02%
89 | 220 | 220 kV S/S Dhandhari Kalan 1 and 2 | Spillover | FY 2017-18 | 0 | Provision of 220 kV Double bus bar arrangement | -0.5 | -0.55 | -5.417% | -5.169%
90 | 220 | 220 kV S/S Sahnewal | Spillover | FY 2017-18 | 0 | Provision of making 66 kV double bus arrangement including dismantlement & erection of new towers | 0.54272 | 0.74 | 24.67% | 29.25%
102 | 220 | New Civil Works in respect of 5 no. stores such as sheds, plinths and Boundry walls etc. | Spillover | FY 2017-18 | 0 | HR, IT, S&D Organization work | -1.2 | -1.53 | -24% | -26.56%
104 | 220 | Procurement of Hardwares, Server, Furniture, IT Space renovation (Civil Works) & Unforeseen Capital Expenditure | Spillover | FY 2017-18 | 0 | HR, IT, S&D Organization work | 2.54 | 3.06 | 93.04% | 97.14%
107 | 220 | 220 kV S/Stn Sadiq | Spillover | FY 2017-18 | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F | 0 | 0.4 | 0% | 3.937%
108 | 220 | 220 kV S/Stn Bajakhana | Spillover | FY 2017-18 | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F | 0.05 | 0.46 | 0.5675% | 4.528%
110 | 220 | 220 kV S/Stn Ghubaya | Spillover | FY 2017-18 | 0 | Repl. of 100 MVA with 160 MVA, 220/66 kV T/F | 0 | 0.4 | 0% | 3.937%
116 | 220 | 220 kV S/Stn Banga (U/G from 132 kV) | Spillover | FY 2017-18 | 0 | 1x100 MVA, 220/132 kV T/F as spared from 220 kV S/Stn Mahilpur | 4.0908 | 5.22 | 49.95% | 55.3%
119 | 220 | 220 kV Line bays at 220 kV S/Stn Banga (Proposed) | Spillover | FY 2017-18 | 0 | 2 Nos. (cost of 1no. Line bay already included in s/stn. | 0 | 0.04 | 0% | 2.685%
120 | 220 | 220 kV S/Stn Sherpur (Focal Point) (U/G from 66 kV grid with 220 kV side GIS and 66 kV side Conventional) | Spillover | FY 2017-18 | 0 | 1x160 MVA, 220/66 kV T/F | 4 | 4.92 | 39.22% | 41.84%
121 | 220 | LILO of both ckts of 220 kV S/Stn Jamalpur - 220 kV S/Stn Dhandari Kalan-I line at 220 kV S/Stn Sherpur (Focal Point) | Spillover | FY 2017-18 | 13 | 0 | -1.2 | -1.33 | -28.57% | -27.48%
123 | 220 | 220 kV S/Stn Budhlada (U/G from 66 kV) | Spillover | FY 2017-18 | 0 | 1x160 MVA, 220/66 kV T/F | 15.65 | 18.23 | 185.6% | 187.7%
124 | 220 | 220 kV S/Stn Mansa - 220 kV S/Stn Budhlada DC Line | Spillover | FY 2017-18 | 40 | 0 | 0 | 0.07 | 0% | 0.3332%
128 | 400 | 400 kV S/Stn Doraha (New at Village Dhanansu) | Spillover | FY 2017-18 | 0 | 2x315 MVA, 400/220 kV T/Fs | 4.96 | 6.41 | 14.74% | 16.52%
129 | 400 | LILO of one ckt. of 400 kVJalandhar-Kurukshetra D/C line f at 400 kV Dhanansu(Quad Moose) | Spillover | FY 2017-18 | LILO length =5 km(approx) | 0 | 5.04 | 5.85 | 67.56% | 68.02%
130 | 400 | (i) 400 kV Bays (ii) 220 kV Bays at 400 kV S/Stn Doraha | Spillover | FY 2017-18 | 0 | (i) 4 Nos. (ii) 6 Nos. | 16.39 | 19.1 | 251% | 253.7%
131 | 220 | 220 kV Banur-Mohali (GMADA) DC line | Spillover | 0 | 4 km Line Length ACSR ZEBRA Conductor | 0 | 1.66 | 1.86 | 118.6% | 115.5%
132 | 220 | 220 kV DC line from 400 kV Grid near Doraha to 220 kV Kohara | Spillover | 0 | 12 km (approx.) Line Length / 420 sq mm DC ACSR Zebra | 0 | 1.97 | 2.39 | 27.36% | 28.8%
133 | 220 | 220 kV DC line from 400 kV Grid near Doraha to 220 kV Doraha | Spillover | 0 | 10 km (approx.)/ 420 sq mm DC ACSR Zebra | 0 | 0.44 | 0.58 | 6.111% | 6.988%
134 | 220 | 220 kV DC line from 400 kV Grid near Doraha to 220 kV Ikolaha | Spillover | 0 | 10 km (approx.)/ 420 sq mm DC ACSR Zebra | 0 | 0.44 | 0.58 | 6.111% | 6.988%
135 | 220 | 220 kV Bays (2Nos. at 220 kV Ikolaha, 2 Nos. at Doraha, 2Nos. at Kohara (220 kV bus)and 2 no. ICT bays | Spillover | FY 2017-18 | 0 | 8 Nos. | 6.56 | 7.73 | 164% | 167.7%
136 | 220 | LILO of 220 kV S/Stn Mansa - Sunam (SC) at 400 kV S/Stn Patran (220 kV bus). | Spillover | FY 2017-18 | 40 km (approx.) Line Length / 1xDC with 420 sq mm ACSR (Zebra) | 0 | 8.08 | 9.59 | 35.94% | 37.01%
137-140 |  | 1. Aug/Strengthening of bus bars 2. Extension in Switchyard buildings, Provision for AC etc. 3. Provision for Reactive Compensation 4. Addition of bays/system strengthening required on account of RE generation | Spillover (refer Annexure C1) | 0 | 0 | 0 | 2.6278 | 4.21 | 15.46% | 21.48%
142 | 400 | Replacement of Disc Insulators of 400 kV PSTCL lines with Polymer Insulators | Spillover | 0 | 0 | 0 | 67 | 79.03 | 268% | 274.2%
143 | 220 | 220 kV DC line from 220 kV S/Stn Gaunsgarh to 220 kV S/Stn Ladhowal. | Spillover | FY 2018-19 | 18 | 0 | -2.03 | -0.81 | -14.1% | -4.88%
152-155 |  | 1. Aug/Strengthening of bus bars 2. Extension in Switchyard buildings, Provision for AC etc. 3. Provision for Reactive Compensation 4. Addition of bays/system strengthening required on account of RE generation | Spillover (refer Annexure C1) | FY 2018-19 | 0 | 0 | 17.3754 | 21.32 | 102.2% | 108.8%
163 | 220 | 132 kV Samadh Bhai | Spillover | FY 2018-19 | 0 | Construction of a new Switch House Building at a new raised level | 0.05 | 0.07 | 4.348% | 5.303%
164 | 132 | 132 kV Pathankot | Spillover | FY 2018-19 | 0 | Construction of a new control- room building by replacing old control - room building | 0.35 | 0.46 | 30.43% | 34.85%
166 | 220 | 220 kV S/Stn Bhawanigarh | Spillover | FY 2019-20 | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F | 3.11 | 3.45 | 71.82% | 69.14%
167 | 220 | 220 kV S/Stn Jadla | Spillover | FY 2019-20 | 0 | Addl. 2nd 100MVA, 220/66 kV T/F | 3.11 | 3.43 | 71.82% | 68.74%
168 | 220 | 220 kV S/Stn Botianwala (Thatha Sahib) | Spillover | FY 2019-20 | 0 | Addl. 3rd 160 MVA, 220/66 kV T/F | 4.35 | 4.81 | 73.73% | 70.74%
169 | 220 | 220 kV S/Stn Majitha | Spillover | FY 2019-20 | 0 | Addl. 2nd 100 MVA, 220/66 kV T/F | 3.26 | 3.61 | 75.29% | 72.34%
170 | 132 | 132 kV S/Stn Pathankot | Spillover | FY 2019-20 | 0 | Repl. of 1x12.5/16 MVA, 132/66-33 kV T/F with 1x20/25 MVA, 132/66 kV T/F | 0.05 | 0.05 | 23.81% | 20.83%
171 | 132 | 132 kV IGC, Bathinda | Spillover | FY 2019-20 | 0 | Repl. of 1x25 MVA, 132/66 kV T/F with 1x50 MVA, 132/66 kV T/F | 3.38 | 4.1 | 1878% | 1952%
172-175 |  | 1. Aug/Strengthening of bus bars 2. Extension in Switchyard buildings, Provision for AC etc. 3. Provision for Reactive Compensation 4. Addition of bays/system strengthening required on account of RE generation | Spillover (refer Annexure C1) | FY 2018-19 | 0 | 0 | 26.5386 | 32.85 | 156.1% | 167.6%
176 | 220 | Replacement of Existing conductor of 220 kV Mohali-I - Mohali-II line | Spillover | FY 2020-21 | 13 | 0 | 25.96 | 30 | 2596% | 2609%
177 | 220 | 220 kV S/Stn Fazilka (U/G from 66 kV) | Spillover | FY 2019-20 | 0 | 0 | 21.8 | 25.39 | 2180% | 2208%
178 | 220 | 400 kV S/Stn Mukatsar - 220 kV S/Stn Fazilka 220 kV DC line | Spillover | FY 2019-20 | 0 | 0 | 21.47 | 25 | 2147% | 2174%
179 | 220 | 220 kV Bays | Spillover | FY 2019-20 | 0 | 0 | 4.78 | 5.48 | 956% | 961.4%
180 | 220 | 220 kV DC line from 400 kV Jalandhar (PGCIL) to 220 kV Kartarpur | Spillover | FY 2020-21 | Augmentation of existing conductor of both circuits with HTLS conductor of min 1200 A capacity | 0 | 31 | 36.06 | 618.8% | 625%
Total | [6 empty] | 327.4 | 389.71 | 95.85% | 98.98%